## NCR
2022-01-25 | [10 empty] | For Basha
NCR No | Date raised | Train Impacted | Sub-system | Description of issue | Responsibility | Impact | Root cause | Correction required | Status | Comments/Progress/Evidence | NCR Opened Week | NCR Closed Week | NCR Closed date | NCR Type
188667 | 2021-04-07 | All | PACIS | D-TCCU master doesnt work | STE - VBN | Low | SW issue | Issue to be resloved with STR5.6.1 | Closed |  | 15 |  |  | SQ NCR
188673 | 2021-04-08 | All | PACIS | N-PEI not working (speech) | STE - VBN | Medium | Hw : Repair at STEE site (Change out 3-port switch card) Sw : Repair at Riyadh | Hw : Repair at STEE site Sw : Repair at Riyadh | Closed |  | 15 |  |  | SQ NCR
188791 | 2021-04-08 | All | PACIS | G-NVR Solder | STE - VBN | Medium | Hw issue, quality of soldering of NVR components | Hw issue, Retrofit by STEE sent back to Riyadh. | Closed |  | 15 |  |  | SQ NCR
192367 | 2021-05-19 | All | PACIS | A-issue LCD brightness | STE - VBN | Low | Issue 2, 3 and 1 : Sw & Issue 4: hw- rough handling | SW:Define and implement contrast checking as per the sw release note | Closed | Issue is closed SW: SW release note 5.6.1 HW: DCU4 repaired by STE in Riaydh | 21 |  |  | SQ NCR
192374 | 2021-05-19 | All | PACIS | B-LCD (LID) white screen | STE - VBN | Low | SW Issue: damage of memory flash | Repair by STEE / installation Correction of SMARC module by 5.6.1 | Closed |  | 21 |  |  | SQ NCR
192376 | 2021-05-19 | All | PACIS | J-Display 18.5 not working | STE - VBN | Low | Bad SW installation. | Re instal Sw | Closed |  | 21 |  |  | SQ NCR
192376 | 2021-05-19 | All | PACIS | K-Display 18.5 working loss com | STE - VBN | Low | Several hardware issues | Replacement of faulty hardware parts | Closed |  | 21 |  |  | SQ NCR
192379 | 2021-05-19 | All | PACIS | L-SWD Half | STE - VBN | Low | Hardware issue | Repair/replacement of the AD board | Closed |  | 21 |  |  | SQ NCR
192707 | 2021-05-19 | All | OBCN | E-PAPIS in UM | STE - VBN | Low | netbox configuration issue | Upload with new software V3.8.0 | Closed | Low priority , no impact on sys demo and trial run | 21 |  |  | SQ NCR
192708 | 2021-05-19 | All | PACIS | F-Fault loss com (TCCU) | STE - VBN | Medium | SW task stopped which is not normal and TCCU is not seen by ISM | To be corrected by 5.6.1 | Closed |  | 21 |  |  | SQ NCR
192709 | 2021-05-19 | All | PACIS | H-NVR power supply | STE - VBN | Medium | Hw issue, power supply component defective | Retrofit by Riyadh. . | Closed |  | 21 |  |  | SQ NCR
192711 | 2021-05-19 | All | PACIS | I-NVR mask camera | STE - VBN | Low | SW issue | Correction to be implemented in STR571 | Open | 22-Dec-2021: Correction will be implemented in STR 5.7.2 (to be confirmed) 18/11/21 : Correction implemented in STR571 : tests to be done in dynamic mode @Charaf to check when the tests can be performed. | 21 |  |  | SQ NCR
192713 | 2021-05-19 | All | PACIS | O-PEI power off | STE - VBN | Medium | Sw issue: corruption of memory | New software STR 5.61 to be installed - For new issues with such problems it can be corrected with STR 5.6.1 | Closed |  | 21 |  |  | SQ NCR
192713 | 2021-05-17 | All | PACIS | U-SWD White screen | STE - VBN | Low | Bad SW installation. | Reinstall the last PACIS release | Closed |  | 21 |  |  | SQ NCR
192714 | 2021-05-19 | All | PACIS | P-PEI not stable | STE - VBN | Low | Bad SW installation. | Reinstall the last PACIS release | Closed |  | 21 |  |  | SQ NCR
192716 | 2021-05-17 | All | PACIS | S-SW central upload | STE - VBN | Low | Analysis to start, problem with PST alstom tool. | Use only the software update tool provided by STE | Closed |  | 21 |  |  | SQ NCR
192717 | 2021-05-19 | All | PACIS | T-Eqpmt contain old SW content | STE - VBN | Low | SW installation tool issue. | Sw Clean up in STR5.6.1 | Closed | 5.6.1 implemented | 21 |  |  | SQ NCR
196402 | 2021-06-22 | 615 | CVS | CVS MF Transformer terminal and cables burned. | CRL | Low | litz cables fastenings found loose and out of torque | Verify and retorque all the fastenings of litz cables of the CVS transformer terminals which are out of torque | Closed | 138 CVS(100%) have been inspected and the re-marking and retorquing has been done for the incorrect ones. | 26 |  |  | SQ NCR
196626 | 2021-06-24 | 424 | CVS | Internal short circuit CVS 3-phase output contactor | CRL | High | to be updated once root cause is provided by CRL | 1) Replace the ouput 3-phase output contactor 2) Implement corrective actions once they are provided by CRL | Closed | Removed, replaced with new output contactor. Parts sent to CRL, Root cause and corrective actions under investigation. This NCR will be managed through the portal. | 26 |  |  | SQ NCR
199832 | 2021-07-25 | 516 | CVS | Internal short circuit in CVS invertor power module | CRL | Low | >>wrong connection for current sensor feedback. wiring found wrong connection between SI_11W13 bus bar for SI_11B02(MesUrsOutInv) and SI_11W14 bus bar for SI_11B01 (MesUrtOutInv). >SI_11W13 bus bar have one cable (11P1700_032B) / should have 2 feedback cable. >SI_11W14 bus bar have two cable (11P1700_031B and 11P1700_031C) / should have one feedback cable only. | install correctly by referring to AKD0001916304_K schematic | Closed | NCR to be closed officially in quality portal refering to the corrective actions taken and the parts replaced. | 31 |  |  | SQ NCR
202239 | 2021-08-23 | All | PACIS | C-TCU card offline in TCN | STE - VBN | Medium | automatic software installation should have been preferred instead of manual installation | SW to be reinstalled (14 units done – topic closed for now): | Closed |  | 35 |  |  | SQ NCR
203806 | 2021-05-19 | All | PACIS | M-SWD working loss comm | STE - VBN | Low | Analysis to start, problem with PST alstom tool. | Use only the software update tool provided by STE | Closed |  | 21 |  |  | SQ NCR
203809 | 2021-09-07 | All | PACIS | Q-DaisyChain | STE - VBN | Low | HW issue | Send to STE for repair | Closed |  | 37 |  |  | SQ NCR
203810 | 2021-09-07 | All | PACIS | R-LCD (LID) working loss com | STE - VBN | Low | Analysis to start, problem with PST alstom tool. | Use only the software update tool provided by STE | Closed |  | 37 |  |  | SQ NCR
220211 | 2022-01-05 | 603, 601 | Brakes | Air leakage is observed from the spring brake part. | FT | Low | To be investigated with supplier Faiveley | Need to replace the Brake Unit With Parking Brake | Open | Supplier to provide the investigation report with the rootcause and corrective actions | 2 |  |  | SQ NCR
NCR0001 | 2017-07-09 | 403 | Electrical wiring | Connector broken | KTW | High | Manufcaturing Defect | Replace the connector | Closed |  | 28 |  |  | Internal NCR
NCR0002 | 2017-07-09 | 501 | Windows | Wave on sealing rubber of the window | KTW | Low | Manufcaturing Defect | Correct during retroft, Replace the wavy rubber | Closed |  | 28 |  |  | Internal NCR
NCR0003 | 2017-07-09 | 501 | Bogie | Rust on the head bolster. | Le Creusot | Low | Just a small grease on the joint of the lifting plate | Cleaning of the grease, No effect on the quality | Closed |  | 28 |  |  | Internal NCR
NCR0004 | 2017-07-09 | 501 | Battery | Damaged Label in the batterie box. | Hoppecke | Low | Label damaged during manufacturing | close duering retrofit of the battery | Closed |  | 28 |  |  | Internal NCR
NCR0005 | 2017-07-25 | 604 | Electrical wiring | Damaged connector | KTW | Low | Damaged during transport | Replace the connector | Closed |  | 30 |  |  | Internal NCR
NCR0006 | 2017-08-17 | 605 | Gangway | Problem with the internal gangway fitting. | KTW | High | Manufcaturing Defect | Correct during retroft, Replace | Closed |  | 33 |  |  | Internal NCR
NCR0007 | 2017-08-17 | 605 | Carbody | Transsfert of blue paint on the car. | KTW | Low | Issue happened during transport | Repaint | Closed |  | 33 |  |  | Internal NCR
NCR0008 | 2017-08-17 | 605, 502 | Coupler | Missing socket join. | KTW | High | Missing Item during delivery | order and fix the socket join | Closed | We received 2 extra sockets, then now all the train received have well the socket join inside the box. | 33 |  |  | Internal NCR
NCR0009 | 2017-08-21 | 403 | Carbody | Cocconing damage (explose like a balloon) | KTW | Low | Transport materials affected the quality of the paint | Repaint | Closed |  | 34 |  |  | Internal NCR
NCR0010 | 2017-08-21 | 403 | Windows | Glue on the windows | KTW | Low | Transport materials affected the quality of the paint | Cleaning and window polishing | Closed |  | 34 |  |  | Internal NCR
NCR0011 | 2017-08-21 | 606 | Coupler | Reccurent problem with the jumper cable clamp | KTW | Low | Manufcaturing Defect | Replace | Closed |  | 34 |  |  | Internal NCR
NCR0012 | 2017-08-21 | 606 | Bogie | Problem of the boggie painting | Le Creusot | Low | Manufcaturing Defect | Repaint | Closed |  | 34 |  |  | Internal NCR
NCR0013 | 2017-09-25 | GEN | Bogie | Lenght and installationof hose | Le Creusot | Low | Manufcaturing Defect | Rearrange the hose length (cut) | Closed |  | 39 |  |  | Internal NCR
NCR0014 | 2017-09-25 | GEN | Gen | missing parts on train | KTW | Low | Missing during delivery | Receive and fix during the retrofit | Closed |  | 39 |  |  | Internal NCR
NCR0015 | 2017-09-25 | GEN | Gen | Sanding hose issues | KTW | Low | Manufcaturing Defect | Hose are to be cut accordingly and the clamp to be replaced | Closed |  | 39 |  |  | Internal NCR
NCR0016 | 2017-10-03 | 406 | Doors | Door scratch during transportation | KTW | Low | Door scratch during transportation | Repaint | Closed |  | 40 |  |  | Internal NCR
NCR0017 | 2017-10-05 | 504 | Coupler | Missing cable clamps | KTW | Low | Missing during delivery | Receive and fix during the retrofit | Closed |  | 40 |  |  | Internal NCR
NCR0018 | 2017-10-05 | 607 | Carbody | The thread of screw damaged inside the carbody | KTW | Low | Mishandling during installation | Replace | Closed |  | 40 |  |  | Internal NCR
NCR0019 | 2017-10-05 | 603 | Interior | Missing passenger lighting | KTW | Low | Missing during delivery | Receive and fix during the retrofit | Closed |  | 40 |  |  | Internal NCR
NCR0020 | 2017-10-05 | 601 | LV | Broken bolt and the thread of screw of the LV box internal door. | KTW | Low | Mishandling during installation | Replace | Closed |  | 40 |  |  | Internal NCR
NCR0218 | 2021-06-21 | 410 | PACIS | TCCU failure | STE - VBN | High | TCCU malfunction | Replace TCCU | Closed |  | 26 |  |  | Internal NCR
NCR0219 | 2021-06-22 | 601 | Doors | Door not open | KN | High | Relay malfunction | Replace relays | Closed |  | 26 |  |  | Internal NCR
NCR0220 | 2021-05-09 | 615 | CVS | CVS MF Transformer terminal and cables burned. | CRL | High | transformer failure | Replace CVS box | Closed |  | 20 |  |  | Internal NCR
NCR0221 | 2021-06-22 | 410 | PACIS | TCCU failure | STE - VBN | High | NCR cancelled | NCR cancelled | Cancelled |  | 26 |  |  | Internal NCR
NCR0222 | 2021-06-24 | 417 | PACIS | LEDI4 Error display | STE - VBN | Low | Software corrupted | Replace LEDI4 | Closed |  | 26 |  |  | Internal NCR
NCR0223 | 2021-06-27 | TS-L4-6 | Electrical wiring | Many wires damage | Alstom | High | Roof panel grinding wires when frequent opening is causing earthing | Replace and dress the wires properly | Closed |  | 27 |  |  | Internal NCR
NCR0224 | 2021-06-27 | 418 | PACIS | SWD fail to start up | STE - VBN | Low | to beupdated once root cause is provided by CRL | Replace the part | Closed |  | 27 |  |  | Internal NCR
NCR0225 | 2021-03-02 | 606 | Windows | Damaged train wipers | Alstom | Low | The horizontal brush of Auto wash plant was touching the train wiper during four cars washing. | 1)The Supplier has to modify the software of the vehicle washing machine (the software version of CPU I is #V112--> Done). 2) Replace the broken wipers | Open | 1) the software version of CPU Installed is #V112--> Done 2)Wipers need to be replaced --Target 29-Dec-2021 | 10 | 0 |  | Internal NCR
NCR0226 | 2021-03-02 | 604 | Windows | Damaged train wipers | Alstom | Low | The horizontal brush of Auto wash plant was touching the train wiper during four cars washing. | 1)The Supplier has to modify the software of the vehicle washing machine (the software version of CPU I is #V112--> Done). 2) Replace the broken wipers | Open | 1) the software version of CPU Installed is #V112--> Done 2)Wipers need to be replaced --Target 29-Dec-2021 | 10 | 0 |  | Internal NCR
NCR0227 | 2021-03-02 | 416 | Windows | Damaged train wipers | Alstom | Low | The horizontal brush of Auto wash plant was touching the train wiper during four cars washing. | 1)The Supplier has to modify the software of the vehicle washing machine (the software version of CPU I is #V112--> Done). 2) Replace the broken wipers | Open | 1) the software version of CPU Installed is #V112--> Done 2)Wipers need to be replaced --Target 29-Dec-2021 | 10 | 0 |  | Internal NCR
NCR0228 | 2021-06-28 | 418 | PACIS | SWD fail to start up | STE - VBN | Low | to beupdated once root cause is provided by CRL | Replace the part | Closed |  | 27 |  |  | Internal NCR
NCR0229 | 2021-06-29 | 415 | PACIS | SWD half display | STE - VBN | Low | Hardware issue | Replace with new part | Closed |  | 27 |  |  | Internal NCR
NCR0230 | 2021-06-30 | 607 | PACIS | SWD half display | STE - VBN | Low | Hardware issue | Replace with new part | Closed |  | 27 |  |  | Internal NCR
NCR0231 | 2021-07-07 | 423 | Brakes | Realy failure | FT | High | Relay malfunction | Replace Relays | Closed |  | 28 |  |  | Internal NCR
NCR0232 | 2021-07-07 | 510 | Doors | USB port not working | KN | Low | USB port corrupted, not able to upload software | Replace DCU | Closed |  | 28 |  |  | Internal NCR
NCR0233 | 2021-07-07 | 409 | Network | NETMM1 in HC1 found faulty | Alstom | Low | Part malfunction, not able to recover. | Replace with new Netbox | Closed | CM0100 | 28 |  |  | Internal NCR
NCR0234 | 2021-07-12 | 407 | Doors | Door Motor Brake Faulty. | KN | High | Moter brake Faulty | Replace the motor | Closed | CM0051 | 29 |  |  | Internal NCR
NCR0235 | 2021-07-13 | 407 | PACIS | TCCU failure | STE - VBN | High | TCCU malfunction | Replace TCCU | Closed |  | 29 |  |  | Internal NCR
NCR0236 | 2021-07-13 | 407 | PACIS | NVR failure | STE - VBN | Medium | Loss 0f NVR communication with the train | Retrofit | Closed | NVR retrofit | 29 |  |  | Internal NCR
NCR0237 | 2021-07-15 | 516 | CVS | Internal short circuit in CVS invertor power module | CRL | High | Testing Purpose | NA | Closed |  | 29 |  |  | Internal NCR
NCR0238 | 2021-07-15 | 614 | PACIS | SWD half display | STE - VBN | Low | Hardware issue | Replace with new part | Closed |  | 29 |  |  | Internal NCR
NCR0239 | 2021-07-15 | 414 | PACIS | TCCU lost communication | STE - VBN | Low | TCCU malfunction | Replace with new part | Closed |  | 29 |  |  | Internal NCR
NCR0240 | 2021-07-15 | 413 | Network | Consist Ring Switch (CRS) communication loss | Alstom | Low | CRS malfunction | Replace with new part | Closed |  | 29 |  |  | Internal NCR
NCR0241 | 2021-07-26 | 617 | PACIS | NVR missing in the train | STE - VBN | Medium | to beupdated once root cause is provided by CRL | Fix after retroft | Closed |  | 31 |  |  | Internal NCR
NCR0242 | 2021-07-26 | 617 | PACIS | TCCU failure | STE - VBN | Medium | TCCU malfunction | Replace TCCU | Closed |  | 31 |  |  | Internal NCR
NCR0243 | 2021-08-03 | 615 | Network | Consist Ring Switch (CRS) communication loss | Alstom | Low | CRS unable to recover manually | Replace new CRS | Closed |  | 32 |  |  | Internal NCR
NCR0244 | 2021-08-04 | 418 | CVS | CVS CONVERTER MODULE - Testing Purpose | CRL | Low | For testing purpose | NA | Cancelled |  | 32 |  |  | Internal NCR
NCR0245 | 2021-08-04 | 608 | Doors | Door not get hold | KN | High | Relay malfunction | Replace Relays | Closed |  | 32 |  |  | Internal NCR
NCR0246 | 2021-08-07 | 422 | Brakes | BCE loss of communication | FT | High | Loss of ED BCE | Replaced new A-Matric | Closed |  | 32 |  |  | Internal NCR
NCR0247 | 2021-08-07 | 422 | Doors | Door not get hold | KN | High | Relay malfunction | Replace Relays | Closed |  | 32 |  |  | Internal NCR
NCR0248 | 2021-08-08 | 418 | CVS | CVS INVERTER MODULE (REC-INV-BC) - Internal failure | CRL | High | Internal failure & Repairing | Replace inverter module | Closed |  | 33 |  |  | Internal NCR
NCR0249 | 2021-08-08 | 615 | CVS | CVS INVERTER MODULE (REC-INV-BC) - Missing Item | CRL | High | Missing Item | NA | Closed |  | 33 |  |  | Internal NCR
NCR0250 | 2021-08-08 | 418 | CVS | CVS CONVERTER MODULE - Testing Purpose | CRL | Low | For testing purpose | NA | Cancelled |  | 33 |  |  | Internal NCR
NCR0251 | 2021-08-08 | 413 | Network | Consist Ring Switch (CRS) communication loss | Alstom | Medium | CRS unable to recover manually | Replace new CRS | Closed |  | 33 |  |  | Internal NCR
NCR0252 | 2021-08-09 | 420 | Brakes | EB not relase | FT | High | Relay malfunction | Replace Relays | Closed |  | 33 |  |  | Internal NCR
NCR0253 | 2021-08-10 | 410 | Doors | Emergency unlock switch S3 mechanical issue | KN | High | Mechanical Issue | Mechanical repair of the emergency unlock switch S3 | Closed |  | 33 |  |  | Internal NCR
NCR0254 | 2021-08-11 | 616 | Traction | MV Earth fault | CRL | High | Internal short of fan coil | Replace traction fan | Closed |  | 33 |  |  | Internal NCR
NCR0255 | 2021-08-11 | 615 | Doors | Realy failure | KN | High | Relay malfunction | Replace Relays | Closed |  | 33 |  |  | Internal NCR
NCR0256 | 2021-08-12 | 602 | Doors | Relay failure | KN | High | Relay malfunction | Replace Relays | Closed |  | 33 |  |  | Internal NCR
NCR0257 | 2021-08-14 | 617 | Doors | Realy failure | KN | High | Relay malfunction | Replace Relays | Closed |  | 33 |  |  | Internal NCR
NCR0258 | 2021-08-17 | 609 | Electrical wiring | Circuit Breaker for WIFI modification | Alstom | Low | NA | NA | Closed |  | 34 |  |  | Internal NCR
NCR0259 | 2021-08-17 | 609 | Electrical wiring | Circuit Breaker for WIFI modification | Alstom | Low | NCR cancelled | NCR cancelled | Cancelled |  | 34 |  |  | Internal NCR
NCR0260 | 2021-08-17 | 605 | Traction | Loss of traction and ED brake on one PCE | CRL | High | inverter power module shortage | Replace inverter power module | Closed |  | 34 |  |  | Internal NCR
NCR0261 | 2021-08-17 | 612 | Doors | Relay failure | KN | High | Relay malfunction | Replace Relays | Closed |  | 34 |  |  | Internal NCR
NCR0262 | 2021-08-17 | 617 | Network | Consist Ring Switch (CRS) communication loss | Alstom | Low | CRS malfunction | Replace with new part | Closed | Rectification by manual recovery and no replacement of part | 34 |  |  | Internal NCR
NCR0263 | 2021-08-22 | 611 | HVAC | MV Earth fault | FT | Low | short of compressor cable | Replace the compressor | Closed |  | 35 |  |  | Internal NCR
NCR0264 | 2021-08-23 | 416 | HVAC | Compressor failure | FT | Low | short of compressor cable | Replace the compressor | Closed |  | 35 |  |  | Internal NCR
NCR0265 | 2021-08-23 | 514 | Doors | Relay failure | KN | High | Relay malfunction | Replace Relays | Closed |  | 35 |  |  | Internal NCR
NCR0266 | 2021-08-23 | 512 | Doors | Relay failure | KN | High | Relay malfunction | Replace Relays | Closed |  | 35 |  |  | Internal NCR
NCR0267 | 2021-08-23 | 503 | Doors | Relay failure | KN | High | Relay malfunction | Replace Relays | Closed |  | 35 |  |  | Internal NCR
NCR0268 | 2021-08-23 | 403 | PACIS | TCCU failure | STE - VBN | Low | TCCU malfunction | Replace TCCU | Closed |  | 35 |  |  | Internal NCR
NCR0269 | 2021-08-24 | 403 | PACIS | TCCU failure | STE - VBN | Low | NCR cancelled | NCR cancelled | Cancelled | duplicate with NCR0268 | 35 |  |  | Internal NCR
NCR0270 | 2021-08-25 | 609 | Electrical wiring | Circuit Breaker for WIFI modification | Alstom | Low | NA | NA | Closed | SAP NCR# 741032 | 35 |  |  | Internal NCR
NCR0271 | 2021-08-25 | 403 | PACIS | TCCU failure | STE - VBN | Low | TCCU malfunction | Replace with new part | Closed |  | 35 |  |  | Internal NCR
NCR0272 | 2021-08-26 | 606 | Battery | Connector broken | Hoppecke | Low | Wrong dimension of support plate | Fix new connector & modifify support plate | Closed |  | 35 |  |  | Internal NCR
NCR0273 | 2021-08-31 | 508 | Doors | Door not get hold | KN | High | Motor brake issue | Replace EDCU and Motor | Closed |  | 36 |  |  | Internal NCR
NCR0274 | 2021-09-01 | 516 | CVS | 3Phase output contactor (Testing purpose only) | CRL | Medium | For testing purpose | NA | Cancelled |  | 36 |  |  | Internal NCR
NCR0275 | 2021-09-02 | 612 | Doors | DCU offline | KN | High | Internal failure of EDCU | Replace with new EDCU | Closed |  | 36 |  |  | Internal NCR
NCR0276 | 2021-09-02 | 516 | CVS | CVS INVERTER MODULE (REC-INV-BC) - Internal failure | CRL | High | wrong wiring for feedback at the output basbar | Normalize the wiring | Closed |  | 36 |  |  | Internal NCR
NCR0277 | 2021-09-05 | 508 | Doors | Door not get hold | KN | High | Motor brake issue | Replace EDCU and Motor | Closed |  | 37 |  |  | Internal NCR
NCR0278 | 2021-09-05 | 407 | HVAC | HVAC Not cooling | FT | High | Leakage of gas from the compressor 2, Manufacturing issue | Replace compressor | Closed |  | 37 |  |  | Internal NCR
NCR0279 | 2021-09-05 | 423 | PACIS | SWD half display | STE - VBN | Low | Hardware issue | Replace with new part | Closed |  | 37 |  |  | Internal NCR
NCR0280 | 2021-09-06 | 505 | Brakes | Faulty pulse enable of BCE or PCE in single configuration | FT | High | no holding brake not available | Replace A-matrix | Closed |  | 37 |  |  | Internal NCR
NCR0281 | 2021-09-06 | 418 | CVS | CVS CONVERTER MODULE - Testing Purpose | CRL | Low | For testing purpose | NA | Cancelled |  | 37 |  |  | Internal NCR
NCR0282 | 2021-09-06 | 608 | Horn | Horn funtion issue | Alstom | High | Harware issue | Replace horn | Closed | SAP NCR# 741033, CM0280 | 37 |  |  | Internal NCR
NCR0283 | 2021-09-12 | 623 | PACIS | NVR failure | STE - VBN | High | Internal failure | Replace new NVR | Closed |  | 38 |  |  | Internal NCR
NCR0284 | 2021-09-14 |  | PACIS | TCCU failure | STE - VBN | Medium | PA intermittent issue | Replace TCCU | Closed |  | 38 |  |  | Internal NCR
NCR0285 | 2021-09-15 | 504 | PACIS | Connector broken | STE - VBN | Low | Wrong dimension of support plate | Fix new connector & modifify support plate | Closed |  | 38 |  |  | Internal NCR
NCR0286 | 2021-09-19 | 424 | PACIS | PEI lost communication | STE - VBN | Medium | Hardware issue | Replace with new part | Closed |  | 39 |  |  | Internal NCR
NCR0287 | 2021-09-19 | 601 | PACIS | TCCU failure | STE - VBN | Medium | 'New software parameter issue, still to be confirmed | Replace with new part | Closed | no impact on the functionality of the board despite the burn mark of PAU card--analysis ongoing - Send the PAU module to STE for repair/replacement | 39 |  |  | Internal NCR
NCR0288 | 2021-09-19 | 601 | PACIS | TCCU failure | STE - VBN | Medium | 'New software parameter issue, still to be confirmed | Replace with new part | Closed | no impact on the functionality of the board despite the burn mark of PAU card--analysis ongoing - Send the PAU module to STE for repair/replacement | 39 |  |  | Internal NCR
NCR0289 | 2021-09-19 | 424 | PACIS | TCCU failure | STE - VBN | Medium | 'New software parameter issue, still to be confirmed | Replace with new part | Closed | no impact on the functionality of the board despite the burn mark of PAU card--analysis ongoing - Send the PAU module to STE for repair/replacement | 39 |  |  | Internal NCR
NCR0290 | 2021-09-19 | 424 | PACIS | TCCU failure | STE - VBN | Medium | 'New software parameter issue, still to be confirmed | Replace with new part | Closed | no impact on the functionality of the board despite the burn mark of PAU card--analysis ongoing - Send the PAU module to STE for repair/replacement | 39 |  |  | Internal NCR
NCR0291 | 2021-09-20 | 407 | PACIS | TCCU failure | STE - VBN | Medium | 'New software parameter issue, still to be confirmed | Replace with new part | Closed | no impact on the functionality of the board despite the burn mark of PAU card--analysis ongoing - Send the PAU module to STE for repair/replacement | 39 |  |  | Internal NCR
NCR0292 | 2021-09-20 | 407 | PACIS | TCCU failure | STE - VBN | Medium | 'New software parameter issue, still to be confirmed | Replace with new part | Closed | no impact on the functionality of the board despite the burn mark of PAU card--analysis ongoing - Send the PAU module to STE for repair/replacement | 39 |  |  | Internal NCR
NCR0293 | 2021-09-20 | 405 | HVAC | HVAC not working | FT | Medium | KA4 contactor not Energized (K22Z type)-Malfunction | Replace the contactor | Closed |  | 39 |  |  | Internal NCR
NCR0294 | 2021-09-21 | 518 | HVAC | Compressor not working. | FT | Medium | KM2 contactor not Energized coil itself faulty | Replace the contactor | Closed | CM0094 | 39 |  |  | Internal NCR
NCR0295 | 2021-09-27 | 424 | PACIS | TCCU failure | STE - VBN | Medium | TCCU malfunction | Replace TCCU | Closed |  | 40 |  |  | Internal NCR
NCR0296 | 2021-09-20 | 601 | Battery | IOS182 related to battery | Hoppecke | Low | cable X2 for relay 52K13 disconnected | Remove the pin and install new pin with cable properly. | Closed | CM0053 | 39 |  |  | Internal NCR
NCR0297 | 2021-09-20 | 602 | Traction | IOS 228 : At least one minor failure on PCE | CRL | Low | Found 1 pin (P0703A) female gold pin push back | Normalize the pin and test. | Closed | CM0052 | 39 |  |  | Internal NCR
NCR0298 | 2021-09-26 | 613 | Electrical wiring | Reported 52Q13 tripped | Alstom | Low | Found cable at XT02+RP3_009, cable number WD61224 loose and touching body. | After recorrect and fit cable properly | Closed | CM0061 | 40 |  |  | Internal NCR
NCR0306 | 2021-09-19 | 405 | PACIS | LEDi4 display not ok | STE - VBN | Low | Software corrupted | New software upload to recover, if it is not possible to recover, replace with new one | Closed | CM0480 | 39 | 2 | 2022-01-04 | Internal NCR
NCR0307 | 2021-09-19 | 406 | PACIS | IP offline | STE - VBN | Low | Software corrupted | New software upload to recover, if it is not possible to recover, replace with new one | Closed | CM0482 | 39 | 2 | 2022-01-04 | Internal NCR
NCR0308 | 2021-09-26 | 402 | Doors | IOS071 : Discrepancy between EED and ATC information | KN | High | Cable 981 at microswitch S7 at EED assemble cable connection wrongly installed, should be install atterminal 1, but it was at terminal 2. | Install 981 cable at terminal 1 and test by activating EED including monitor by train tracer | Closed | Issue closed, CM report to be linked | 40 |  |  | Internal NCR
NCR0309 | 2021-09-28 | 410 | Doors | Emergency unlock switch S3 mechanical issue | KN | High | Emergency Unlock switch S3 mechanical issue | Mechanical repair of the emergency unlock switch S3 | Closed | CM0024 | 40 |  |  | Internal NCR
NCR0310 | 2021-09-28 | 422,602,608,612,615,617,503,509 | Doors | Relay failure | KN | Medium | Relay malfunction | Replace Relays | Closed | CM0025,CM0027,CM0030,CM0031,CM0032,CM0033,CM0037,CM0039,CM0046,CM0047,CM0054 | 40 |  |  | Internal NCR
NCR0311 | 2021-09-28 | 601,607,624 | Doors | HDC Trainline wiring | KN | High | 601-LV wire got damaged with ground , 607-CB61Q10 shunt loose, 624-Cable loose connection at (XT02+ROM_57) | Replace wires and fix loose connection | Closed | CM0026, CM0029, CM0035 | 40 |  |  | Internal NCR
NCR0312 | 2021-09-28 | 603,619,622,510 | Doors | Mechanical adjustment of PEED | KN | High | Mechanical adjustment failure of PEED | Mechanical adjustment PEED to be done | Closed | CM0028, CM0040, CM0055 | 40 |  |  | Internal NCR
NCR0313 | 2021-09-28 | 508 | Doors | Door not open | KN | High | Motor brake issue | Replace EDCU & Motor2 | Closed | CM0038 | 40 |  |  | Internal NCR
NCR0314 | 2021-09-29 | 605 | Traction | No cab actvie and EB not release. | CRL | High | Contactor 61K13 coil malfunction when drive mode select to UTO or Manual Mode. The contactor details : AF09ZB-30-10RT-22 | Replacement new part and test. | Closed | CM0060,SAP NCR# 741034 | 40 |  |  | Internal NCR
NCR0315 | 2021-10-05 | 605 | Traction | IOS226 : Loss of traction and ED brake on one PCE | CRL | High | Found speed sensor for PCE at bogie 2 have cable cut because cable hanging and touched the wheel, and also no cable tie and cable arrangement not good | Replacement with new part | Closed | CM0062, SAP NCR# 741035 | 41 |  |  | Internal NCR
NCR0316 | 2021-10-14 | 513 | Network | Consist Ring Switch (CRS) communication loss | Alstom | High | CRS offline | Replacement with new part | Closed | CM0159 | 42 |  |  | Internal NCR
NCR0317 | 2021-10-24 | 513 | Network | Consist Ring Switch (CRS) communication loss | Alstom | High | CRS offline | Replacement with new part | Closed | CM0479 | 44 | 2 | 2022-01-04 | Internal NCR
NCR0318 | 2021-10-24 | 424 | Network | Consist Ring Switch (CRS) communication loss | Alstom | High | CRS offline | Replacement with new part | Closed | CM0168 | 44 |  |  | Internal NCR
NCR0319 | 2021-10-28 | 615 | PACIS | PEI lost communication | STE - VBN | Medium | PEI offline | Replacement with new part | Closed | CM0221 | 44 |  |  | Internal NCR
NCR0320 | 2021-10-28 | 422 | CVS | CVS critcal fault by MPU logs and by CVS logs | CRL | High | Inveter defected. | Inverter module need to change. | Closed | CM0214 | 44 |  |  | Internal NCR
NCR0321 | 2021-10-31 | 418 | PACIS | PEI lost communication | STE - VBN | Medium | PEI offline | Replacement with new part | Closed | CM0232 | 45 |  |  | Internal NCR
NCR0322 | 2021-10-31 | 407 | CVS | Leakage from the input Capacitor | CRL | Medium | To be analyzed by CRL | Replacement with new part | Closed | CM0215 | 45 |  |  | Internal NCR
NCR0323 | 2021-11-01 | 609 | PACIS | NVR fault | STE - VBN | Low | Software and HDD conneciton issue. | STE local support to reprogram again, reinsert HDD and connect to train. Do power off/on for three times to check stability and confirm OK. | Closed | CM0301 | 45 |  |  | Internal NCR
NCR0324 | 2021-11-04 | 615 | PACIS | NVR fault | STE - VBN | Low | Suspected hardware issue. | Need to send back to Sigapore for investigation work (STE local support checked and try manual recover NVR but still not working. STE Singapore suspected this NVR have hardware issue). | Closed | M0287 | 45 |  |  | Internal NCR
NCR0325 | 2021-11-04 | 406 | PACIS | NVR fault | STE - VBN | High | Suspected hardware issue. | Need to send back to Singapore for investigation work (STE local support checked and try manual recover NVR but still not working. STE Singapore suspected this NVR have hardware issue. ) | Closed | CM0289 | 45 |  |  | Internal NCR
NCR0326 | 2021-11-08 | 609 | PACIS | NVR fault | STE - VBN | High | Suspected hardware issue. | Need to send back to Singapore for investigation work (STE local support checked and try manual recover for 2 times but NVR still not working. STE Singapore suspected this NVR have hardware issue.) | Closed | CM0286 | 46 |  |  | Internal NCR
NCR0327 | 2021-11-11 | 417 | Brakes | IOS015 : Service brake loop fault indicaion. | Alstom | High | 62K08 relay malfunction/stuck.. | Replace 62K08 relay. | Closed | CM0290 | 46 |  |  | Internal NCR
NCR0328 | 2021-11-11 | 412 | PACIS | NVR fault | STE - VBN | High | Software and HDD conneciton issue. | Replace NVR | Closed | CM0288 | 46 |  |  | Internal NCR
NCR0329 | 2021-11-14 | 401 | PACIS | Relay failure | STE - VBN | High | Relay malfunction. | 61K03 relay to be replaced. | Closed | CM0291 | 47 |  |  | Internal NCR
NCR0330 | 2021-11-14 | 407 | HVAC | HVAC unit cooling fault | FT | High | Compressor leaking from the upper joint(repeated issue), might be manufacturing defect | Compressor need to be replaced. | Closed | CM0300 | 47 |  |  | Internal NCR
NCR0331 | 2021-11-14 | 401 | Elecrical | Found relay voltage limitter abnormal ohm value | Alstom | High | Relay voltage limitter have abnormal resistant value. | Relay voltage limitter need to change and test. | Closed | CM0296 | 47 |  |  | Internal NCR
NCR0332 | 2021-11-13 | 612 | PACIS | Found relay voltage limitter abnormal ohm value | STE - VBN | High | DCU communaction loss | Need to replace DCU | Closed | CM0297 | 46 |  |  | Internal NCR
NCR0333 | 2021-11-13 | 403 | PACIS | PEI lost communication | STE - VBN | Medium | PEI failure | PEI to be replaced | Closed | CM0293 | 46 |  |  | Internal NCR
NCR0334 | 2021-11-13 | 403 | PACIS | PEI lost communication | STE - VBN | Medium | PEI failure | PEI to be replaced | Closed | CM0302 | 46 |  |  | Internal NCR
NCR0335 | 2021-11-16 | 414 | PACIS | PEI lost communication | STE - VBN | Medium | E1 ethernet port malfunction. | PEI module need to change.Software also need to reupload to latest configuration. | Closed | CM0298 | 47 |  |  | Internal NCR
NCR0336 | 2021-11-17 | 401 | PACIS | TCCU1 on but PAPIS show lost communication in ISM | STE - VBN | Low | TCCU malfunction | Need to replace TCCU | Closed | CM0292 | 47 |  |  | Internal NCR
NCR0337 | 2021-11-17 | 401 | PACIS | PEI lost communication | STE - VBN | Medium | PEI failure | PEI to be replaced | Closed | CM0295 | 47 |  |  | Internal NCR
NCR0338 | 2021-11-17 | 404 | PACIS | PEI lost communication | STE - VBN | Medium | PEI failure | PEI to be replaced | Closed | CM0281 | 47 |  |  | Internal NCR
NCR0339 | 2021-11-18 | 606 | Network | Consist Ring Switch (CRS) fail to power up | Alstom | Low | CRS42 failure, fail to power up | Replacement with new part | Closed | CM0294 | 47 |  |  | Internal NCR
NCR0340 | 2021-11-21 | 421 | HVAC | HVAC fault. | FT | High | HVAC1 condenser fan failure and confimred by check it with MONA, observed fault code DF-1021_CDFL and DF-1022_CDFH. | Replace Condenser fan | Closed | CM0283 | 48 |  |  | Internal NCR
NCR0341 | 2021-11-21 | 421 | HVAC | HVAC fault. | FT | Low | emergency ventilation fault | HVAC will be checked by local supplier support and corrections will be managed through CM report. | Open | issue is closed, CM report to be issued | 48 | 0 |  | Internal NCR
NCR0342 | 2021-11-23 | 406 | PACIS | PEI lost communication | STE - VBN | Medium | PEI failure, STE to investigate | PEI to be replaced | Open | parts available , to be fixed by CM | 48 | 0 |  | Internal NCR
NCR0343 | 2021-11-29 | 604 | PACIS | TOM NOK issue. NVR lost communication with IOS191. | STE - VBN | High | Checked by NVR logs and we found HDD1 not working (confrimed by swapped with HDD2, no HDD connnection issue). | HDD need to replaced. | Closed | CM0489 | 49 | 2 | 2022-01-05 | Internal NCR
NCR0344 | 2021-11-23 | 404 | Traction | Loss of traction and ED brake on one PCE | CRL | High | wrong cable connection in the discharging circuit inside the traction invertor power module | Correct the wrong cable connection | Closed | CM0483 | 48 | 2 | 2022-01-04 | Internal NCR
NCR0345 | 2021-11-24 | 412 | PACIS | SWD Error display | STE - VBN | Low | SWD fault, suspected hardware issue. STE to investigate. | To be replaced with a new one | Closed | CM0491 | 48 | 2 | 2022-01-06 | Internal NCR
NCR0346 | 2021-11-29 | 516 | Network | BRIOM Remote input-output module issue | Alstom | High | BRIOM device found faulty. | To be replaced with a new one | Closed | This NCR sttaus to be verified with CM report summary | 49 |  |  | Internal NCR
NCR0347 | 2021-12-01 | 507 | Shoe Collector | Collector shoe damaged | Le Creusot | High | Cause by train accident. Wheel choke which was supposed to be removed before train movement was not removed by the driver causing the train to derail | To be replaced with a new parts | Closed | CM0284 | 49 | 0 |  | Internal NCR
NCR0348 | 2021-11-30 | 512 | HVAC | HVAC compressor and ventilation fault | FT | High | Need further investigation, to be checked by local supplier.. | Need further investigation and to be closed this issue through corrective maintenance reportt | Open | Under investigation by supplier | 49 | 0 |  | Internal NCR
NCR0349 | 2021-12-01 | 603 | Brakes | Relay no power supply | Alstom | Low | Disconnected wiring W56802 for relay 61k37-D4 | Connect the wiring W56802 for relay 61k37-D4 and test | Closed | CM0485 | 49 |  |  | Internal NCR
NCR0350 | 2021-11-30 | 604 | Brakes | Holding brake issue with A-MATRIC | FT | High | Holding brake output is broken from A-Matric | A-MATRIC to be replaced | Closed | CM0486 | 49 | 2 | 2022-01-05 | Internal NCR
NCR0351 | 2021-12-02 | 410 | PACIS | NVR communication lost | STE - VBN | High | NVR swapped and test in other train, we still have the same communcation fault each time train wake up. | NVR need to be changed | Closed | CM0487 | 49 | 2 | 2022-01-05 | Internal NCR
NCR0352 | 2020-10-10 | 418 | Doors | Passenger door glass cracked | Alstom | Low | Unknow reason,old issue. | Analyze if this can be eradicate by a chemical adhesive without replacement of windows. If issue can not be fixed, replace the window glass. | Open | Requested sourcing the glass fixing gel , waiting for the delivery | 41 | 0 |  | Internal NCR
NCR0353 | 2020-06-25 | 624 | Doors | Scratches on T624 HC1 Door glass | Alstom | Low | Unknow reason,old issue. | Repair if minor scratch, replace if scratches are too deep. | Open | Issue is closed , CM report to be issued | 26 | 0 |  | Internal NCR
NCR0354 | 2021-12-06 | 401 | SLV-ATC | Issue with ATC odometer | Alstom | Medium | The PIN 24/27 can't be connected properly in the connector XP03+GCL. Crimping already done for theses 2 PIN but loosed again after train moving in Mainline | Need to change the connector XP03+GCL (HC2) | Closed | CM0481 | 50 | 2 | 2022-01-04 | Internal NCR
NCR0355 | 2021-12-06 | 605 | PACIS | LEDI failed to ping | STE - VBN | Medium | LEDI fault | To be replaced with new LEDI | Closed | CM0492 | 50 | 2 | 2022-01-06 | Internal NCR
NCR0356 | 2021-12-06 | 623 | PACIS | Issue with PEI leading the equipment behind it offline | STE - VBN | Low | PEI E2 port faulty | To be replaced with new PEI | Closed | CMN0514 | 50 | 3 | 2022-01-13 | Internal NCR
NCR0357 | 2021-12-06 | 608 | Compressors | AGTU filter locked nut thread damaged | FT | Low | AGTU filter locked nut thread damaged | To be replaced with new lock nut | Closed | CM0354 | 50 |  | 2021-12-20 | Internal NCR
NCR0358 | 2021-02-21 | 411 | Coupler | Electrical coupler frame broken | KTW | Medium | Improper uncoupling | Coupler frame to be replaced | Open | No material available, ordered through SAP ( informed to kTW) | 9 | 0 |  | Internal NCR
NCR0359 | 2021-12-07 | 608 | Coupler | Semi permenant coupler side A earthing screw missing. | KTW | Low | earthing screw missing | To be fixed with new head screw | Closed | CM0285 | 50 |  |  | Internal NCR
NCR0360 | 2021-12-07 | 502 | Sanding | Sanding rubber hoses and clams missing | KTW | Low | Reason unknown | Need to fix with new part rubber hoses with clamps | Open | Supplier missed the hoses while delivering, pending | 50 | 0 |  | Internal NCR
NCR0361 | 2021-12-07 | 603 | DCS | Beacon Antenna screws missing | KTW | Low | Not installed due to out of stock (root cause unknown) | To be fixed with new screws | Open | No material available, ordered through SAP ( informed to kTW) | 50 | 0 |  | Internal NCR
NCR0362 | 2021-12-08 | 603 | Sanding | Left side sanding hose not availabe | KTW | Low | unknown reason | Need to fix with new part rubber hose with clamps | Open | Supplier missed the hoses while delivering, pending | 50 | 0 |  | Internal NCR
NCR0363 | 2021-12-08 | 605 | PACIS | PAPIS displays communication loss | STE - VBN | Low | Parts failure | Listed components SWD, LCD & LEDi to be replaced | Closed | CMN0505 | 50 |  | 2022-01-11 | Internal NCR
NCR0364 | 2021-12-08 | 412 | Lighting | Cab light dim | KTW | Low | Light issue | Light to be replaced | Cancelled |  | 50 |  |  | Internal NCR
NCR0365 | 2021-12-08 | 411 | Lighting | Cab light dim | KTW | Low | Light issue | Light to be replaced | Cancelled |  | 50 |  |  | Internal NCR
NCR0366 | 2021-12-08 | 623 | PACIS | Ledi blank display | STE - VBN | Low | LEDI failure, to be investigated by STE | Replace LEDi | Closed | CM0493 | 50 | 2 | 2022-01-06 | Internal NCR
NCR0367 | 2021-12-08 | 619 | PACIS | PAPIS blank displays and multimedia not update | STE - VBN | Low | Component failures | Replace the displays listed | Closed | CMN0504 | 50 | 3 | 2022-01-11 | Internal NCR
NCR0368 | 2021-12-08 | 403 | PACIS | LEDi error display | STE - VBN | Low | LEDI failure, to be investigated by STE | Replace LEDi | Closed | CM0494 | 50 | 2 | 2022-01-06 | Internal NCR
NCR0369 | 2021-12-08 | 619 | PACIS | LEDi dark display and offline | STE - VBN | Low | LEDI failure, to be investigated by STE | Replace LEDi | Closed | CM0496 | 50 | 0 |  | Internal NCR
NCR0370 | 2021-12-08 | 414 | PACIS | PAPIS displays issues | STE - VBN | Low | Component failures | Replace the displays listed | Closed | CMN0515 | 50 | 3 | 2022-01-13 | Internal NCR
NCR0371 | 2021-12-08 | 423 | PACIS | PAPIS displays issues | STE - VBN | Low | Component failures | Replace the displays listed | Closed | CM0495 | 50 | 3 | 2022-01-09 | Internal NCR
NCR0372 | 2021-12-08 | 606 | Carbody | Gap filler between HVAC and Gangway missing | KTW | Low | Missing, reason unknown | Need to fix with the new Gap filler | Open | Material not available, SAP NCR is requested to KTW | 50 | 0 |  | Internal NCR
NCR0373 | 2021-12-09 | 606 | PACIS | SWD blinking issue | STE - VBN | Low | Component failure | Replace SWD | Closed | CM0469 | 50 | 2 | 2022-01-02 | Internal NCR
NCR0374 | 2021-12-09 | 616 | PACIS | SWD half display | STE - VBN | Low | SWD5_V1 half display | Replace SWD | Closed | CM0471 | 50 | 2 | 2022-01-02 | Internal NCR
NCR0375 | 2021-12-12 | 601 | Compressors | AGTU_Missing of Sand filter Assembly | FT | Low | Missing.Root cause unknown | Need to normalize by adding the missing part. | Open |  | 51 | 0 |  | Internal NCR
NCR0376 | 2021-12-12 | 601 | Brakes | leakage found from the spring brake part. | FT | Low | To be investigated with supplier Faiveley | Need to replace the BRAKE UNIT of PARKING BRAKE | Open | To be sent to supplier FT ( India) for investigation and repair. Supplier to provide the investigation report with the rootcause and corrective actions | 51 | 0 |  | Internal NCR
NCR0377 | 2021-12-12 | 610 | Lighting | Head and Tail Light white LED not working | KTW | Low | Reason unknown | Need to replace and send to supplier for repairing | Open | only 1 led light not working out of 23, no need to change it now, kept on Hold | 51 | 0 |  | Internal NCR
NCR0378 | 2021-12-12 | 617 | Lighting | Head and Tail Light white LED not working | KTW | Low | Reason unknown | Need to replace and send to supplier for repairing | Open | only 1 led light not working out of 23, no need to change it now, kept on Hold | 51 | 0 |  | Internal NCR
NCR0379 | 2021-12-12 | 617 | Lighting | PALM TREE LIGHT not Working | KTW | Low | DC light converter issue | Need to Replace the 110v to 24v DC Light converter | Closed | CMN0502 | 51 | 3 | 2022-01-10 | Internal NCR
NCR0380 | 2021-12-12 | 617 | PACIS | SWD half display | STE - VBN | Low | Component failure, to be investigated by STE | Replace SWD | Closed | CM0490 | 51 | 2 | 2022-01-06 | Internal NCR
NCR0381 | 2021-12-12 | 601 | PACIS | LCD & EDI error display | STE - VBN | Low | Component failure | Replace LCD,LEDI | Open | Material available, to be fixed by CM | 51 | 0 |  | Internal NCR
NCR0382 | 2021-12-13 | 611 | Bogie | Axle Gearbox leakage | Le Creusot | Low | Leakage found from inspection cover | Need to replace the Gasket/Sealant RTV | Open | Waiting for material (in transit) | 51 | 0 |  | Internal NCR
NCR0383 | 2021-12-13 | 611 | Lighting | Head and Tail Light LED not working | KTW | Low | Unknown, LED light failure | Need to replace and send the defective part to supplier for repairing | Open | To be sent to supplier for repair | 51 | 0 |  | Internal NCR
NCR0384 | 2021-12-13 | 611 | Lighting | Saloon light not working | KTW | Low | Unknown reason | Need to replace the saloon light | Closed | CMN0509 | 51 | 3 | 2022-01-12 | Internal NCR
NCR0385 | 2021-12-13 | 417 | Interior | Under seat fire extinguisher BOX and GCL fire Extinguisher bracket not available | Alstom | Low | No stock available | Need to install new | Closed | CMN0358 | 51 | 4 | 2022-01-16 | Internal NCR
NCR0386 | 2021-12-14 | 608 | PACIS | LED, LCD and SWD display issues | STE - VBN | Low | Component failures | Replace LCD,LEDI | Closed | CMN0506 | 51 | 3 | 2022-01-11 | Internal NCR
NCR0387 | 2021-12-14 | 626 | PACIS | LCD poor display issue | STE - VBN | Low | Component failure | Replace LCD | Open | Material available, to be fixed by CM | 51 | 0 |  | Internal NCR
NCR0388 | 2021-12-13 | 625 | Network | CRS communiction loss | Alstom | Low | Hardware issue coming from DC/DC converter. | Need to replace by new CRS | Closed | CM0304 | 51 |  |  | Internal NCR
NCR0389 | 2021-12-14 | 507 | Interior | Under seat fire extinguisher BOX not available | Alstom | Low | No stock available | Need to install new | Open | To procure and install | 51 | 0 |  | Internal NCR
NCR0390 | 2021-12-14 | 404 | Interior | fire extinguisher holding plate not available | Alstom | Low | No stock available | Need to install new | Closed | CMN0543 | 51 | 5 | 2022-01-23 | Internal NCR
NCR0391 | 2021-12-13 | 404 | Lighting | Saloon light not working | KTW | Low | Unknow reason | Need to install new | Closed | CMN0519 | 51 | 4 | 2022-01-17 | Internal NCR
NCR0392 | 2021-12-15 | 624 | PACIS | SWD half display | STE - VBN | Low | Component failure | Replace SWD | Closed | CM0472 | 51 | 2 | 2022-01-02 | Internal NCR
NCR0393 | 2021-12-15 | 612 | PACIS | LCD display issues | STE - VBN | Low | Component failure | Replace L CDs | Open | Material available, to be fixed by CM | 51 | 0 |  | Internal NCR
NCR0394 | 2021-12-15 | 422 | Doors | Door glass cracked | Alstom | Low | Reason unknown, To be investigated | Analyze if this can be eradicate by a chemical adhesive without replacement of windows. If issue can not be fixed, replace the window glass. | Open | Requested sourcing the glass fixing gel , waiting for the delivery | 51 | 0 |  | Internal NCR
NCR0395 | 2021-12-15 | 601 | Lighting | Saloon Light not working | KTW | Low | Unknow reason | Need to install new | Open | Part available, will be fixed by CM team | 51 | 0 |  | Internal NCR
NCR0396 | 2021-12-15 | 623 | Lighting | Saloon Light not working | KTW | Low | Unknow reason | Need to install new | Closed | CMN0508 | 51 | 3 | 2022-01-12 | Internal NCR
NCR0397 | 2021-12-15 | 623 | Lighting | Driver Cab Light not working | KTW | Low | Unknow reason | Need to install new | Closed | CMN0520 | 51 | 4 | 2022-01-17 | Internal NCR
NCR0398 | 2021-12-15 | 409 | Lighting | Saloon Light not working | KTW | Low | Unknow reason | Need to install new | Closed | CMN0507 | 51 | 3 | 2022-01-11 | Internal NCR
NCR0399 | 2021-12-16 | 613 | Traction | IOS226 : Loss of traction and ED brake on one PCE | CRL | High | Traction not discharging voltage and after checked we found 3 bad pin at terminal behind Agate. | Need to replace the pin. | Closed | CM0305 | 51 |  |  | Internal NCR
NCR0400 | 2021-12-16 | 602 | PACIS | SWD, LEDi display issues | STE - VBN | Low | Componet failure | Replace LEDi amd SWD | Cancelled | NCR cancelled as confirmed by Guan, Reason of cancellation to be provided by Guan | 51 |  |  | Internal NCR
NCR0401 | 2021-12-16 | 416 | PACIS | LCD display issues | STE - VBN | Low | LCD failure | Replace LCD | Open | Material available, to be fixed by CM | 51 | 0 |  | Internal NCR
NCR0402 | 2021-12-16 | 609 | PACIS | LCD display issues | STE - VBN | Low | LCD failure | Replace LCD | Closed | CM0497 | 51 | 3 | 2022-01-09 | Internal NCR
NCR0403 | 2021-12-19 | 603 | Brakes | Air leakage found from the spring brake part. | FT | Low | Unknown. To be investigated by supplier FT | Need to replace the Brake Unit With Parking Brake | Open | Supplier to provide the investigation report with the rootcause and corrective actions | 52 | 0 |  | Internal NCR
NCR0404 | 2021-12-19 | 619 | Compressors | Plastic washer broken in air dryer | FT | Low | Unknown. Reported by preventive maintenance | Check with Faively to know if need to replace this washer. Reference not available, supplier will provide if need to change. | Closed | CM0501 | 52 | 3 | 2022-01-10 | Internal NCR
NCR0405 | 2021-12-19 | 404 | Electrical wiring | HV cable gland missing from the underframe Junction Box | KTW | Low | Part missing, root cause not known | Need to order the part and installed. | Open | Material availability to be checked by CM | 52 | 0 |  | Internal NCR
NCR0406 | 2021-12-19 | 623 | Traction | stinger cap cover broken | CRL | Low | During the plugging 750v in workshop stinger cap cover broken | Need to install new cap | Open | Material availability to be checked by CM | 52 | 0 |  | Internal NCR
NCR0407 | 2021-12-19 | 606 | Lighting | saloon lights not working | KTW | Low | 110v to 24v DC Light converter issue | Need to fix with new 110v to 24v DC Light converter | Closed | CMN0503 | 52 | 3 | 2022-01-10 | Internal NCR
NCR0408 | 2021-12-19 | 606 | Interior | Gangway Gap filler damaged | KTW | Low | Was not installed properly | Need to install new gap filler | Open | Material not available, SAP NCR is requested to KTW | 52 | 0 |  | Internal NCR
NCR0409 | 2021-12-19 | 623 | Traction | IOS227: Loss of traction and ED brake on atleast twon PCE | CRL | High | Relay mulfunction(Q_NEB relay) | Relay need to be changed. | Closed | CM0355 | 52 |  |  | Internal NCR
NCR0410 | 2021-12-19 | 411 | PACIS | PEI offline | STE - VBN | Low | PEI5-V1 failure | Replace PEI | Closed | CM0470 | 52 |  |  | Internal NCR
NCR0411 | 2021-12-20 | 621 | PACIS | LCD offline | STE - VBN | Low | LCD2-V2 failure | Replace LCD | Closed | CM0451 | 52 |  |  | Internal NCR
NCR0412 | 2021-12-20 | 412 | PACIS | LCD dim display issue | STE - VBN | Low | LCD3-V2 failure | Replace LCD | Closed | CMN0511 | 52 | 3 | 2022-01-12 | Internal NCR
NCR0413 | 2021-12-20 | 613 | PACIS | LCD dim display issue | STE - VBN | Low | LCD4-V1 failure | Replace LCD | Closed | CMN0512 | 52 | 3 | 2022-01-12 | Internal NCR
NCR0414 | 2021-12-20 | 415 | Coupler | Earthing cable is not connected between permanent coupler | KTW | Low | Missing , no stock available | Need to procure and install new earthig cables | Open | Material not available, SAP NCR is requested to KTW | 52 | 0 |  | Internal NCR
NCR0415 | 2021-12-20 | 605 | Shoe Collector | Fuse box type B glass cracked | Le Creusot | Low | The glass clamp over tighten. | Need to change the triplex glass. | Closed | CM0357 | 52 |  |  | Internal NCR
NCR0416 | 2021-12-20 | 605 | Electrical wiring | Jumper cable support bracket missing. | KTW | Low | Part missing. | Need to order jumper cable support and fix it. | Closed | CM0356 | 52 |  |  | Internal NCR
NCR0417 | 2021-12-20 | 618 | Coupler | Earthing cable is not connected between permanent coupler | KTW | Low | Part missing, reason unknown | Need to procure and install new earthig cables | Open | Material not available, SAP NCR is requested to KTW | 52 |  |  | Internal NCR
NCR0418 | 2021-12-20 | 622 | Coupler | Earthing cable is not connected between permanent coupler | KTW | Low | Missing , no stock available | Need to procure and install new earthig cables | Open | Material not available, SAP NCR is requested to KTW | 52 | 0 |  | Internal NCR
NCR0419 | 2021-12-20 | 611 | PACIS | NETBOX2 offline and LEDi blurring issue | STE - VBN | Low | NETBOX2 failure;LEDI1-V1; LEDI1-V2 failure | Replace NETBOX2 ;LEDI1-V1; LEDI1-V2 | Closed | CM0498 | 52 | 3 | 2022-01-09 | Internal NCR
NCR0420 | 2021-12-21 | 403 | Bogie | Axle Gearbox leakage | Le Creusot | Low | Leakage found from inspection cover | Need to replace the Gasket/Sealant RTV | Open | Waiting for material (in transit) | 52 | 0 |  | Internal NCR
NCR0421 | 2021-12-21 | 622 | Traction | Traction cover Screw Damaged.Screw was broken inside . | CRL | Low | Wrong threaded during the screw opening | Need to install new screw | Closed | CM0359 | 52 |  |  | Internal NCR
NCR0422 | 2021-12-21 | 512 | Lighting | Head and Tail Light white LED not working | KTW | Low | One LED not working | Need to Replace and send to supplier for repair | Open | To be sent for repair | 52 | 0 |  | Internal NCR
NCR0423 | 2021-12-22 | 618 | PACIS | LCD error display and SWD half display | STE - VBN | Low | LCD1-V1 ;SWD3-V1 failure | Replace LCD1-V1 ;SWD3-V1 | Closed | CM0452 | 52 |  |  | Internal NCR
NCR0424 | 2021-12-22 | 411 | Interior | Seat not closing | KTW | Low | During the opening folding mechanism broken | Need to be repair the folding mechanism if not possible install the new seat | Closed | CM0500 | 52 | 3 | 2022-01-09 | Internal NCR
NCR0425 | 2021-12-22 | 503 | Lighting | Gangway lights Dim,working inversely | KTW | Low | Issue with 110v to 24v DC Light converter | Need to replace the 110v to 24v DC Light converter | Closed | CMN0517 | 52 | 4 | 2022-01-17 | Internal NCR
NCR0426 | 2021-12-23 | 614 | PACIS | SWD offline and half display | STE - VBN | Low | SWD5-V2 component failure | Replace SWD5-V2 | Closed | CM0499 | 52 | 3 | 2022-01-09 | Internal NCR
NCR0427 | 2021-12-23 | 413 | Bogie | Stick holding safety pin missing. | Le Creusot | Low | Missing, part not available. | Normalize by adding new safety pin(R-CLIP DOUBLE) | Open |  | 52 | 0 |  | Internal NCR
NCR0428 | 2021-12-23 | 410 | PACIS | LCD dim display issue | STE - VBN | Low | LCD2-V2 component failure. | Replace LCD | Open |  | 52 | 0 |  | Internal NCR
NCR0429 | 2021-12-23 | 503 | Shoe Collector | Fuse box glass cracked. | Le Creusot | Low | Checked and no possibility cracked cause by hit, behind the fuse cover we have two glass holding bracket. The only cause were by bad installation process. Bolt for the glass clamp were too tight. | Replace the Fuse box triplex glass. Spare need to be ordered. | Open |  | 52 | 0 |  | Internal NCR
NCR0430 | 2021-12-26 | 501 | Doors | DOOR indication light not working | KTW | Low | Reason unknown | Need to install new indicator | Open |  | 53 | 0 |  | Internal NCR
NCR0431 | 2021-12-26 | 515 | Shoe Collector | Fuse box glass cracked. | Le Creusot | Low | Unknown (visually like broken by a shock) | Replace the Fuse box triplex glass. Spare need to be ordered. | Open |  | 53 | 0 |  | Internal NCR
NCR0432 | 2021-12-27 | 508 | SLV-ATC | STF-DL beacon Antenna : HC1 1 bolt ,HC2 2 bolt not available | Alstom | Low | Missing, reason unknown | Normalize by putting new bolt | Open |  | 53 | 0 |  | Internal NCR
NCR0433 | 2021-12-28 | 515 | Bogie | Stick holding safety pin missing | Le Creusot | Low | Missing, reason unknown | Normalize by adding new safety pin(R-CLIP DOUBLE) | Open |  | 53 | 0 |  | Internal NCR
NCR0434 | 2021-12-28 | 501 | Electrical wiring | Sleep push button not working. Train can't be asleep manually from the push button | KTW | Low | The cable WF00062 in PIN73 should be connected to XR02+CCC instead of XR03+CC | Normalize by removing the cable in the PIN73 XR03 and put this cable in the connector XR02 pin 73 | Closed | CM0484 | 53 | 2 | 2022-01-05 | Internal NCR
NCR0435 | 2021-12-29 | 513 | Network | CRS hardware issue | Alstom | High | Checked and found the switches (CRS) slow to wake up after power on (by battery), observed also the dataplug data version 2.10. Swapped with CRS from HC2 and everything were normal and for the defected CRS which is reporogram and tested but same issue observed. | Need to replace CRS1_V1/VS1_V1(72W09). Give time between 30-40 second for all train switch on or train switch status can confirmed by IP scanner before requesting wake up | Closed | CMN0516 | 53 | 2 | 2022-01-05 | Internal NCR
NCR0436 | 2022-01-02 | 507 | Shoe Collector | HV cable support clamp missing | Le Creusot | Low | Accident train, part missing | Need to fix with spare parts | Open |  | 2 | 0 |  | Internal NCR
NCR0437 | 2022-01-02 | 504 | Gangway | Gangway Panel has scractch &Lock missing | KTW | Low | Retrofit work not done and if compared the lock type, this lock type were old type. | Need to finish the retofit work and re-painting. | Open |  | 2 | 0 |  | Internal NCR
NCR0438 | 2022-01-02 | 501 | Derailment sensor | Derailment sensor cable clamp missing | KTW | Low | Part missing, reason unknown | Order and Install with spare part | Open |  | 2 | 0 |  | Internal NCR
NCR0439 | 2022-01-03 | 410 | Gangway | ONE INTERNAL Gangway COVER MISSING | KTW | Low | Reason unknown | Instal the gangway cover | Open |  | 2 | 0 |  | Internal NCR
NCR0440 | 2022-01-03 | 625 | PACIS | SWD3-V1 half display issue | STE - VBN | Low | SWD3-V1 component failure (suspect card failure) | To replace SWD | Open |  | 2 | 0 |  | Internal NCR
NCR0441 | 2022-01-03 | 601 | Gangway | Gangways panels are not able to be closed | KTW | Low | Reason unknown | Need to install new panel | Open |  | 2 | 0 |  | Internal NCR
NCR0442 | 2022-01-04 | 502 | Bogie | Found minor leakage from the gearbox drain plug cause by O-ring defect. | Le Creusot | Low | O-ring attached to drain pulg defective | O ring need to change and tightened accordingly. | Open |  | 2 | 0 |  | Internal NCR
NCR0443 | 2022-01-05 | 407 | Bogie | Found minor leakage from the gearbox inspection cover | Le Creusot | Low | Inspection cover mole have issue | Inspection cover to be sent to supplier for repair work. | Open |  | 2 | 0 |  | Internal NCR
NCR0444 | 2022-01-05 | 412 | Gangway | Gangways panels are missing | KTW | Low | Reason unknown | Need to install new gangway covers | Open |  | 2 | 0 |  | Internal NCR
NCR0445 | 2022-01-05 | 410 | Gangway | Gangways panel is missing | KTW | Low | Reason unknown | Need to install new gangway cover | Open |  | 2 | 0 |  | Internal NCR
NCR0446 | 2022-01-05 | 609 | Gangway | Gangway locks missing | KTW | Low | Reason unknown | Need to fix the side panel locks | Open |  | 2 | 0 |  | Internal NCR
NCR0447 | 2022-01-09 | 511 | Roof | Roof antenna damaged due to hit roller shutter at W5 while movement | Alstom | Low | Accident train, shutter door opening not checked by the PICOW befre the train movement | Required to replace new antenna. Item: PLANAR ANTENNA N FEMALE CONNECTOR, DTR No : DTR0000170632, Quantity : 4. | Closed | CMN0518 | 3 | 4 | 2022-01-17 | Internal NCR
NCR0448 | 2022-01-09 | 415 | Electrical wiring | Cant move train in WM as WM in hc1 no active | Alstom | Low | Checked and found the realy 61K07 were defective. | Need to change relay. | Closed | CMN0510 | 3 | 3 | 2022-01-12 | Internal NCR
NCR0449 | 2022-01-09 | 607 | Bogie | Gearbox oil axle 3 is contaminated. | Le Creusot | Low | Need laboratory report and root cause need to be defined. | For further checking activities we received laboratory report. | Open |  | 3 | 0 |  | Internal NCR
NCR0450 | 2022-01-09 | 607 | Bogie | Gear box oil level is below minimum level | Le Creusot | Low | Gearbox oil were not fully fill when train were in factory. | Need to topup the gearbox oil. | Open |  | 3 | 0 |  | Internal NCR
NCR0451 | 2022-01-10 | 412 | PACIS | PEI1-V2 offline, Both portE1 and E2 no communication | STE - VBN | Low | PEI component faillure | Replace PEI | Closed | CMN0513 | 3 | 3 | 2022-01-13 | Internal NCR
NCR0452 | 2022-01-10 | 422 | PACIS | LEDI1-V2 offline and dark | STE - VBN | Low | LEDI1-V2 component faillure | Replace LEDI | Open |  | 3 | 0 |  | Internal NCR
NCR0453 | 2022-01-10 | 611 | Battery | Battery Door tubular seal some damaged | Hoppecke | Low | Battery Door tubular seal damaged, Wrong handling of the door opening | Replace Rubber | Open |  | 3 | 0 |  | Internal NCR
NCR0454 | 2022-01-10 | 611 | Battery | Battery Door External safety label damaged | Hoppecke | Low | Label damaged during handling | Replace label | Open |  | 3 | 0 |  | Internal NCR
NCR1002 | 2022-01-11 | 409 | CVS | IOS185 : 1 APC LV Status false, IOS179 : 1 APC MV Status false | CRL | High | Root cause still not define but we need a CVS converter to perform a test. | To be confirmed | Open |  | 3 | 0 |  | Internal NCR
NCR1007 | 2022-01-18 | 611 | Doors | DCU Faulty No Communication(Data bus Communication Failure) | CRL | Low | Unknown | Need to install new EDCU | Closed | CMN1007 | 4 | 5 | 2022-01-24 | Internal NCR
NCR1038 | 2022-01-24 | 415 | Interior | HC1 ROOF PANEL1 ALLEN SREW 1MISSING AND 1DAMAGE HC2 ROOF PANEL1 ALLEN SREW1DAMAGE | CRL | Low | Due to not alignment properly and put by force the screw. | Need to install new nut and screw | Open |  | 5 | 0 |  | Internal NCR
NCR1044 | 2022-01-24 | 402 | Interior | HC1 ROOF PANEL1 ALLEN SREW 1MISSING AND 1DAMAGE HC2 ROOF PANEL1 ALLEN 2 SREW1DAMAGE. | CRL | Low | Due to not alignment properly and put by force the screw. | Need to install new nut and screw | Open |  | 5 | 0 |  | Internal NCR
NCR1056 | 2022-01-10 | 404 | Bogie | Gearbox 1&2 oil level below minimum but no leakage issue observed. | CRL | High | Oli not fully inserted since from factory. | Need to topup gear box oil. | Open |  | 3 | 0 |  | Internal NCR
NCR1073 | 2022-01-18 | 603 | Gangway | GANGWAY INTERNAL PANELS IS MISSING | KTW | Low | Unknown | Need to install new | Open |  | 4 | 0 |  | Internal NCR
NCR1076 | 2022-01-24 | 609 | Interior | HC1 ROOF PANEL1 ALLEN SREW 1MISSING AND 1DAMAGE HC2 ROOF PANEL1 ALLEN 2 SREW1DAMAGE. | KTW | Low | Due to not alignment properly and put by force the screw. | Need to install new nut and screw | Open |  | 5 | 0 |  | Internal NCR
NCR1087 | 2022-01-19 | 502 | Gangway | Gangway locks missing | KTW | Low | Unknown | Need to install new | Open |  | 4 | 0 |  | Internal NCR
NCR1088 | 2022-01-19 | 512 | Gangway | Gangway locks missing | KTW | Low | Unknown | Need to install new | Open |  | 4 | 0 |  | Internal NCR
NCR1092 | 2022-01-18 | 602 | Bogie | The 750 HV cable from the Fuse box to the Junction box was damaged during a sweep run on the mainline | Alstom | Low | Incident in the mainline | Need to install new | Open |  | 4 | 0 |  | Internal NCR
NCR1098 | 2022-01-18 | 408 | Gangway | GANGWAY INTERNAL PANELS IS MISSING | KTW | Low | Unknown | Need to install new | Open |  | 4 | 0 |  | Internal NCR
NCR1099 | 2022-01-10 | 611 | Battery | HC1, Battery Door tubular seal some damaged | KTW | Low | HC2 ROOF PANEL1 ALLEN 2 SREW1DAMAGE. | Replace rubber | Open |  | 3 | 0 |  | Internal NCR
NCR1109 | 2022-01-18 | 402 | Gangway | Gangway locks missing | KTW | Low | Unknown | Need to install new | Open |  | 4 | 0 |  | Internal NCR
NCR1111 | 2022-01-17 | 415 | Doors | DCU Faulty No Communication | KN | Low | Unknown | Need to install new DCU | Open |  | 4 | 0 |  | Internal NCR
NCR1130 | 2022-01-17 | 615 | Coupler | Semi permanent coupler grounding bolt missing | KN | Low | Not in stock, need to request the new material | Need to install new | Open |  | 4 | 0 |  | Internal NCR
NCR1150 | 2022-01-13 | 414 | Interior | Partition door lock missing | KTW | Low | Unknown | Need to install new | Open |  | 3 | 0 |  | Internal NCR
NCR1152 | 2022-01-24 | 404 | Interior | HC1 ROOF PANEL1 ALLEN SREW 1MISSING AND 1DAMAGE HC2 ROOF PANEL1 ALLEN 2 SREW1DAMAGE.Partition door lock missing | KTW | Low | Due to not alignment properly and put by force the screw. | Need to install new nut and screw | Open |  | 5 | 0 |  | Internal NCR
NCR1154 | 2022-01-17 | 403 | LV | Unconnected Grounding cable in the LV Box | KTW | Low | Unknown | Need to install new | Open |  | 4 | 0 |  | Internal NCR
NCR1168 | 2022-01-19 | 615 | HVAC | HVAC -Venting error in MONA software but physically we cheched its was working | FT | Low | Unknown | Need to checked with supplier | Open |  | 4 | 0 |  | Internal NCR
NCR1194 | 2022-01-24 | 626 | CVS | 52Q11 and 11Q02 was tripping (short circuit in AA3S) | CRL | Low | Unknown | Need to install new AA3S | Open |  | 5 | 0 |  | Internal NCR
Formulas:
NCR Opened Week = WEEKNUM([Date raised])
NCR Closed Week = WEEKNUM([NCR Closed date])

## 8D
2022-01-25
8D Ref | Date raised | Impact K# | Sub-system | Description of issue | Responsibility | Root Cause | Correction Required | Target Date | Status 8D Step | Comments/Progress
8D-144118 | 2019-11-14 | K1S | Traction | Loosening tightening torque on traction box fixation bolt M16 between Traction feet and CBS | CRL | For the interface level, single layer paint for bolted connection (ASP10 category) has not been requested during design phase and it’s the reason why it’s not exported to CB | 1. Torque (re)check before start refenue service 2. To take into account REX from metro Amsterdam 3. 2nd wave of inspection completed. RUH_TSY_RST_Traction bolts control sheet 2nd wave 4. Control of additional 77 connection defined by Eng. (see action) 5. Last torque inspection completed 30-12-2020 for 28 Trains. |  | D8 : Closed
8D-200484 | 2021-03-26 | K4 | PACIS | TCCU offline in TCN - Master does not manage all system at certain times (TCU card online) TCCU issues: 3 types of issues 1. TCU card offline 2. TCCU Master does not work 3. TCCU loss com | STE - VBN | 1. TCU card offline - Root cause: Manual installation with bad IP address 2. TCCU Master does not work - Root cause: Software (TCCU MAIN ) is crashed. 3. TCCU loss com: Root cause: Manual installation with bad IP address | 1. TCU card offline - Reflash the module, proceed with automatic software installations => Done 2. TCCU Master does not work - TCCU mastership issue is resolved with STR 5.6.1 --> DOne 3. TCCU loss com: Reflash the module, proceed with automatic software installations => Done | 2022-01-30 | D7 : Rex | D7 is ongoing, Brainstorming session is scheduled to complete the REX
8D-200494 | 2021-03-26 | K4 | PACIS | PEI : 3 types of issues 1. PEI speech not working 2. PEI power off: 3. PEI unstable | STE - VBN | 1. PEI speech not working: Hardware issue, component failure on PICU board 2. PEI power off: Software design issue : Memory corrupted after shut down during write procedure 3. PEI unstable: Bad manual installation | 1. PEI speech not working: Replace the IP PICU board done 2. PEI power off: Correction (preventive action) need to use shutdown command from TCMS -> TCCU -> All devices (LCD Displays, TCCU, TOCP, PEC, NVR) to instruct all devices to stop writing logs to FLASH memory when power shutdown is expected. =>5.6.1 is installed, now under monitoring 3. PEI unstable: SW 5.6.0 to be reinstalled before installation of 5.6.1 =>5.6.1 is installed in 3 trains, now under monitoring | 2022-01-30 | D7 : Rex | D7 is ongoing, Brainstorming session is scheduled to complete the REX
8D-209814 | 2021-06-23 | K1S | CVS | CVS MF Transformer terminal and cables burned. | CRL | Loosening of the litz cable fasteners of CVS Transformer | 1) Inspection of the torque on entire fleet of CVS MF Transformer Litz cables fasteners 2) Redo the torque marking and set the right torque again 3)Rreinspect the torque on 50% of CVS (which were initially not ok) 3 months after first inspection to confirm whether its a production or design issue 4)Other corrective actions depends on the results of D5 | 2022-02-10 | D5 : Root cause | one action ongoing in Riyadh to recheck the torque on the CVS MF transformers which were detected Torque Not OK before . This recheck is to be done 3 months after first inspection and correction date as per the instructions from CRL. This recheck will trigger the corrective actions ( after confirming whether it is a design /manufacturing issue).
8D-210735 | 2021-07-01 | K1S | Doors | Train Running with one Unlocked Door | Alstom | Mechanical adjustment issue on the door “unlock” function. | 1) Mechanical Adjustment of EED (Emergency Egress Device) 2) Design improvement to be done(under discussion) A) Current design: As per the actual design, the train does not stop if during movement all doors are closed and the locked signal is lost  when the train reaches the next station, an operator must intervene to isolate the concerned door B) New proposed design: When the train is running ( Vitesse > TBD) and a door is detected as not locked, a full-service brake will be applied by the train, then the normal evacuation process will take place 3) Supplier KN still to provide the corrective actions to be implemented | 2022-01-25 | D5 : Root cause | Investigation ongoing with Supplier KN
8D-145850 (MULTI-PROJECT) | 2019-11-28 | K1S | Battery | Open Battery cells and water refilling rubber hoses cracked | Hoppecke | To be compliance to EN45545, a flame retardant had been used in Polyflam plastic cell and this chemical corrode or accelare the degradation of the plastic. This is generate a leackage of plastic cell | Change of battery case material from Polyflam to Thermofil |  | D5 : Root cause | All batteries retrofit fully completed. Total 138 of 138 (plus 3 spares) retrofitted and installed in the fleet. Topic is closed for Riyadh.
8D-204175 (MULTI-PROJECT) | 2021-04-30 | K1S | Brakes | SMNW - Faiveley Reducing Valve Potentially causing Parking Brake Failure | FT | Insufficient design of the pressure reducing valve : The design of the pressure reducing valve had the potential to prevent the reversibility function of the valve, which is needed to apply the parking brake on the trains that are switched off/de-energised if there is a leak in the air supply. The lip seal and rubber bonded valve in combination did not allow air to pass through by not moving as it was tight. It was discovered that this occurred at increased temperatures which resulted in over pressure on the output pressure side of the valve. | There are currently 2 solutions being validated by FT. One involves modifying the valve diameter - making it smaller to increase the capability of balancing pressures which will allow reversibility. The second solution (will be implemneted in Riaydh) involves modification to the valve by introducing a channel between supply pressure and output pressure and the addition of an o-ring to act as a check valve to balance the pressure. |  | D6 : Correction | 18-Jan-2022: Parts will be received by end of Jan 2022. ***** Retrofit activities of parking brakes will start after receiving the parts.Valve delivery has been delayed. Now due in mid December. Amended target start date from 10/12/2021 to 28/02/2022. FT Australia is producing a plan to roll out the modified valve and will advise how they will manage the spares.
8D-231330 | 2021-12-09 | K1S | Brakes | No holding brake applied in the stabling when the train is awake and doors closed | Alstom | To be managed with CHR#M3-TSY-CHR-000475 | To be managed with CHR# M3-TSY-CHR-000475 | 2022-01-30 | D5 : Root cause | This 8D to be closed as this issue will be managed through the CHR# M3-TSY-CHR-000475. to be followed with RAMS director for the closure of this 8D and also to categorize it to K3 Or K4.
8D-231727 | 2021-12-12 | K1 External | Roof | Train roof hit the shutter door while in shunting operation using loco shunt (Unimog) | Alstom | 1) The shutter door was not fully opened when the train movements started. The PICOW was positioned at the back of the second train ( 80mts away from the door) and could not detect in time that the door was not opened enough. 2)Due to fatigue, the shutter door operator applied minimum effort when opening the door. He assumed that he had opened the shutter door sufficiently for the train to pass. He misjudged the required height. | 1) The drivers and picows should be instructed not to move any train unless the shutter door is 100% open (Responsibility : TOO) 2) The shutter doors should be electrified asap so that the door opening is facilitated and the fatigue root cause is removed (Responsibility : CJV) 3) To mark the shutter door frames so that visually it can be verified whether the door has been sufficiently opened before the train movement starts (Responsibility ---> Alstom) | 2022-02-10 | D6 : Correction | D6 ongoing, refer to the corrective actions

## REX
2022-08-25
Rex No | Date raised | Origin of Rex | Sub-system | Description of issue | Responsibility | Potential Impact | Root cause | Action required | Target Date | Status | Comments/Progress | Inspection Report No.
REX001 | 2021-09-02 | Dubai | Gangway | Gangway stitching found melting and sticky | Ultimate | Train OK for mainline | Statement from Supplier(ULTIMATE): "This used butyl tape can slightly work its way out of the seam in the course of the movements, as this is a permanently pasty material that does not harden. From Ultimate side we see no technical problem with this issue about melting and sticky of sealant, on the contrary, it is a normal effect of this sealing." | Full fleet inspection to be done | 2021-09-18 | Inspection OK | Full fleet has been verified fully in detail, all ok. This activity is covered in preventive maintenance.
REX002 | 2021-08-23 | Dubai | Smoke detector | Heater fault in smoke detector | TBC | Train OK for mainline | A heater device is included to these detectors to remove humidity from smoke chamber to avoid dust to stick on humidity and avoid false alarm. Heater device switch on & off temperature was identical (45°C). On Dubai Metro if HVAC was off, temperature reach 45°C and remain stable. Software request heater to switch on & off several time in a short period. Heater was not able to follow this order and declare itself as faulty and ask for reset | 1) Fault log to be shared with the supplier to confirm we have the same issues as Dubai. If confirmed supplier will release new SW-->Done 2) 4Tools to be ordered for the SW upgrade 3) Cleaning of smoke detectors to be added to monthly preventive maintenance |  | Correction under implementation | Software to be updated for the Smoke detector, Waiting for the tool to upload. These tools are not available in the market. 20-Jan-22: PO to be issued-->Elie
REX003 | 2021-08-23 | Dubai | HVAC | False alarm issue | FT | Minor Restriction | All detectors have heavy dust accumulation on external cover. Dust comes off detectors cover and go through smoke chamber. This amount of particles is not consider as dust due to software behavior (accumulation is a long process and don’t consider huge increase of dust). Opacity of light beam detector is increasing and after validation time a fire alarm is trigger. This analysis confirm supplier analysis and Alstom expectation. | Cleaning of smoke detectors to be added to monthly preventive maintenance instead of every 6 months according to care taking plan |  | To be further monitored | Cleaning of smoke detectors is added to monthly preventive maintenance
REX004 | 2021-07-27 | Dubai | CVS | Neutral inductor burnt in 7 trains (5 Revenue trains) due to new APS sw 1.4.14. RCA is known and it is due to new sw and the sw was reverted as instructed by CRL. New sw version 1.5.0 released and under test trials on 5 trains. So far no issue observed. | CRL | Train NOT OK for mainline | Under analysis at Supplier (BLOCK) and in Dubai by CRL team. RCA report expected by 09-Sep Preliminary results show issue due to quality issue of potting in the material and core over-temperature | 1) Full fleet inspection to be done 2) Implemented software modification to be discussed with CRL. Are we at risk? | 2021-09-30 | To be further monitored | 138 of 138 CVS have been verified, no burn marks have been observed
REX005 | 2021-08-04 | Dubai | Bogie | M36 screw lost on stone guard | LCR | Train OK for mainline | 1) Paint issue on stone guard (issue probable) - Surface without paint too small =>> pre-tention lost 2) + Lack of Loctite (issue confirmed) - Low quantity of loctite found on the screw =>> process implementation of Loctite =>> securization of the bolt assembly (with Loctite) not sufficient 3) Tab washer installation issue (issue highly probable) - Installation of the tab washer not optimale =>> second securization of the bolt assembly failed | 1) Replace all bolts and tab washer which new spares 2) Check the conformity of the painting area in the assembly 3) Ensure the Loctite application in line with the new procedure (Loctite apply on screw and tapping) 4)Install the tab washer in line with the new procedure |  | Not applicable | Riyadh does not have a stone guard
REX006 | 2021-08-22 | Dubai | Bogie | Screws missing or untightened on axle boxes | LCR | Train NOT OK for mainline | Rootcause under investigation: 1) Screws have been tightened in Le Creusot factory, using automatic control torque wrenches. =>> Tightening curve and mounting procedure under analysis 2) Map of the damage under investigation 3) SKF, who designed and delivered the axlebox, is deeply involved. | Visual inspection of the fleet : check if screws are not missing and if the torque mark is not cutted and retorque if required. |  | To be further monitored | Inspection done on complete fleet, 34% of bolts had to be retorqued. Need further investigation on the rootcause of this issue. New full fleet inspection is required in 3 months. | IR0001
REX007 | 2021-08-23 | Dubai | Bogie | Gearbox labyrinth R Ring displacement issue | LCR | Train OK for mainline | under investigation | Visual inspection of the fleet : check that labyrinth R Ring is in correct position |  | Inspection OK | Inspection completed on full fleet, no issue found | IR0002
REX008 | 2021-08-23 | Dubai | Bogie | Oil leakage detected on gearbox door inspection | LCR | Train OK for mainline | 1) Wrong flatness of the covers 2) Gasket (loctite 518) not properly applied | Visual inspection of the fleet . If leakage is found a replacement of the gasket is required |  | To be further monitored | Inspection completed on full fleet, 9 out of 552 have leakage. Gaskets to be changed during the 30K Kilometers gearbox overhaul | IR0003
REX009 | 2021-09-13 | Dubai | Doors | DOORS – Obstacle issue - Supplier: KN CHINA False door obstacle detection encountered after the doors were adjusted to detect 10mm obstacle (contractual requirement) from its previous position of 6mm | KN | Train NOT OK for mainline | Due to HVAC overpressure, false door obstacle detection appeared during service. Random behavior identified: the issue is not appearing at each station, not on the same door and not on all the trains. The default is not repeatable and difficult to detect, as it is concerning only a small percentage of the fleet cycles. | 1a) Check the contractual requirement applicable to Riyadh--> Mattias 1)Software modification: Slip the control at the end of closing phase, optimizing the speed and current of the different segments to improve both obstacle detection function and door closing function. 2) Rubber insert implementation on door leaf: Insert a rubber in the cavity of the finger protection rubber to reduce the seal displacement and increase the obstacle detection property. |  | Not applicable | 1) The door is not the same as Dubai 2) We do not have the same contractual requirement for obstacle detection as Dubai 3) We need to double check with the supplier KN if in our case we need to modify the door software
REX010 | 2021-08-15 | Dubai | CVS&Traction | APS – AGATE Failures - Supplier: AT Charleroi / AT VBN 8D#202543: Agates in CVS (DTR2000002771) failing in fleet with U12V error code. | CRL | Train NOT OK for mainline | Issue is with the DC/DC converter “PMD50” bought directly from MTM (VBN’s supplier – Design authority is CRL) mounted on the Agates. There is an identified problem with the failure of converter which leads to the false detection of internal over-temperature which shuts down the converter permanently. As the Agate does have the power supply from the converter, it cannot operate and therefore declared as an Agate failure. The DC converter is not designed to withstand the temperature inside CVS. | Retrofit the full fleet with new PMD60 converters which are validated and proven design eliminating the failure of false detection in internal over-temperature. Due to time constraints of the project, it is decided to replace all Agates with new Agates manufactured with PMD60 and perform the retrofit of existing stock in parallel. |  | Under Investigation | 1)CRL to check the concerned qty of this issue related to Riyadh. 2) PMD50 agates to be sent back to CRL once the action plan is in place (issue with only 1 of 2 suppliers) - Serial numbers of Agates (276 of 276 ) have been collected 20-Jan-22: 56 of Agates to be replaced, duplication of serial numbers to be rechecked for L4&6 -->Elie& Osama
REX011 | 2021-08-15 | Dubai | CVS&Traction | APS – AGATE Failures - Supplier: AT Charleroi / AT VBN 8D#202542 : Agates in CVS (DTR2000002771) and Traction (DTR2000000075) have premature failures in fleet | CRL | Train NOT OK for mainline | Failure occurred due to Resistances R1156-R1281 mounted in the Agate failed prematurely. Issue observed mainly during the first few kms run by each train. Fleet wide retrofit launched by AT VBN and CRL. Retrofit halted mid way and planned to be done along with U12V error issue. | Retrofit full fleet for resistance R1156-R1281. Meanwhile to mitigate failure, additional spares stock provided. |  | Correction under implementation | 1) Retrofit and test 58% (116 pcs out of 200) of line L4 & L6 completed. L5 still not started. 2)Retrofit is stopped due to lack of varnish, delivery ongoing 3)Procurement to be done for the other chemical ULS. 20-Jan-22: Prepare the first batch of parts to be sent , regroup the agates to be exchanged considering the retrofits of PMD60 and Resistor change -->Elie& Osama
REX012 | 2021-08-23 | Dubai | E Cubicles | 8D# 213977 : Increase of STPI Relay Failures H600 - DTR00267348HE mounted inside Electrical cubicles | CRL | Major Restriction | The problems on relays are located in its control coil. This problem has been encountered in the past, and the conclusion was due to it’s manufacturing problem. Report awaited from Supplier. | Full fleet replacement of H600 Relays is required |  | Under Investigation | Charaf to identify the critical relays to be replaced -->Charaf
REX013 | 2021-09-27 | Dubai | HVAC | VAC – Water leakage: Water leakage observed from VAC drain pipe & flexible hose connections wherever the rubber gets mated with metal surface | FT | Major Restriction | Improper tightening of hose with metal cover found to be the root cause | Details not available |  | Not applicable | different HVAC supplier
REX014 | 2021-09-27 | Dubai | CVS | APS – Power modules: Train specific issues. Power module fails , CVS went to degarded mode | CRL | Minor Restriction | Details not available | Dubai waiting for investigation report from CRL |  | Not applicable
REX015 | 2021-09-27 | Dubai | Traction | Traction – IES Limit switch: Dust accumulation inside the IES switch panel leading to failure of limit switch. Panel is IP40 rating and isn’t preventing dust ingress inside panel. Corrective action plan under discussion. | CRL | Train NOT OK for mainline | Dust accumulation inside the IES switch panel leading to failure of limit switch. Panel is IP40 rating and isn’t preventing dust ingress inside panel. | Full fleet inspection to be done |  | Investigation Not Started | Inspection started in Line 5, this activity to be included in 2weekly preventive maintenance activity till the inspection is completed. Target to be completed 5th Feb 2022 -->Osama
REX016 | 2021-09-27 | Dubai | Doors | Door closing fault: Issue due to poor workmanship | KN | Train NOT OK for mainline | Issue due to poor workmanship. Car D door A2 guiding rail bolts are loose & misaligned due to which the door cannot be closed nor isolated | Rework |  | Not applicable | Riyadh door is not the same
REX017 | 2021-09-27 | Dubai | Interior | Draught screen found broken inside the train | KTW | Train NOT OK for mainline | Wrong installation in factory leading to internal stress inside the glass and sudden shattering. | check bracket alignment for any random draught screen which is healthy to see the bracket alignment |  | Not applicable | Riyadh does not have the same screens
REX018 | 2021-11-16 | Dubai | Doors | Movement with door opened | KTW | Train NOT OK for mainline | The analysis has demonstrated that the fault has been the consequence of an event which is external to the design and which although being alarmed to the operator, the operator did not respond to it. | Although the door assembly is compliant to standard and industry practice, in the spirit of collaboration and for customer satisfaction, Alstom will propose to insulate the affected switches in the SIL4 loop by the use of insulated covers for the terminals. Picture below is for sole illustrative purpose and proper change process will be followed. |  | Investigation Not Started | Improvement proposal to be done on 1 door train by Taha by 27-Jan-2022.-->Taha
REX019 | 2021-08-31 | Dubai | Doors | Unexpected unlocking of train door (8D#216589) | KTW | Train NOT OK for mainline | Due to locking nut creating inconsistancy in closing of doors, locking switch triggered in advance leading to inconsistancy between LHS & RHS of door leaf. | Corrective action has three steps: 1. Door locking nut inspection - completed on full fleet of dubai 2. S1 switch adjustment - completed on full fleet. 3. Door unlocking force measurement - to be initiated in fleet based on the acceptance criteria to be defined by KN. 6 projects identified to be impacted with this issue and REX shared to each project site for their internal validation and retrofit. |  | Not applicable | Riyadh is not identified as impacted project by Suppleir KN
REX020 | 2021-10-21 | Dubai | Brakes | Air Reservoir Tank fixation issue 8D#223232. Fixation bands found loosen with potential transversal misplacement of the tank | FT | Train NOT OK for mainline | RCA ongoing | Steps to follow & check (For Dubai Metro) : 1. RE-TIGHTEN SCREWS AND APPLY TORQUE 25 Nm. 2. MEASURE CURRENT DISTANCE FROM AIRTANK TO CONNECTION PIPE (DIMENSION 210±2 mm). 3. MARK 10 mm INDICATION ON ALL PIPES CONNECTED DIRECTLY TO THE TANKS (USE PERMANENT MARKER) FOR MONITORING. Steps to follow & check (For Riyadh Metro) : 1. RE-TIGHTEN SCREWS AND APPLY TORQUE 35 Nm (Class 8.8 screw) 2. To be checked with supplier for further actions |  | Investigation Not Started | Inspection to be planned for the torque mark and retorquening, target by 5th Feb 2022 -->Osama
REX021 | 2021-09-29 | Dubai | CVS | CVS Voltage transducer faulty | CJM | Train NOT OK for mainline | Faulty sub-component "wafer" (To be validated in 8D team). A sub-component inside the current sensor become faulty in a high humidity environment. The sub-component in question is the wafer, and for a specific batch it has been found a deviation with the borophosphosilicate Glass (BPSG) deposition. The relatively higher concentration of Boron in the BPSG film may allow the BPSG to be susceptible to moisture absorption. Moisture absorption can increase the potential for inter-layer dielectric (ILD) separation with exposure to stresses after wafer processes. Batch incriminated : from 819177 to 819252 (Current sensor SN) | Retrofit and replacement of the sensors identified as faulty or potentially faulty in the future. the serial numbers installed on the Riyadh tractions and found that the following 4 are faulty and have to be returned back to Coimbatore for analysis/replacement. • 8191880115 – Installed on TC#2132, mounted on Train#616 – HSCB Platine input stage – LVMD (part was fixed on TC#2132 in week 47 of year 2019 as it was damaged during retrofit assembly) • 8191880118 – part of consignment stock at Riyadh depot • 8191880117– part of consignment stock at Riyadh depot • 8191880114– part of consignment stock at Riyadh depot |  | Under Investigation | 20-Jan-2022: Check the stock for the exact sapares avaialble and send the 2 parts to Coimbatore considering the impact. -->Elie

## NCR KPI
NCR KPI
Status | Count of Status
Cancelled | 10
Closed | 206
Open | 79
Grand Total | 295
Responsibility | Count of Responsibility
Alstom | 35
CRL | 30
FT | 21
Hoppecke | 5
KN | 24
KTW | 63
Le Creusot | 16
STE - VBN | 101
Grand Total | 295
Sub-system | Count of Sub-system
Battery | 3
Bogie | 10
Brakes | 3
Carbody | 1
Compressors | 1
Coupler | 5
DCS | 1
Derailment sensor | 1
Doors | 5
Electrical wiring | 1
Gangway | 11
HVAC | 3
Interior | 7
Lighting | 5
PACIS | 9
Sanding | 2
Shoe Collector | 3
SLV-ATC | 1
Traction | 1
Windows | 3
CVS | 2
LV | 1
Grand Total | 79

## 8D KPI
8D KPI
Status | Count of Status 8D Step
D5 : Root cause | 4
D7 : Rex | 2
D8 : Closed | 1
D6 : Correction | 2
Grand Total | 9
Responsibility | Count of Responsibility
Alstom | 3
CRL | 2
FT | 1
Hoppecke | 1
STE - VBN | 2
Grand Total | 9
Sub-system | Count of Sub-system
Battery | 1
Brakes | 2
CVS | 1
Doors | 1
PACIS | 2
Traction | 1
Roof | 1
Grand Total | 9

## REX KPI
REX KPI
Status | Count of Status
Correction under implementation | 2
Inspection OK | 2
Investigation Not Started | 3
Not applicable | 7
To be further monitored | 4
Under Investigation | 3
Grand Total | 21
Responsibility | Count of Responsibility
CJM | 1
CRL | 6
FT | 3
KN | 2
KTW | 3
LCR | 4
TBC | 1
Ultimate | 1
Grand Total | 21
Sub-system | Count of Sub-system
Bogie | 4
Brakes | 1
CVS | 3
CVS&Traction | 2
Doors | 4
E Cubicles | 1
Gangway | 1
HVAC | 2
Interior | 1
Smoke detector | 1
Traction | 1
Grand Total | 21

## SQ NCR KPI
SQ NCR KPI
Status | Count of Status
Corrective Action defined | 1
NCR closed | 23
NCR opened | 1
Grand Total | 25
Responsibility | Count of Responsibility
CRL | 3
STE - VBN | 21
FT | 1
Grand Total | 25
Subsystem | Count of Sub-system
CVS | 3
OBCN | 1
PACIS | 20
Brakes | 1
Grand Total | 25

## KPI S-curve (hidden)
Week num | New NCR opened | Total NCR opened | NCR Closed this week | Total NCR Closed | Remakrks
W53 | 255 | 255 | 174 | 174
W01 | 1 | 256
W02 | 1 | 257
W03 | 2 | 259
W04 | 3 | 262
W05 |  | 262
W06 |  | 262
W07 |  | 262
W08 |  | 262
W09 |  | 262
W10 |  | 262

## SAP NCR request (hidden)
Sno | NCR No | Train Impacted | Item description | Date Requested | Quantity Requested | DTR reference | SAP NCR Status | Comments/Progress/Evidence
1 | NA |  | Door seal for the battery door | 2021-12-02 | 20 | DT0000900284 | Requested to KTW | KTW to update
2 | NA |  | HDD WD10JUCT | 2021-12-02 | 5 | DTR0000377521 | Requested to KTW | KTW to update
3 | NA |  | Sand filter Assembly (Manufacture reference: CIDM000288231) | 2021-12-09 | 1 | Not available | Requested to KTW | KTW to update
4 | NCR0354 | 401 | Connector Han 42DD-F. XP03+GCL (issue with ATC odometer) | 2021-12-15 | 10 | DTR0000069085 or DTR0000318277 | Requested to KTW | KTW to update
5 | NCR0359 | 608 | Semi-permanent coupler side A earthing screw (Head Screw) | 2021-12-15 | 20 | DTR0009908251 | Requested to KTW | KTW to update
6 | NCR0361 | 603 | Beacon Antenna screws & washers | 2021-12-15 | 10 | DTR0009908442 & DTR0009909474 | Requested to KTW | KTW to update
7 | NCR0372 | 606 | Gap filler between HVAC and Gangway missing | 2021-12-15 | 10 | DW00000768254 | Requested to KTW | KTW to update
8 | NCR0358 | 411 | Electric coupler FRAME
|  |  | FRAME | 2021-12-15 | 1 | DTR0000464801 | Requested to KTW | KTW to update
|  |  | SEAL FRONT | 2021-12-15 | 1 | DTR0000464814 | Requested to KTW | KTW to update
|  |  | SOCKET HEAD SCREW, A4-80, ISO 4762 M5X25 | 2021-12-15 | 10 | DTR0000286568 OR DTR0000286577 | Requested to KTW | KTW to update
|  |  | GUIDING PIN | 2021-12-15 | 1 | DTR0000142062 | Requested to KTW | KTW to update
|  |  | SEAL STRIP | 2021-12-15 | 2 | DTR0009611643 | Requested to KTW | KTW to update
|  |  | WASHER | 2021-12-15 | 1 | DTR0009611655 | Requested to KTW | KTW to update
|  |  | SOCKET HEAD SCREW, A4-80, ISO 4762 M6X25 | 2021-12-15 | 1 | DTR0009012929 | Requested to KTW | KTW to update

## Supplier NCR (hidden)
2021-12-15
NCR No | Date raised | Train Impacted | Sub-system | Description of issue | Responsibility | Impact | Root cause | Correction required | Status | Comments/Progress/Evidence | Type
188667 | 2021-04-07 | All | PACIS | D-TCCU master doesnt work | STE - VBN | Minor Restriction | SW issue | Issue to be resloved with STR5.6.1 | NCR closed
188673 | 2021-04-08 | All | PACIS | N-PEI not working (speech) | STE - VBN | Major Restriction | Hw : Repair at STEE site (Change out 3-port switch card) Sw : Repair at Riyadh | Hw : Repair at STEE site Sw : Repair at Riyadh | NCR closed
188791 | 2021-04-08 | All | PACIS | G-NVR Solder | STE - VBN | Major Restriction | Hw issue, quality of soldering of NVR components | Hw issue, Retrofit by STEE sent back to Riyadh. | NCR closed
192367 | 2021-05-19 | All | PACIS | A-issue LCD brightness | STE - VBN | Train OK for mainline | Issue 2, 3 and 1 : Sw & Issue 4: hw- rough handling | SW:Define and implement contrast checking as per the sw release note | NCR closed | Issue is closed SW: SW release note 5.6.1 HW: DCU4 repaired by STE in Riaydh
192374 | 2021-05-19 | All | PACIS | B-LCD (LID) white screen | STE - VBN | Minor Restriction | SW Issue: damage of memory flash | Repair by STEE / installation Correction of SMARC module by 5.6.1 | NCR closed
192376 | 2021-05-19 | All | PACIS | J-Display 18.5 not working | STE - VBN | Minor Restriction | Bad SW installation. | Re instal Sw | NCR closed
192376 | 2021-05-19 | All | PACIS | K-Display 18.5 working loss com | STE - VBN | Minor Restriction | Several hardware issues | Replacement of faulty hardware parts | NCR closed
192379 | 2021-05-19 | All | PACIS | L-SWD Half | STE - VBN | Minor Restriction | Hardware issue | Repair/replacement of the AD board | NCR closed
192707 | 2021-05-19 | All | OBCN | E-PAPIS in UM | STE - VBN | Minor Restriction | netbox configuration issue | Upload with new software V3.8.0 | NCR closed | Low priority , no impact on sys demo and trial run
192708 | 2021-05-19 | All | PACIS | F-Fault loss com (TCCU) | STE - VBN | Major Restriction | SW task stopped which is not normal and TCCU is not seen by ISM | To be corrected by 5.6.1 | NCR closed
192709 | 2021-05-19 | All | PACIS | H-NVR power supply | STE - VBN | Major Restriction | Hw issue, power supply component defective | Retrofit by Riyadh. . | NCR closed
192711 | 2021-05-19 | All | PACIS | I-NVR mask camera | STE - VBN | Minor Restriction | SW issue | Correction to be implemented in STR571 | Corrective Action defined | 22-Dec-2021: Correction will be implemented in STR 5.7.2 (to be confirmed) 18/11/21 : Correction implemented in STR571 : tests to be done in dynamic mode @Charaf to check when the tests can be performed.
192713 | 2021-05-19 | All | PACIS | O-PEI power off | STE - VBN | Major Restriction | Sw issue: corruption of memory | New software STR 5.61 to be installed - For new issues with such problems it can be corrected with STR 5.6.1 | NCR closed
192713 | 2021-05-17 | All | PACIS | U-SWD White screen | STE - VBN | Minor Restriction | Bad SW installation. | Reinstall the last PACIS release | NCR closed
192714 | 2021-05-19 | All | PACIS | P-PEI not stable | STE - VBN | Minor Restriction | Bad SW installation. | Reinstall the last PACIS release | NCR closed
192716 | 2021-05-17 | All | PACIS | S-SW central upload | STE - VBN | Train OK for mainline | Analysis to start, problem with PST alstom tool. | Use only the software update tool provided by STE | NCR closed
192717 | 2021-05-19 | All | PACIS | T-Eqpmt contain old SW content | STE - VBN | Train OK for mainline | SW installation tool issue. | Sw Clean up in STR5.6.1 | NCR closed | 5.6.1 implemented
196402 | 2021-06-22 | 615 | CVS | CVS MF Transformer terminal and cables burned. | CRL | Train OK for mainline | litz cables fastenings found loose and out of torque | Verify and retorque all the fastenings of litz cables of the CVS transformer terminals which are out of torque | NCR closed | 138 CVS(100%) have been inspected and the re-marking and retorquing has been done for the incorrect ones.
196626 | 2021-06-24 | 424 | CVS | Internal short circuit CVS 3-phase output contactor | CRL | Train NOT OK for mainline | to be updated once root cause is provided by CRL | 1) Replace the ouput 3-phase output contactor 2) Implement corrective actions once they are provided by CRL | NCR closed | Removed, replaced with new output contactor. Parts sent to CRL, Root cause and corrective actions under investigation. This NCR will be managed through the portal.
199832 | 2021-07-25 | 516 | CVS | Internal short circuit in CVS invertor power module | CRL | Train OK for mainline | >>wrong connection for current sensor feedback. wiring found wrong connection between SI_11W13 bus bar for SI_11B02(MesUrsOutInv) and SI_11W14 bus bar for SI_11B01 (MesUrtOutInv). >SI_11W13 bus bar have one cable (11P1700_032B) / should have 2 feedback cable. >SI_11W14 bus bar have two cable (11P1700_031B and 11P1700_031C) / should have one feedback cable only. | install correctly by referring to AKD0001916304_K schematic | NCR closed | NCR to be closed officially in quality portal refering to the corrective actions taken and the parts replaced.
202239 | 2021-08-23 | All | PACIS | C-TCU card offline in TCN | STE - VBN | Major Restriction | automatic software installation should have been preferred instead of manual installation | SW to be reinstalled (14 units done – topic closed for now): | NCR closed
203806 | 2021-05-19 | All | PACIS | M-SWD working loss comm | STE - VBN | Minor Restriction | Analysis to start, problem with PST alstom tool. | Use only the software update tool provided by STE | NCR closed
203809 | 2021-09-07 | All | PACIS | Q-DaisyChain | STE - VBN | Train OK for mainline | HW issue | Send to STE for repair | NCR closed
203810 | 2021-09-07 | All | PACIS | R-LCD (LID) working loss com | STE - VBN | Train OK for mainline | Analysis to start, problem with PST alstom tool. | Use only the software update tool provided by STE | NCR closed
220211 | 2022-01-05 | 603, 601 | Brakes | Air leakage is observed from the spring brake part. | FT | Minor Restriction | To be investigated with supplier Faiveley | Need to replace the Brake Unit With Parking Brake | NCR opened | Supplier to provide the investigation report with the rootcause and corrective actions

## Version History (hidden)
Version History
Version | Description of change | Date correction applied

## REX - Copy (hidden)
2021-10-18
Rex No | Date raised | Origin of Rex | Sub-system | Description of issue | Responsibility | Potential Impact | Root cause | Action required | Target Date | Status | Comments/Progress
REX002 | 2021-08-23 | Dubai | Smoke detector | Heater fault in smoke detector | TBC | Train OK for mainline | A heater device is included to these detectors to remove humidity from smoke chamber to avoid dust to stick on humidity and avoid false alarm. Heater device switch on & off temperature was identical (45°C). On Dubai Metro if HVAC was off, temperature reach 45°C and remain stable. Software request heater to switch on & off several time in a short period. Heater was not able to follow this order and declare itself as faulty and ask for reset | 1) Fault log to be shared with the supplier to confirm we have the same issues as Dubai. If confirmed supplier will release new SW-->Done 2) 4Tools to be ordered for the SW upgrade 3) Cleaning of smoke detectors to be added to monthly preventive maintenance |  | Correction under implementation | Software to be updated for the Smoke detector, Waiting for the tool to upload. These tools are not available in the market.
REX003 | 2021-08-23 | Dubai | HVAC | False alarm issue | FT | Minor Restriction | All detectors have heavy dust accumulation on external cover. Dust comes off detectors cover and go through smoke chamber. This amount of particles is not consider as dust due to software behavior (accumulation is a long process and don’t consider huge increase of dust). Opacity of light beam detector is increasing and after validation time a fire alarm is trigger. This analysis confirm supplier analysis and Alstom expectation. | Cleaning of smoke detectors to be added to monthly preventive maintenance instead of every 6 months according to care taking plan |  | To be further monitored | Cleaning of smoke detectors is added to monthly preventive maintenance
REX004 | 2021-07-27 | Dubai | CVS | Neutral inductor burnt in 7 trains (5 Revenue trains) due to new APS sw 1.4.14. RCA is known and it is due to new sw and the sw was reverted as instructed by CRL. New sw version 1.5.0 released and under test trials on 5 trains. So far no issue observed. | CRL | Train NOT OK for mainline | Under analysis at Supplier (BLOCK) and in Dubai by CRL team. RCA report expected by 09-Sep Preliminary results show issue due to quality issue of potting in the material and core over-temperature | 1) Full fleet inspection to be done 2) Implemented software modification to be discussed with CRL. Are we at risk? | 2021-09-30 | To be further monitored | 138 of 138 CVS have been verified, no burn marks have been observed
REX006 | 2021-08-22 | Dubai | Bogie | Screws missing or untightened on axle boxes | LCR | Train NOT OK for mainline | Rootcause under investigation: 1) Screws have been tightened in Le Creusot factory, using automatic control torque wrenches. =>> Tightening curve and mounting procedure under analysis 2) Map of the damage under investigation 3) SKF, who designed and delivered the axlebox, is deeply involved. | Visual inspection of the fleet : check if screws are not missing and if the torque mark is not cutted and retorque if required. |  | To be further monitored | Inspection done on complete fleet, 34% of bolts had to be retorqued. Need further investigation on the rootcause of this issue. New full fleet inspection is required in 3 months.
REX008 | 2021-08-23 | Dubai | Bogie | Oil leakage detected on gearbox door inspection | LCR | Train OK for mainline | 1) Wrong flatness of the covers 2) Gasket (loctite 518) not properly applied | Visual inspection of the fleet . If leakage is found a replacement of the gasket is required |  | To be further monitored | Inspection completed on full fleet, 9 out of 552 have leakage. Gaskets to be changed during the 30K Kilometers gearbox overhaul
REX010 | 2021-08-15 | Dubai | CVS&Traction | APS – AGATE Failures - Supplier: AT Charleroi / AT VBN 8D#202543: Agates in CVS (DTR2000002771) failing in fleet with U12V error code. | CRL | Train NOT OK for mainline | Issue is with the DC/DC converter “PMD50” bought directly from MTM (VBN’s supplier – Design authority is CRL) mounted on the Agates. There is an identified problem with the failure of converter which leads to the false detection of internal over-temperature which shuts down the converter permanently. As the Agate does have the power supply from the converter, it cannot operate and therefore declared as an Agate failure. The DC converter is not designed to withstand the temperature inside CVS. | Retrofit the full fleet with new PMD60 converters which are validated and proven design eliminating the failure of false detection in internal over-temperature. Due to time constraints of the project, it is decided to replace all Agates with new Agates manufactured with PMD60 and perform the retrofit of existing stock in parallel. |  | Under Investigation | 1)CRL to check the concerned qty of this issue related to Riyadh. 2) PMD50 agates to be sent back to CRL once the action plan is in place (issue with only 1 of 2 suppliers) - Serial numbers of Agates (276 of 276 ) have been collected
REX011 | 2021-08-15 | Dubai | CVS&Traction | APS – AGATE Failures - Supplier: AT Charleroi / AT VBN 8D#202542 : Agates in CVS (DTR2000002771) and Traction (DTR2000000075) have premature failures in fleet | CRL | Train NOT OK for mainline | Failure occurred due to Resistances R1156-R1281 mounted in the Agate failed prematurely. Issue observed mainly during the first few kms run by each train. Fleet wide retrofit launched by AT VBN and CRL. Retrofit halted mid way and planned to be done along with U12V error issue. | Retrofit full fleet for resistance R1156-R1281. Meanwhile to mitigate failure, additional spares stock provided. |  | Correction under implementation | 1) Retrofit and test 58% (116 pcs out of 200) of line L4 & L6 completed. L5 still not started. 2)Retrofit is stopped due to lack of varnish, delivery ongoing 3)Procurement to be done for the other chemical ULS.
REX012 | 2021-08-23 | Dubai | E Cubicles | 8D# 213977 : Increase of STPI Relay Failures H600 - DTR00267348HE mounted inside Electrical cubicles | CRL | Major Restriction | The problems on relays are located in its control coil. This problem has been encountered in the past, and the conclusion was due to it’s manufacturing problem. Report awaited from Supplier. | Full fleet replacement of H600 Relays is required |  | Under Investigation | Charaf to identify the critical relays to be replaced
REX014 | 2021-09-27 | Dubai | CVS | APS – Power modules: Train specific issues. Power module fails , CVS went to degarded mode | CRL | To be updated once have more details | Details not available | Dubai waiting for investigation report from CRL |  | Investigation Not Started | Request dubai again to share the details
REX015 | 2021-09-27 | Dubai | Traction | Traction – IES Limit switch: Dust accumulation inside the IES switch panel leading to failure of limit switch. Panel is IP40 rating and isn’t preventing dust ingress inside panel. Corrective action plan under discussion. | CRL | Train NOT OK for mainline | Dust accumulation inside the IES switch panel leading to failure of limit switch. Panel is IP40 rating and isn’t preventing dust ingress inside panel. | Full fleet inspection to be done |  | Investigation Not Started | Inspection will start on 5th Dec 2021
REX018 | 2021-11-16 | Dubai | Doors | Movement with door opened | KTW | Train NOT OK for mainline | The analysis has demonstrated that the fault has been the consequence of an event which is external to the design and which although being alarmed to the operator, the operator did not respond to it. | Although the door assembly is compliant to standard and industry practice, in the spirit of collaboration and for customer satisfaction, Alstom will propose to insulate the affected switches in the SIL4 loop by the use of insulated covers for the terminals. Picture below is for sole illustrative purpose and proper change process will be followed. |  | Investigation Not Started | Improvement proposal to be done on 1 door train by Taha by 10th Dec 2021.
REX019 | 2021-08-31 | Dubai | Doors | Unexpected unlocking of train door | KTW | Train NOT OK for mainline | Due to locking nut creating inconsistancy in closing of doors, locking switch triggered in advance leading to inconsistancy between LHS & RHS of door leaf. | Corrective action has three steps: 1. Door locking nut inspection - completed on full fleet. 2. S1 switch adjustment - completed on full fleet. 3. Door unlocking force measurement - to be initiated in fleet based on the acceptance criteria to be defined by KN. 6 projects identified to be impacted with this issue and REX shared to each project site for their internal validation and retrofit. |  | Investigation Not Started | Inspection to start on 12th Dec 2021
REX020 | 2021-10-21 | Dubai | Brakes | Air Reservoir Tank fixation issue 8D#223232. Fixation bands found loosen with potential transversal misplacement of the tank | FT | Train NOT OK for mainline | RCA ongoing | Steps to follow & check: 1. RE-TIGHTEN SCREWS AND APPLY TORQUE 25 Nm. 2. MEASURE CURRENT DISTANCE FROM AIRTANK TO CONNECTION PIPE (DIMENSION 210±2 mm). 3. MARK 10 mm INDICATION ON ALL PIPES CONNECTED DIRECTLY TO THE TANKS (USE PERMANENT MARKER) FOR MONITORING. |  | Investigation Not Started | Inspection to be planned for the torque mark and retorquening

## NCR - copy (hidden)
2021-10-18
NCR No | Date raised | Train Impacted | Sub-system | Description of issue | Responsibility | Impact | Root cause | Correction required | Status | Comments/Progress/Evidence
192711 | 2021-05-19 | All | PACIS | I-NVR mask camera | STE - VBN | Low | SW issue | Correction to be implemented in STR571 | Open | 22-Dec-2021: Correction will be implemented in STR 5.7.2 (to be confirmed) 18/11/21 : Correction implemented in STR571 : tests to be done in dynamic mode @Charaf to check when the tests can be performed.
220211 | 2022-01-05 | 603, 601 | Brakes | Air leakage is observed from the spring brake part. | FT | Low | To be investigated with supplier Faiveley | Need to replace the Brake Unit With Parking Brake | Open | Supplier to provide the investigation report with the rootcause and corrective actions
NCR0225 | 2021-03-02 | 606 | Windows | Damaged train wipers | Alstom | Low | The horizontal brush of Auto wash plant was touching the train wiper during four cars washing. | 1)The Supplier has to modify the software of the vehicle washing machine (the software version of CPU I is #V112--> Done). 2) Replace the broken wipers | Open | 1) the software version of CPU Installed is #V112--> Done 2)Wipers need to be replaced --Target 29-Dec-2021
NCR0226 | 2021-03-02 | 604 | Windows | Damaged train wipers | Alstom | Low | The horizontal brush of Auto wash plant was touching the train wiper during four cars washing. | 1)The Supplier has to modify the software of the vehicle washing machine (the software version of CPU I is #V112--> Done). 2) Replace the broken wipers | Open | 1) the software version of CPU Installed is #V112--> Done 2)Wipers need to be replaced --Target 29-Dec-2021
NCR0227 | 2021-03-02 | 416 | Windows | Damaged train wipers | Alstom | Low | The horizontal brush of Auto wash plant was touching the train wiper during four cars washing. | 1)The Supplier has to modify the software of the vehicle washing machine (the software version of CPU I is #V112--> Done). 2) Replace the broken wipers | Open | 1) the software version of CPU Installed is #V112--> Done 2)Wipers need to be replaced --Target 29-Dec-2021
NCR0341 | 2021-11-21 | 421 | HVAC | HVAC fault. | FT | Low | emergency ventilation fault | HVAC will be checked by local supplier support and corrections will be managed through CM report. | Open | issue is closed, CM report to be issued
NCR0342 | 2021-11-23 | 406 | PACIS | PEI lost communication | STE - VBN | Medium | PEI failure, STE to investigate | PEI to be replaced | Open | parts available , to be fixed by CM
NCR0348 | 2021-11-30 | 512 | HVAC | HVAC compressor and ventilation fault | FT | High | Need further investigation, to be checked by local supplier.. | Need further investigation and to be closed this issue through corrective maintenance reportt | Open | Under investigation by supplier
NCR0352 | 2020-10-10 | 418 | Doors | Passenger door glass cracked | Alstom | Low | Unknow reason,old issue. | Analyze if this can be eradicate by a chemical adhesive without replacement of windows. If issue can not be fixed, replace the window glass. | Open | Requested sourcing the glass fixing gel , waiting for the delivery
NCR0353 | 2020-06-25 | 624 | Doors | Scratches on T624 HC1 Door glass | Alstom | Low | Unknow reason,old issue. | Repair if minor scratch, replace if scratches are too deep. | Open | Issue is closed , CM report to be issued
NCR0358 | 2021-02-21 | 411 | Coupler | Electrical coupler frame broken | KTW | Medium | Improper uncoupling | Coupler frame to be replaced | Open | No material available, ordered through SAP ( informed to kTW)
NCR0360 | 2021-12-07 | 502 | Sanding | Sanding rubber hoses and clams missing | KTW | Low | Reason unknown | Need to fix with new part rubber hoses with clamps | Open | Supplier missed the hoses while delivering, pending
NCR0361 | 2021-12-07 | 603 | DCS | Beacon Antenna screws missing | KTW | Low | Not installed due to out of stock (root cause unknown) | To be fixed with new screws | Open | No material available, ordered through SAP ( informed to kTW)
NCR0362 | 2021-12-08 | 603 | Sanding | Left side sanding hose not availabe | KTW | Low | unknown reason | Need to fix with new part rubber hose with clamps | Open | Supplier missed the hoses while delivering, pending
NCR0372 | 2021-12-08 | 606 | Carbody | Gap filler between HVAC and Gangway missing | KTW | Low | Missing, reason unknown | Need to fix with the new Gap filler | Open | Material not available, SAP NCR is requested to KTW
NCR0375 | 2021-12-12 | 601 | Compressors | AGTU_Missing of Sand filter Assembly | FT | Low | Missing.Root cause unknown | Need to normalize by adding the missing part. | Open
NCR0376 | 2021-12-12 | 601 | Brakes | leakage found from the spring brake part. | FT | Low | To be investigated with supplier Faiveley | Need to replace the BRAKE UNIT of PARKING BRAKE | Open | To be sent to supplier FT ( India) for investigation and repair. Supplier to provide the investigation report with the rootcause and corrective actions
NCR0377 | 2021-12-12 | 610 | Lighting | Head and Tail Light white LED not working | KTW | Low | Reason unknown | Need to replace and send to supplier for repairing | Open | only 1 led light not working out of 23, no need to change it now, kept on Hold
NCR0378 | 2021-12-12 | 617 | Lighting | Head and Tail Light white LED not working | KTW | Low | Reason unknown | Need to replace and send to supplier for repairing | Open | only 1 led light not working out of 23, no need to change it now, kept on Hold
NCR0381 | 2021-12-12 | 601 | PACIS | LCD & EDI error display | STE - VBN | Low | Component failure | Replace LCD,LEDI | Open | Material available, to be fixed by CM
NCR0382 | 2021-12-13 | 611 | Bogie | Axle Gearbox leakage | Le Creusot | Low | Leakage found from inspection cover | Need to replace the Gasket/Sealant RTV | Open | Waiting for material (in transit)
NCR0383 | 2021-12-13 | 611 | Lighting | Head and Tail Light LED not working | KTW | Low | Unknown, LED light failure | Need to replace and send the defective part to supplier for repairing | Open | To be sent to supplier for repair
NCR0387 | 2021-12-14 | 626 | PACIS | LCD poor display issue | STE - VBN | Low | Component failure | Replace LCD | Open | Material available, to be fixed by CM
NCR0389 | 2021-12-14 | 507 | Interior | Under seat fire extinguisher BOX not available | Alstom | Low | No stock available | Need to install new | Open | To procure and install
NCR0393 | 2021-12-15 | 612 | PACIS | LCD display issues | STE - VBN | Low | Component failure | Replace L CDs | Open | Material available, to be fixed by CM
NCR0394 | 2021-12-15 | 422 | Doors | Door glass cracked | Alstom | Low | Reason unknown, To be investigated | Analyze if this can be eradicate by a chemical adhesive without replacement of windows. If issue can not be fixed, replace the window glass. | Open | Requested sourcing the glass fixing gel , waiting for the delivery
NCR0395 | 2021-12-15 | 601 | Lighting | Saloon Light not working | KTW | Low | Unknow reason | Need to install new | Open | Part available, will be fixed by CM team
NCR0401 | 2021-12-16 | 416 | PACIS | LCD display issues | STE - VBN | Low | LCD failure | Replace LCD | Open | Material available, to be fixed by CM
NCR0403 | 2021-12-19 | 603 | Brakes | Air leakage found from the spring brake part. | FT | Low | Unknown. To be investigated by supplier FT | Need to replace the Brake Unit With Parking Brake | Open | Supplier to provide the investigation report with the rootcause and corrective actions
NCR0405 | 2021-12-19 | 404 | Electrical wiring | HV cable gland missing from the underframe Junction Box | KTW | Low | Part missing, root cause not known | Need to order the part and installed. | Open | Material availability to be checked by CM
NCR0406 | 2021-12-19 | 623 | Traction | stinger cap cover broken | CRL | Low | During the plugging 750v in workshop stinger cap cover broken | Need to install new cap | Open | Material availability to be checked by CM
NCR0408 | 2021-12-19 | 606 | Interior | Gangway Gap filler damaged | KTW | Low | Was not installed properly | Need to install new gap filler | Open | Material not available, SAP NCR is requested to KTW
NCR0414 | 2021-12-20 | 415 | Coupler | Earthing cable is not connected between permanent coupler | KTW | Low | Missing , no stock available | Need to procure and install new earthig cables | Open | Material not available, SAP NCR is requested to KTW
NCR0417 | 2021-12-20 | 618 | Coupler | Earthing cable is not connected between permanent coupler | KTW | Low | Part missing, reason unknown | Need to procure and install new earthig cables | Open | Material not available, SAP NCR is requested to KTW
NCR0418 | 2021-12-20 | 622 | Coupler | Earthing cable is not connected between permanent coupler | KTW | Low | Missing , no stock available | Need to procure and install new earthig cables | Open | Material not available, SAP NCR is requested to KTW
NCR0420 | 2021-12-21 | 403 | Bogie | Axle Gearbox leakage | Le Creusot | Low | Leakage found from inspection cover | Need to replace the Gasket/Sealant RTV | Open | Waiting for material (in transit)
NCR0422 | 2021-12-21 | 512 | Lighting | Head and Tail Light white LED not working | KTW | Low | One LED not working | Need to Replace and send to supplier for repair | Open | To be sent for repair
NCR0427 | 2021-12-23 | 413 | Bogie | Stick holding safety pin missing. | Le Creusot | Low | Missing, part not available. | Normalize by adding new safety pin(R-CLIP DOUBLE) | Open
NCR0428 | 2021-12-23 | 410 | PACIS | LCD dim display issue | STE - VBN | Low | LCD2-V2 component failure. | Replace LCD | Open
NCR0429 | 2021-12-23 | 503 | Shoe Collector | Fuse box glass cracked. | Le Creusot | Low | Checked and no possibility cracked cause by hit, behind the fuse cover we have two glass holding bracket. The only cause were by bad installation process. Bolt for the glass clamp were too tight. | Replace the Fuse box triplex glass. Spare need to be ordered. | Open
NCR0430 | 2021-12-26 | 501 | Doors | DOOR indication light not working | KTW | Low | Reason unknown | Need to install new indicator | Open
NCR0431 | 2021-12-26 | 515 | Shoe Collector | Fuse box glass cracked. | Le Creusot | Low | Unknown (visually like broken by a shock) | Replace the Fuse box triplex glass. Spare need to be ordered. | Open
NCR0432 | 2021-12-27 | 508 | SLV-ATC | STF-DL beacon Antenna : HC1 1 bolt ,HC2 2 bolt not available | Alstom | Low | Missing, reason unknown | Normalize by putting new bolt | Open
NCR0433 | 2021-12-28 | 515 | Bogie | Stick holding safety pin missing | Le Creusot | Low | Missing, reason unknown | Normalize by adding new safety pin(R-CLIP DOUBLE) | Open
NCR0436 | 2022-01-02 | 507 | Shoe Collector | HV cable support clamp missing | Le Creusot | Low | Accident train, part missing | Need to fix with spare parts | Open
NCR0437 | 2022-01-02 | 504 | Gangway | Gangway Panel has scractch &Lock missing | KTW | Low | Retrofit work not done and if compared the lock type, this lock type were old type. | Need to finish the retofit work and re-painting. | Open
NCR0438 | 2022-01-02 | 501 | Derailment sensor | Derailment sensor cable clamp missing | KTW | Low | Part missing, reason unknown | Order and Install with spare part | Open
NCR0439 | 2022-01-03 | 410 | Gangway | ONE INTERNAL Gangway COVER MISSING | KTW | Low | Reason unknown | Instal the gangway cover | Open
NCR0440 | 2022-01-03 | 625 | PACIS | SWD3-V1 half display issue | STE - VBN | Low | SWD3-V1 component failure (suspect card failure) | To replace SWD | Open
NCR0441 | 2022-01-03 | 601 | Gangway | Gangways panels are not able to be closed | KTW | Low | Reason unknown | Need to install new panel | Open
NCR0442 | 2022-01-04 | 502 | Bogie | Found minor leakage from the gearbox drain plug cause by O-ring defect. | Le Creusot | Low | O-ring attached to drain pulg defective | O ring need to change and tightened accordingly. | Open
NCR0443 | 2022-01-05 | 407 | Bogie | Found minor leakage from the gearbox inspection cover | Le Creusot | Low | Inspection cover mole have issue | Inspection cover to be sent to supplier for repair work. | Open
NCR0444 | 2022-01-05 | 412 | Gangway | Gangways panels are missing | KTW | Low | Reason unknown | Need to install new gangway covers | Open
NCR0445 | 2022-01-05 | 410 | Gangway | Gangways panel is missing | KTW | Low | Reason unknown | Need to install new gangway cover | Open
NCR0446 | 2022-01-05 | 609 | Gangway | Gangway locks missing | KTW | Low | Reason unknown | Need to fix the side panel locks | Open
NCR0449 | 2022-01-09 | 607 | Bogie | Gearbox oil axle 3 is contaminated. | Le Creusot | Low | Need laboratory report and root cause need to be defined. | For further checking activities we received laboratory report. | Open
NCR0450 | 2022-01-09 | 607 | Bogie | Gear box oil level is below minimum level | Le Creusot | Low | Gearbox oil were not fully fill when train were in factory. | Need to topup the gearbox oil. | Open
NCR0452 | 2022-01-10 | 422 | PACIS | LEDI1-V2 offline and dark | STE - VBN | Low | LEDI1-V2 component faillure | Replace LEDI | Open
NCR0453 | 2022-01-10 | 611 | Battery | Battery Door tubular seal some damaged | Hoppecke | Low | Battery Door tubular seal damaged, Wrong handling of the door opening | Replace Rubber | Open
NCR0454 | 2022-01-10 | 611 | Battery | Battery Door External safety label damaged | Hoppecke | Low | Label damaged during handling | Replace label | Open
NCR1002 | 2022-01-11 | 409 | CVS | IOS185 : 1 APC LV Status false, IOS179 : 1 APC MV Status false | CRL | High | Root cause still not define but we need a CVS converter to perform a test. | To be confirmed | Open
NCR1038 | 2022-01-24 | 415 | Interior | HC1 ROOF PANEL1 ALLEN SREW 1MISSING AND 1DAMAGE HC2 ROOF PANEL1 ALLEN SREW1DAMAGE | CRL | Low | Due to not alignment properly and put by force the screw. | Need to install new nut and screw | Open
NCR1044 | 2022-01-24 | 402 | Interior | HC1 ROOF PANEL1 ALLEN SREW 1MISSING AND 1DAMAGE HC2 ROOF PANEL1 ALLEN 2 SREW1DAMAGE. | CRL | Low | Due to not alignment properly and put by force the screw. | Need to install new nut and screw | Open
NCR1056 | 2022-01-10 | 404 | Bogie | Gearbox 1&2 oil level below minimum but no leakage issue observed. | CRL | High | Oli not fully inserted since from factory. | Need to topup gear box oil. | Open
NCR1073 | 2022-01-18 | 603 | Gangway | GANGWAY INTERNAL PANELS IS MISSING | KTW | Low | Unknown | Need to install new | Open
NCR1076 | 2022-01-24 | 609 | Interior | HC1 ROOF PANEL1 ALLEN SREW 1MISSING AND 1DAMAGE HC2 ROOF PANEL1 ALLEN 2 SREW1DAMAGE. | KTW | Low | Due to not alignment properly and put by force the screw. | Need to install new nut and screw | Open
NCR1087 | 2022-01-19 | 502 | Gangway | Gangway locks missing | KTW | Low | Unknown | Need to install new | Open
NCR1088 | 2022-01-19 | 512 | Gangway | Gangway locks missing | KTW | Low | Unknown | Need to install new | Open
NCR1092 | 2022-01-18 | 602 | Bogie | The 750 HV cable from the Fuse box to the Junction box was damaged during a sweep run on the mainline | Alstom | Low | Incident in the mainline | Need to install new | Open
NCR1098 | 2022-01-18 | 408 | Gangway | GANGWAY INTERNAL PANELS IS MISSING | KTW | Low | Unknown | Need to install new | Open
NCR1099 | 2022-01-10 | 611 | Battery | HC1, Battery Door tubular seal some damaged | KTW | Low | HC2 ROOF PANEL1 ALLEN 2 SREW1DAMAGE. | Replace rubber | Open
NCR1109 | 2022-01-18 | 402 | Gangway | Gangway locks missing | KTW | Low | Unknown | Need to install new | Open
NCR1111 | 2022-01-17 | 415 | Doors | DCU Faulty No Communication | KN | Low | Unknown | Need to install new DCU | Open
NCR1130 | 2022-01-17 | 615 | Coupler | Semi permanent coupler grounding bolt missing | KN | Low | Not in stock, need to request the new material | Need to install new | Open
NCR1150 | 2022-01-13 | 414 | Interior | Partition door lock missing | KTW | Low | Unknown | Need to install new | Open
NCR1152 | 2022-01-24 | 404 | Interior | HC1 ROOF PANEL1 ALLEN SREW 1MISSING AND 1DAMAGE HC2 ROOF PANEL1 ALLEN 2 SREW1DAMAGE.Partition door lock missing | KTW | Low | Due to not alignment properly and put by force the screw. | Need to install new nut and screw | Open
NCR1154 | 2022-01-17 | 403 | LV | Unconnected Grounding cable in the LV Box | KTW | Low | Unknown | Need to install new | Open
NCR1168 | 2022-01-19 | 615 | HVAC | HVAC -Venting error in MONA software but physically we cheched its was working | FT | Low | Unknown | Need to checked with supplier | Open
NCR1194 | 2022-01-24 | 626 | CVS | 52Q11 and 11Q02 was tripping (short circuit in AA3S) | CRL | Low | Unknown | Need to install new AA3S | Open