## Train status
2022-08-25
Open Date | Doc Ref | CM Ref | TRAIN | Description | IMPACT | Progress
2021-09-20 | TIR0019 |  | 418 | HC1 Door1 glass found minor cracked | Low
2021-09-21 | TIR0027 |  | 422 | HC1 Door-6 glass cracked | Low
2021-09-26 | TIR0036 |  | 601 | HC2- Saloon lights NOK | Low
2021-11-21 | TIR0102 |  | 421 | ventilation fault HVAC2-V2 | Low
2021-12-06 | TIR0148 |  | 608 | 1.HVAC-Roof Panel gap filler plate not fixed(near to Gangway) | Low
2021-12-06 | TIR0158 |  | 411 | HC1- Electrical Coupler NOK. ( Required Fasteners ). | Low
2021-12-06 | TIR0163 |  | 623 | T623_HC2_RHS_ Sanding rubber hoses damaged - 1 nos. (DTR0000550155) | Low
2021-12-07 | TIR0170 |  | 411 | coupler without electrical coupler cover | Low
2021-12-08 | TIR0175 |  | 415 | Earthing cable is not connected between permanent coupler | Low
2021-12-08 | TIR0182 |  | 606 | Gangway light mounting nok,there is a gap | Low
2021-12-09 | TIR0202 |  | 601 | T601_HC2- missing of sand filter assembly | Low
2021-12-09 | TIR0209 |  | 618 | Semi permanent coupler earthing bolt is missing,and Earth strip is lose both sides. | Low
2021-12-09 | TIR0210 |  | 622 | Semi permanent coupler earthing bolt is missing. | Low
2021-12-12 | TIR0214 |  | 404 | HC1 Bogie1- One HV cable gland missing from the underframe JB. | Low
2021-12-14 | TIR0234 |  | 413 | HC1-BOGIE 2 RIGHT HAND SIDE (WFL)WHEEL FLANGE LUBRICATOR STICK HOLDING SAFETY PIN MISSING | Low
2021-12-15 | TIR1032 |  | 414 | HC2: WFL (Wheel flange Lubricator) SAFETY PIN IS MISSING( 2 NOS) | Low
2021-12-20 | TIR1036 |  | 609 | HC2 PANEL NO1 ALLEN SCREW MISSING. HC2 NEAR DOOR2 SEALING PANEL ALLEN SCREW MISSING. HC1&HC2NEAR TO GANGWAY PANEL ALLEN SCREWS ARE MISSING. | Low
2021-12-20 | TIR1037 |  | 609 | Gangway 2 Locks are missing. | Low
2021-12-21 | TIR1038 |  | 415 | HC1 ROOF PANEL1 ALLEN SREW 1MISSING AND 1DAMAGE HC2 ROOF PANEL1 ALLEN SREW1DAMAGE. | Low
2021-12-21 | TIR1040 |  | 605 | hc2 sanding reservoir for re-filling (empty) | Low
2021-12-26 | TIR1044 |  | 402 | HC1 Panel 1 allenkey screw missing | Low
2021-12-28 | TIR0302 |  | 620 | ONE INTERNAL GANG COVER MISSING | Low
2021-12-28 | TIR0313 |  | 601 | gangways panels are not able to closed | Low
2021-12-29 | TIR1062 |  | 619 | HC2-CCC rubber missing. | Low
2021-12-30 | TIR0343 |  | 410 | gangway internal cover is missing | Low
2021-12-30 | TIR1066 |  | 421 | CAR2 HVAC1,HVAC2,DF 1005_EXFL,DF 1006_EMEXF, EXHAUST AIR FAN LOW, EXHAUST AIR FAN HIGH. | Low
2022-01-02 | TIR0349 |  | 412 | GANGWAY INTERNAL PANELS ARE MISSING | Low
2022-01-02 | TIR1072 |  | 603 | hc2 left sanding hose missing | Low
2022-01-02 | TIR1073 |  | 603 | GANGWAY INTERNAL cover missing hc1 right | Low
2022-01-02 | TIR1076 |  | 609 | HC2 PANEL NO1 ALLEN SCREW MISSING. HC2 NEAR DOOR2 SEALING PANEL ALLEN SCREW MISSING. HC1&HC2NEAR TO GANGWAY PANEL ALLEN SCREWS ARE MISSING | Low
2022-01-03 | TIR0375 |  | 609 | Gangway locks missing | Low
2022-01-03 | TIR1086 |  | 621 | Torque mark damage in bolts of half coupler(gear box and motor) HC1-Axle4- | Low
2022-01-04 | TIR1090 |  | 618 | HC1 & HC2 Both side mechanical coupler got stuck while uncoupling of the train | Low
2022-01-04 | TIR1097 |  | 617 | HC2 Ceiling panel cover not fixed ( support bracket missing ) | Low
2022-01-04 | TIR1098 |  | 408 | Issue Detected Train 408: Broken side panel sheet gangway. | Low
2022-01-04 | TIR1099 |  | 611 | Detected during Battery Visual Inspection Trainset 611A - Door tubular seal was found having some damaged. | Low
2022-01-05 | TIR1109 |  | 402 | Gangway cover one lock is broken | Low
2022-01-09 | TIR1130 |  | 615 | semi permanent coupler grounding bolt missing | Low
2022-01-13 | TIR1150 |  | 414 | Partition door lock missing | Low
2022-01-16 | TIR1152 |  | 404 | HC1 PANEL 1- 1 ALLEN SCREW MISSING HC2 PANEL1 - 1 ALLEN SCREW MISSING | Low
2022-01-17 | TIR1163 |  | 422 | hc1-hc2 sandng reservoir for re-filling, almost empty | Low
2022-01-18 | TIR1177 |  | 403 | sand level is low | Low
2022-02-01 | TIR1206 |  | 608 | HC-2, CVS - Cover panel, one lock is missing | Low
2022-02-01 | TIR1212 |  | 416 | HC1 AXLE4 LHS primary suspension dummy caps (bottom part ) are missing HC2 AXLE1 RHS and AXLE4 LHS primary suspension dummy caps (bottom part ) are missing | Low
2022-02-01 | TIR1213 |  | 416 | HC1 Bogie 2 Horizontal damper doesnt have torque marks on its bolts on one end ( two bolts );ALL ECR(earth current return ) cables are without proper torque marks on them (HC1 +HC2) all axle box outer covers are without proper legible torque marks on them (marks are mostly faded are not good) | Low
2022-02-06 | TIR1225 |  | 610 | Semi permament coupler earth strip missing one bolt | Low
2022-02-06 | TIR1226 |  | 618 | HC-02, A-matric exhaust filter Bottom side - bolt missing and HC-01, Auxillary panel lock is missing | Low
2022-02-06 | TIR1227 |  | 414 | No proper (legible ) torque marks on the axle box outer covers (all the axles )-all marks are faded;none of the ECR(EARTH CURRENT RETURN ) cables have proper torque marks on them | Low
2022-02-07 | TIR1233 |  | 408 | ONE GANGWAY PANEL DOOR IS MISSING | Low
2022-02-07 | TIR1235 |  | 404 | No proper (legible ) torque marks on the axle box outer covers (all the axles )-all marks are faded | Low
2022-02-07 | TIR1240 |  | 617 | HC1 windscreen glass broken | High
2022-02-08 | TIR1244 |  | 611 | semi-permanent coupler grounding bolt missing | Low
2022-02-15 | TIR1290 |  | 607 | Momvement on torque marking bolt connection for automatic coupler assembly | Low
2022-02-23 | TIR1335 |  | 613 | Both Gangway door panels are Not available | Low
2022-02-23 | TIR1336 |  | 613 | HC1 CVS gasket (surrounding the AGATE panel )came out condition | Low
2022-02-23 | TIR1343 |  | 410 | HC2, BOGIE-1, Right side, CCD HV cable no clamp for return line | Low
2022-02-24 | TIR1353 |  | 605 | Issue Detected in Train 605A & 605B: Missing/ Damage External Safety labels for Battery Box (see photo attached) | Low
2022-02-24 | TIR1356 |  | 406 | Issue Detected in Train 406: Automatic Coupler assembly bolt connection was having signs of movement on torque markings @ Train 406B. (see photo attached) | Low
2022-02-24 | TIR1357 |  | 607 | Issue Detected in Train 607: Automatic Coupler assembly bolt connection was having signs of movement on torque markings @ Train 607B. (see photo attached) | Low
2022-02-24 | TIR1358 |  | 406 | ssue Detected in Train 406 & 614: Torque marking were no longer visible (fully covered with dust/dirt) to serve its purpose for easy identification for any loose bolt connection. This condition was observed in many trains. (see photo attached) | Low
2022-02-24 | TIR1359 |  | 614 | ssue Detected in Train 406 & 614: Torque marking were no longer visible (fully covered with dust/dirt) to serve its purpose for easy identification for any loose bolt connection. This condition was observed in many trains. (see photo attached) | Low
2022-02-24 | TIR1364 |  | 409 | HC1: LV box-battery connector hinge is missing | Low
2022-02-24 | TIR1369 |  | 619 | HC2, Electrical coupler isolate cock is missing (handle). | Low
2022-02-27 | TIR1381 |  | 407 | PEED Reset from CC not working for all EED in the train (HC1-HC2 Both side) | Low
2022-03-06 | TIR1392 |  | 404 | HC2 axle 2 oil leakage | Low
2022-03-17 | TIR1436 |  | 401 | HC2_ROM - Missing of Male connector for 72W03+ROM_XP_ETH1 of Openbat-F Simple Radio Onboard(DTR0000397019) | Low
2022-03-22 | TIR1459 |  | 621 | CCC Panel -HC1:scratches | Low
2022-03-29 | TIR1503 |  | 411 | HC2 sanding for refilling | Low
2022-03-29 | TIR1505 |  | 412 | HC2 right sanding for refilling | Low
2022-03-29 | TIR1507 |  | 604 | HC-02, Both sand reservior low level | Low
2022-03-29 | TIR1508 |  | 608 | INSIDE TRAIN ONE GANGWAY DOOR NOT AVAILABLE | Low
2022-04-05 | TIR1528 |  | 406 | HC1-Electric coupler spring is missing at one side of the cover | Low
2022-04-06 | TIR1535 |  | 402 | Hc2 Gearbox #4 leakage on door | Low
2022-04-06 | TIR1539 |  | 613 | oil level low and bogie 2 car B, oil color change | Low
2022-04-13 | TIR1594 |  | 604 | missing signs on battery box | Low
2022-04-13 | TIR1595 |  | 610 | FIRE Extinguishers have not been inspected since December 2021 | Low
2022-04-13 | TIR1601 |  | 409 | Horn is not working in HC2 | Low
2022-04-14 | TIR1614 |  | 618 | HC1 right side of head light LED's are not working. | Low
2022-04-14 | TIR1628 |  | 415 | CCC Panel -HC2 MISSING. | Low
2022-04-17 | TIR1639 |  | 613 | oil level low and bogie 2 car B, oil color change | Low
2022-04-18 | TIR1643 |  | 622 | Overfilled gearbox oil HC2 bogie 1 axle 2 | Low
2022-04-18 | TIR1647 |  | 601 | Gearbox Oil leakage HC2 bogie 1 axle 2 | Low
2022-04-19 | TIR1651 |  | 424 | Gangway panel was found missing. | Low
2022-04-19 | TIR1653 |  | 406 | HC-02 BCU matrix - Exhaust filter screw missing | Low
2022-04-26 | TIR1680 |  | 604 | HC2 gearbox door leakage | Low
2022-04-27 | TIR1684 |  | 621 | HC1 AXLE2 RHS ECR cable is damaged-insulation damage at the end of the fixing | Low
2022-04-28 | TIR1689 |  | 603 | EAD not working from Right side HC2 | Low
2022-05-15 | TIR1740 |  | 617 | hvac water drainage distribution box hose damaged during PM simulation | Low
2022-05-16 | TIR1742 |  | 402 | Torqueing to be checked after dismounting the motor for noise test | Low
2022-05-16 | TIR1743 |  | 402 | Seals and motor covers damaged after noise test | Low
2022-05-17 | TIR1750 |  | 602 | Something unknown is restricting the internal gangway panel movement. | Low
2022-05-17 | TIR1751 |  | 611 | The left internal Gangway panel was found missing. | Low
2022-05-17 | TIR1754 |  | 604 | The left internal Gangway panel was found missing. | Low
2022-05-18 | TIR1761 |  | 617 | IOS267 : At least one software version discordancy fault | Low
2022-05-18 | TIR1762 |  | 617 | IOS125 : At least one external smoke sensor is on failure | Low
2022-05-18 | TIR1768 |  | 612 | car2 saloon light off near door2 | Low
2022-05-18 | TIR1769 |  | 405 | car2 horn pushbutton not working | Low
2022-05-23 | TIR1778 |  | 611 | battery warning signages are missing (safety labels) | Low
2022-05-23 | TIR1779 |  | 406 | Safety missing in wheel flange lubricator in hc2 | Low
2022-05-25 | TIR1787 |  | 605 | HC2 HVAC 1 very strange sound is coming from the hvac unit while start up. | Low
2022-05-25 | TIR1788 |  | 420 | HC2 GCL Panel one holding clip missing. | Low
2022-05-25 | TIR1790 |  | 409 | TS409 HC1 LV Earthing Cable is broken | Low
2022-06-02 | TIR1794 |  | 404 | Traction box : Single pole connector (interfaced with a workshop POS stinger) is boken from train side | Low
2022-06-05 | TIR1796 |  | 611 | HC2 HVAC NO2 FAILED IN EXHAUST AIR LOW AND HIGH, CONDENSER FAN lOW AND HIGH | Low
2022-06-05 | TIR1797 |  | 622 | There is abnormal sound coming from HVAC in mC1 while train running through tunnel section. | Low
2022-06-06 | TIR1798 |  | 612 | automatic coupler level, one bolt is not tighten and otrque marquing not visible (see attached picture) | Low
2022-06-06 | TIR1799 |  | 424 | HC2-Left Derailment sensor- one screw Missing | Low
2022-06-09 | TIR1803 |  | 417 | IOS1 : One compressor out of service indication | Low
2022-06-13 | TIR1809 |  | 401 | Left panel safety rope damaged. Right panel safety rope damaged. Right panel damaged because of not closing. | Low
2022-06-13 | TIR1810 |  | 402 | Right Panel safety rope damaged. | Low
2022-06-13 | TIR1811 |  | 403 | Left Panel safety rope damaged. Right Panel safety rope damaged. | Low
2022-06-13 | TIR1812 |  | 404 | Right Panel middle and bottom Square key locks damaged, cannot open the panel. | Low
2022-06-13 | TIR1813 |  | 405 | Gangway left panel door is not available | Low
2022-06-13 | TIR1814 |  | 406 | Left Panel safety rope damaged. Right Panel safety rope damaged. | Low
2022-06-13 | TIR1815 |  | 409 | Left panel square key lock pattern differnt cannot openRight panel middle sqaure key lock cannot close | Low
2022-06-13 | TIR1816 |  | 410 | Right panel middle and bottom Square key locks damaged. | Low
2022-06-13 | TIR1817 |  | 412 | Left Panel safety rope damaged. Right Panel safety rope damaged. | Low
2022-06-13 | TIR1818 |  | 413 | Left Panel middle square key cannot be locked. Right Panel top and bottom Square key locks damaged, cannot open the panel. | Low
2022-06-13 | TIR1819 |  | 417 | on the left side panel -one of the inner black rope is broken on the left side panel -the central lock is unable to close | Low
2022-06-13 | TIR1820 |  | 420 | Left panel lock broken and inside safety rope damage, Also gangway suspension spring out of the wheel | Low
2022-06-13 | TIR1821 |  | 423 | In both sides - gangway inside safety rope broken. | Low
2022-06-13 | TIR1822 |  | 424 | Gangway left panel door is not available Gangway left panel door is not availab | Low
2022-06-13 | TIR1823 |  | 601 | On the left side the locking mechanism plate also missing on left side one of the rope is broken on right side the gangway side wall panel(hold in place with only locks ) is detached from its hinges-no hinges are available to hold the gangway panel on right side gangway -one of the rope is wrongly attached to a corner bolt | Low
2022-06-13 | TIR1824 |  | 602 | Left Panel middle square key cannot be locked | Low
2022-06-13 | TIR1825 |  | 603 | Left Panel middle square key cannot be locked. Left panel safety rope damaged. Right panel safety rope damaged. | Low
2022-06-13 | TIR1826 |  | 604 | gangway left panel was found missing. | Low
2022-06-13 | TIR1827 |  | 605 | Right Panel middle square key cannot be opened, cannot open the panel. | Low
2022-06-13 | TIR1828 |  | 611 | Right panel safety rope is missing. Gangway left found missing | Low
2022-06-13 | TIR1829 |  | 615 | Left Panel middle square key cannot be locked | Low
2022-06-13 | TIR1830 |  | 616 | left side central lock is unable to close left side panel locks -lock indication is reverse position -it is showing open in horizonatl position and closed in vertical position | Low
2022-06-13 | TIR1831 |  | 617 | Right Panel bottom square key lock damaged(rotating). | Low
2022-06-13 | TIR1832 |  | 618 | Left panel one of the safety rope is broken In both the panels the central locks are not able to close -only the top and bottom locks are closed in these two panels | Low
2022-06-13 | TIR1833 |  | 619 | Left panel middle square key cannot be locked Right panel middle squre key lock damaged | Low
2022-06-13 | TIR1834 |  | 622 | Right side panel, lock broken. 2. Also safety rope damage | Low
2022-06-13 | TIR1835 |  | 623 | Right side panel, out of 3 locks, 2 locks are not working properly. | Low
2022-06-13 | TIR1836 |  | 624 | Right panel Red plastic handle missing. | Low
2022-06-13 | TIR1837 |  | 625 | Left panel cannot open Right panel middle square key lock cannot close | Low
2022-06-13 | TIR1838 |  | 626 | Right panel middle square key lock cannot close | Low
2022-06-15 | TIR1843 |  | 407 | siganges of movements of torque marking of hc2 | Low
2022-06-15 | TIR1849 |  | 410 | Many F_DRS_RelCBTrip_2 in the log 45 | Low
2022-06-26 | TIR1862 |  | 617 | CVS1 Major fault | High
2022-06-27 | TIR1863 |  | 617 | A-MATRIC 2 HC1 need to replace (swap with 617 and 625). Communication not established after the wakeup | High
2022-06-27 | TIR1864 |  | 617 | IES module to be replaced PCE_1. | High
2022-06-28 | TIR1868 |  | 604 | The manual partition door locking mechanism is broken | Low
2022-07-06 | TIR1876 |  | 610 | HVAC2 CAR2 Exhaust air fan low and high are failed. | Low
2022-07-19 | TIR1884 |  | 602 | HC2: Bogie2-gearbox 4 has a oil leakage from door | Low
2022-07-20 | TIR1887 |  | 618 | HC-1 ACE 1 Square key lock is missing | Low
2022-07-25 | TIR1891 |  | 611 | HC2: gear box 4 oil is leakage from gearbox door | Low
2022-07-21 | TIR1893 |  | 405 | Pei2/V2 -IP offlineIOS196,203 : Loss of at least 1 PEI in a class | Low
2022-07-31 | TIR1905 |  | 412 | TS412 HC2 Bogie-02 Axle-03 (right), missing clamp. | Low
2022-07-31 | TIR1906 |  | 403 | Light cover inside the train is damaged, second cover, right side HC2. | Low
2022-07-31 | TIR1908 |  | 413 | Saloon light covers inside the train are wrongly positioned. | Low
2022-08-01 | TIR1921 |  | 617 | HC1-LV box front cover removed to installed at HC1 T413, | Low
2022-07-31 | TIR1929 |  | 608 | ACE Cover is with damaged electrical safety stickers | Low
2022-08-04 | TIR1930 |  | 611 | HC2 LV Box Earthing cable found damaged | Low
2022-08-07 | TIR1933 |  | 623 | Broken bolt found in TS623 HC2 Traction Box underframe cover. | Low
2022-08-08 | TIR1934 |  | 404 | Broken bolt found in TS404 HC1 Traction Box Underframe cover. | Low
2022-08-09 | TIR1939 |  | 626 | TS626 HC2 Bogie-01 Current Colector Arm (right) is not properly align. Please see attached photo for your reference | Medium
2022-08-16 | TIR1952 |  | 625 | Corrosion at lifting point on the bogie. Issue observed for all the fleet | Low
2022-08-18 | TIR1956 |  | 424 | Need to wheel profil. Impact observed in some wheels | Low
2022-08-17 | TIR1959 |  | 610 | HC-2 PCE underframe 1 bolt cannot be tightened because of thread not being ok | Low
2022-08-21 | TIR1961 |  | 423 | HC2 - Seat damage. | Low
2022-08-22 | TIR1962 |  | 622 | IOS298:Derailment failure on multiple unit or single unit configuration | Medium
2022-08-22 | TIR1965 |  | 405 | pei1 v2, led3 v1 not working | Low
2022-08-22 | TIR1966 |  | 403 | Train association issues HVAC IOS39/40 | Low
2022-08-22 | TIR1967 |  | 625 | IOS40 and IOS39 , normalized after train sleep-wake-up | Low
2022-08-22 | TIR1968 |  | 602 | IOS39 triggered at transfer track. Could not associate to TT, sent to 6A1. Then 4B1 and 4C1 P1 to associate | Medium
2022-08-23 | TIR1969 |  | 421 | Damaged paint in roof covers HC1 | Low
2022-08-23 | TIR1970 |  | 601 | HVAC 2 V1 communication failed | Low
2022-08-23 | TIR1971 |  | 615 | VAC Auto test failed | Low
2022-08-24 | TIR1972 |  | 413 | IP Offline : papis ctrl2 and pais pa2,UMC autotest failed and UMC2 SW version nok.;IOS251 : One MUC have a communication fault | Low
2022-08-23 | TIR1974 |  | 417 | lcd2-v1 ip offline | Low
2022-08-23 | TIR1975 |  | 619 | papis pa2 ip offline | Low
2022-08-25 | TIR1976 |  | 411 | no CCTV display can seen for any camera | Low
2022-08-25 | TIR1977 |  | 619 | no CCTV display can seen for any camera | Low
2022-08-25 | TIR1978 |  | 601 | IOS250 : One HVAC communication fault. | Low
2022-08-25 | TIR1979 |  | 607 | TS607 HC2 Odometer Cover bolt missing. See attached photo | Low
2022-08-25 | TIR1980 |  | 616 | MC2 water gutter or duct missing. See picture sent in FAMP TSY RST groupe | Low
| RETR0002 | CMR0450 | 401 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0451 | 402 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0452 | 403 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0453 | 404 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0454 | 405 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0455 | 406 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0456 | 407 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0457 | 408 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0458 | 409 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0459 | 410 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0460 | 411 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0461 | 412 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0462 | 413 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0463 | 414 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0464 | 415 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0465 | 416 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0466 | 417 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0467 | 418 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0468 | 419 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0469 | 420 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0470 | 421 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0471 | 422 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0472 | 423 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0473 | 424 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0474 | 601 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0475 | 602 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0476 | 603 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0477 | 604 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0478 | 605 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0479 | 606 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0480 | 607 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0481 | 608 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0482 | 609 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0483 | 610 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0484 | 611 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0485 | 612 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0486 | 613 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0487 | 614 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0488 | 615 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0489 | 616 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0490 | 617 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0491 | 618 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0492 | 619 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0493 | 620 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0494 | 621 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0495 | 622 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0496 | 623 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0497 | 624 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0498 | 625 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0499 | 626 | CVS AGATE Retrofitted | Low
| RETR0003 | CMR0519 | 401 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0520 | 402 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0521 | 403 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0522 | 404 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0523 | 405 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0524 | 406 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0525 | 407 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0526 | 408 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0527 | 409 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0528 | 410 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0529 | 411 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0530 | 412 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0531 | 413 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0532 | 414 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0533 | 415 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0534 | 416 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0535 | 417 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0536 | 418 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0537 | 419 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0538 | 420 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0539 | 421 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0540 | 422 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0541 | 423 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0542 | 424 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0543 | 601 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0544 | 602 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0545 | 603 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0546 | 604 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0547 | 605 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0548 | 606 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0549 | 607 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0550 | 608 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0551 | 609 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0552 | 610 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0553 | 611 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0554 | 612 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0555 | 613 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0556 | 614 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0557 | 615 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0558 | 616 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0559 | 617 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0560 | 618 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0561 | 619 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0562 | 620 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0563 | 621 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0564 | 622 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0565 | 623 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0566 | 624 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0567 | 625 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0568 | 626 | PCE AGATE Retrofitted | Low
| RETR0007 | CMR0590 | 403 | RESCUE COUPLING | Low
| RETR0007 | CMR0598 | 411 | RESCUE COUPLING | Low
| RETR0011 | CMR0726 | 401 | Battery tray connector | Low
| RETR0011 | CMR0727 | 402 | Battery tray connector | Low
2022-02-07 | RETR0011 | CMR0728 | 403 | Battery tray connector | Low
2022-02-01 | RETR0011 | CMR0729 | 404 | Battery tray connector | Low
| RETR0011 | CMR0730 | 405 | Battery tray connector | Low
| RETR0011 | CMR0732 | 407 | Battery tray connector | Low
| RETR0011 | CMR0733 | 408 | Battery tray connector | Low
2022-02-01 | RETR0011 | CMR0734 | 409 | Battery tray connector | Low
| RETR0011 | CMR0735 | 410 | Battery tray connector | Low
| RETR0011 | CMR0738 | 413 | Battery tray connector | Low
| RETR0011 | CMR0739 | 414 | Battery tray connector | Low
| RETR0011 | CMR0740 | 415 | Battery tray connector | Low
| RETR0011 | CMR0741 | 416 | Battery tray connector | Low
2022-02-07 | RETR0011 | CMR0742 | 417 | Battery tray connector | Low
| RETR0011 | CMR0743 | 418 | Battery tray connector | Low
| RETR0011 | CMR0744 | 419 | Battery tray connector | Low
| RETR0011 | CMR0745 | 420 | Battery tray connector | Low
| RETR0011 | CMR0746 | 421 | Battery tray connector | Low
| RETR0011 | CMR0749 | 424 | Battery tray connector | Low
2022-01-31 | RETR0011 | CMR0750 | 601 | Battery tray connector | Low
2022-01-31 | RETR0011 | CMR0751 | 602 | Battery tray connector | Low
| RETR0011 | CMR0752 | 603 | Battery tray connector | Low
2022-01-05 | RETR0011 | CMR0756 | 607 | Battery tray connector | Low
| RETR0011 | CMR0757 | 608 | Battery tray connector | Low
| RETR0011 | CMR0760 | 611 | Battery tray connector | Low
2022-01-09 | RETR0011 | CMR0762 | 613 | Battery tray connector | Low
| RETR0011 | CMR0764 | 615 | Battery tray connector | Low
| RETR0011 | CMR0765 | 616 | Battery tray connector | Low
| RETR0011 | CMR0768 | 619 | Battery tray connector | Low
| RETR0011 | CMR0770 | 621 | Battery tray connector | Low
| RETR0011 | CMR0772 | 623 | Battery tray connector | Low
| RETR0011 | CMR0773 | 624 | Battery tray connector | Low
| RETR0011 | CMR0774 | 625 | Battery tray connector | Low
| RETR0013 | CMR1002 | 401 | HVAC roof plate exchange | Low
| RETR0013 | CMR1005 | 404 | HVAC roof plate exchange | Low
| RETR0013 | CMR1010 | 409 | HVAC roof plate exchange | Low
| RETR0013 | CMR1013 | 412 | HVAC roof plate exchange | Low
| RETR0013 | CMR1019 | 418 | HVAC roof plate exchange | Low
| RETR0013 | CMR1020 | 419 | HVAC roof plate exchange | Low
| RETR0013 | CMR1021 | 420 | HVAC roof plate exchange | Low
| RETR0013 | CMR1023 | 422 | HVAC roof plate exchange | Low
| RETR0013 | CMR1024 | 423 | HVAC roof plate exchange | Low
| RETR0013 | CMR1025 | 424 | HVAC roof plate exchange | Low
| RETR0013 | CMR1029 | 604 | HVAC roof plate exchange | Low
| RETR0013 | CMR1031 | 606 | HVAC roof plate exchange | Low
| RETR0013 | CMR1033 | 608 | HVAC roof plate exchange | Low
| RETR0013 | CMR1034 | 609 | HVAC roof plate exchange | Low
| RETR0013 | CMR1037 | 612 | HVAC roof plate exchange | Low
| RETR0013 | CMR1039 | 614 | HVAC roof plate exchange | Low
| RETR0013 | CMR1040 | 615 | HVAC roof plate exchange | Low
| RETR0013 | CMR1042 | 617 | HVAC roof plate exchange | Low
| RETR0013 | CMR1044 | 619 | HVAC roof plate exchange | Low
| RETR0013 | CMR1049 | 624 | HVAC roof plate exchange | Low
| RETR0013 | CMR1051 | 626 | HVAC roof plate exchange | Low
| RETR0020 | CMR1468 | 403 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1472 | 407 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1477 | 412 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1479 | 414 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1487 | 422 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1488 | 423 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1491 | 602 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1492 | 603 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1495 | 606 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1498 | 609 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1499 | 610 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1500 | 611 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1501 | 612 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1506 | 617 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1507 | 618 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1508 | 619 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1509 | 620 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1513 | 624 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1514 | 625 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1515 | 626 | Jumper cable and piping at intermiddiate. | Low
| RETR0021 | CMR1518 | 403 | Internal HVAC plate | Low
| RETR0021 | CMR1538 | 423 | Internal HVAC plate | Low
| RETR0021 | CMR1544 | 605 | Internal HVAC plate | Low
| RETR0021 | CMR1545 | 606 | Internal HVAC plate | Low
| RETR0021 | CMR1549 | 610 | Internal HVAC plate | Low
| RETR0021 | CMR1550 | 611 | Internal HVAC plate | Low
2022-05-22 | SU0017 | CMS1122 | 617 | TCMS STR3.4.2 | Low
| SU0019 | CMS1210 | 605 | Smoke detector Version : SRN1194B | Low
| SU0019 | CMS1222 | 617 | Smoke detector Version : SRN1194B | Low
| SU0022 | CMS1372 | 617 | Riyadh Traction Software V1.1.6 | High
| SU0023 | CMS1422 | 617 | BRAKE SW V1.02 | High
| SU0024 | CMS1472 | 617 | SLV ATC Baseline BL 2.9.1.7 | High

## availabilityCHK
2022-08-25
Open Date | Doc Ref | CM Ref |  | TRAIN | Description | IMPACT | Progress
2021-09-20 | TIR0019 |  | 418Low | 418 | HC1 Door1 glass found minor cracked | Low
2021-09-21 | TIR0027 |  | 422Low | 422 | HC1 Door-6 glass cracked | Low
2021-09-26 | TIR0036 |  | 601Low | 601 | HC2- Saloon lights NOK | Low
2021-11-21 | TIR0102 |  | 421Low | 421 | ventilation fault HVAC2-V2 | Low
2021-12-06 | TIR0148 |  | 608Low | 608 | 1.HVAC-Roof Panel gap filler plate not fixed(near to Gangway) | Low
2021-12-06 | TIR0158 |  | 411Low | 411 | HC1- Electrical Coupler NOK. ( Required Fasteners ). | Low
2021-12-06 | TIR0163 |  | 623Low | 623 | T623_HC2_RHS_ Sanding rubber hoses damaged - 1 nos. (DTR0000550155) | Low
2021-12-07 | TIR0170 |  | 411Low | 411 | coupler without electrical coupler cover | Low
2021-12-08 | TIR0175 |  | 415Low | 415 | Earthing cable is not connected between permanent coupler | Low
2021-12-08 | TIR0182 |  | 606Low | 606 | Gangway light mounting nok,there is a gap | Low
2021-12-09 | TIR0202 |  | 601Low | 601 | T601_HC2- missing of sand filter assembly | Low
2021-12-09 | TIR0209 |  | 618Low | 618 | Semi permanent coupler earthing bolt is missing,and Earth strip is lose both sides. | Low
2021-12-09 | TIR0210 |  | 622Low | 622 | Semi permanent coupler earthing bolt is missing. | Low
2021-12-12 | TIR0214 |  | 404Low | 404 | HC1 Bogie1- One HV cable gland missing from the underframe JB. | Low
2021-12-14 | TIR0234 |  | 413Low | 413 | HC1-BOGIE 2 RIGHT HAND SIDE (WFL)WHEEL FLANGE LUBRICATOR STICK HOLDING SAFETY PIN MISSING | Low
2021-12-15 | TIR1032 |  | 414Low | 414 | HC2: WFL (Wheel flange Lubricator) SAFETY PIN IS MISSING( 2 NOS) | Low
2021-12-20 | TIR1036 |  | 609Low | 609 | HC2 PANEL NO1 ALLEN SCREW MISSING. HC2 NEAR DOOR2 SEALING PANEL ALLEN SCREW MISSING. HC1&HC2NEAR TO GANGWAY PANEL ALLEN SCREWS ARE MISSING. | Low
2021-12-20 | TIR1037 |  | 609Low | 609 | Gangway 2 Locks are missing. | Low
2021-12-21 | TIR1038 |  | 415Low | 415 | HC1 ROOF PANEL1 ALLEN SREW 1MISSING AND 1DAMAGE HC2 ROOF PANEL1 ALLEN SREW1DAMAGE. | Low
2021-12-21 | TIR1040 |  | 605Low | 605 | hc2 sanding reservoir for re-filling (empty) | Low
2021-12-26 | TIR1044 |  | 402Low | 402 | HC1 Panel 1 allenkey screw missing | Low
2021-12-28 | TIR0302 |  | 620Low | 620 | ONE INTERNAL GANG COVER MISSING | Low
2021-12-28 | TIR0313 |  | 601Low | 601 | gangways panels are not able to closed | Low
2021-12-29 | TIR1062 |  | 619Low | 619 | HC2-CCC rubber missing. | Low
2021-12-30 | TIR0343 |  | 410Low | 410 | gangway internal cover is missing | Low
2021-12-30 | TIR1066 |  | 421Low | 421 | CAR2 HVAC1,HVAC2,DF 1005_EXFL,DF 1006_EMEXF, EXHAUST AIR FAN LOW, EXHAUST AIR FAN HIGH. | Low
2022-01-02 | TIR0349 |  | 412Low | 412 | GANGWAY INTERNAL PANELS ARE MISSING | Low
2022-01-02 | TIR1072 |  | 603Low | 603 | hc2 left sanding hose missing | Low
2022-01-02 | TIR1073 |  | 603Low | 603 | GANGWAY INTERNAL cover missing hc1 right | Low
2022-01-02 | TIR1076 |  | 609Low | 609 | HC2 PANEL NO1 ALLEN SCREW MISSING. HC2 NEAR DOOR2 SEALING PANEL ALLEN SCREW MISSING. HC1&HC2NEAR TO GANGWAY PANEL ALLEN SCREWS ARE MISSING | Low
2022-01-03 | TIR0375 |  | 609Low | 609 | Gangway locks missing | Low
2022-01-03 | TIR1086 |  | 621Low | 621 | Torque mark damage in bolts of half coupler(gear box and motor) HC1-Axle4- | Low
2022-01-04 | TIR1090 |  | 618Low | 618 | HC1 & HC2 Both side mechanical coupler got stuck while uncoupling of the train | Low
2022-01-04 | TIR1097 |  | 617Low | 617 | HC2 Ceiling panel cover not fixed ( support bracket missing ) | Low
2022-01-04 | TIR1098 |  | 408Low | 408 | Issue Detected Train 408: Broken side panel sheet gangway. | Low
2022-01-04 | TIR1099 |  | 611Low | 611 | Detected during Battery Visual Inspection Trainset 611A - Door tubular seal was found having some damaged. | Low
2022-01-05 | TIR1109 |  | 402Low | 402 | Gangway cover one lock is broken | Low
2022-01-09 | TIR1130 |  | 615Low | 615 | semi permanent coupler grounding bolt missing | Low
2022-01-13 | TIR1150 |  | 414Low | 414 | Partition door lock missing | Low
2022-01-16 | TIR1152 |  | 404Low | 404 | HC1 PANEL 1- 1 ALLEN SCREW MISSING HC2 PANEL1 - 1 ALLEN SCREW MISSING | Low
2022-01-17 | TIR1163 |  | 422Low | 422 | hc1-hc2 sandng reservoir for re-filling, almost empty | Low
2022-01-18 | TIR1177 |  | 403Low | 403 | sand level is low | Low
2022-02-01 | TIR1206 |  | 608Low | 608 | HC-2, CVS - Cover panel, one lock is missing | Low
2022-02-01 | TIR1212 |  | 416Low | 416 | HC1 AXLE4 LHS primary suspension dummy caps (bottom part ) are missing HC2 AXLE1 RHS and AXLE4 LHS primary suspension dummy caps (bottom part ) are missing | Low
2022-02-01 | TIR1213 |  | 416Low | 416 | HC1 Bogie 2 Horizontal damper doesnt have torque marks on its bolts on one end ( two bolts );ALL ECR(earth current return ) cables are without proper torque marks on them (HC1 +HC2) all axle box outer covers are without proper legible torque marks on them (marks are mostly faded are not good) | Low
2022-02-06 | TIR1225 |  | 610Low | 610 | Semi permament coupler earth strip missing one bolt | Low
2022-02-06 | TIR1226 |  | 618Low | 618 | HC-02, A-matric exhaust filter Bottom side - bolt missing and HC-01, Auxillary panel lock is missing | Low
2022-02-06 | TIR1227 |  | 414Low | 414 | No proper (legible ) torque marks on the axle box outer covers (all the axles )-all marks are faded;none of the ECR(EARTH CURRENT RETURN ) cables have proper torque marks on them | Low
2022-02-07 | TIR1233 |  | 408Low | 408 | ONE GANGWAY PANEL DOOR IS MISSING | Low
2022-02-07 | TIR1235 |  | 404Low | 404 | No proper (legible ) torque marks on the axle box outer covers (all the axles )-all marks are faded | Low
2022-02-07 | TIR1240 |  | 617High | 617 | HC1 windscreen glass broken | High
2022-02-08 | TIR1244 |  | 611Low | 611 | semi-permanent coupler grounding bolt missing | Low
2022-02-15 | TIR1290 |  | 607Low | 607 | Momvement on torque marking bolt connection for automatic coupler assembly | Low
2022-02-23 | TIR1335 |  | 613Low | 613 | Both Gangway door panels are Not available | Low
2022-02-23 | TIR1336 |  | 613Low | 613 | HC1 CVS gasket (surrounding the AGATE panel )came out condition | Low
2022-02-23 | TIR1343 |  | 410Low | 410 | HC2, BOGIE-1, Right side, CCD HV cable no clamp for return line | Low
2022-02-24 | TIR1353 |  | 605Low | 605 | Issue Detected in Train 605A & 605B: Missing/ Damage External Safety labels for Battery Box (see photo attached) | Low
2022-02-24 | TIR1356 |  | 406Low | 406 | Issue Detected in Train 406: Automatic Coupler assembly bolt connection was having signs of movement on torque markings @ Train 406B. (see photo attached) | Low
2022-02-24 | TIR1357 |  | 607Low | 607 | Issue Detected in Train 607: Automatic Coupler assembly bolt connection was having signs of movement on torque markings @ Train 607B. (see photo attached) | Low
2022-02-24 | TIR1358 |  | 406Low | 406 | ssue Detected in Train 406 & 614: Torque marking were no longer visible (fully covered with dust/dirt) to serve its purpose for easy identification for any loose bolt connection. This condition was observed in many trains. (see photo attached) | Low
2022-02-24 | TIR1359 |  | 614Low | 614 | ssue Detected in Train 406 & 614: Torque marking were no longer visible (fully covered with dust/dirt) to serve its purpose for easy identification for any loose bolt connection. This condition was observed in many trains. (see photo attached) | Low
2022-02-24 | TIR1364 |  | 409Low | 409 | HC1: LV box-battery connector hinge is missing | Low
2022-02-24 | TIR1369 |  | 619Low | 619 | HC2, Electrical coupler isolate cock is missing (handle). | Low
2022-02-27 | TIR1381 |  | 407Low | 407 | PEED Reset from CC not working for all EED in the train (HC1-HC2 Both side) | Low
2022-03-06 | TIR1392 |  | 404Low | 404 | HC2 axle 2 oil leakage | Low
2022-03-17 | TIR1436 |  | 401Low | 401 | HC2_ROM - Missing of Male connector for 72W03+ROM_XP_ETH1 of Openbat-F Simple Radio Onboard(DTR0000397019) | Low
2022-03-22 | TIR1459 |  | 621Low | 621 | CCC Panel -HC1:scratches | Low
2022-03-29 | TIR1503 |  | 411Low | 411 | HC2 sanding for refilling | Low
2022-03-29 | TIR1505 |  | 412Low | 412 | HC2 right sanding for refilling | Low
2022-03-29 | TIR1507 |  | 604Low | 604 | HC-02, Both sand reservior low level | Low
2022-03-29 | TIR1508 |  | 608Low | 608 | INSIDE TRAIN ONE GANGWAY DOOR NOT AVAILABLE | Low
2022-04-05 | TIR1528 |  | 406Low | 406 | HC1-Electric coupler spring is missing at one side of the cover | Low
2022-04-06 | TIR1535 |  | 402Low | 402 | Hc2 Gearbox #4 leakage on door | Low
2022-04-06 | TIR1539 |  | 613Low | 613 | oil level low and bogie 2 car B, oil color change | Low
2022-04-13 | TIR1594 |  | 604Low | 604 | missing signs on battery box | Low
2022-04-13 | TIR1595 |  | 610Low | 610 | FIRE Extinguishers have not been inspected since December 2021 | Low
2022-04-13 | TIR1601 |  | 409Low | 409 | Horn is not working in HC2 | Low
2022-04-14 | TIR1614 |  | 618Low | 618 | HC1 right side of head light LED's are not working. | Low
2022-04-14 | TIR1628 |  | 415Low | 415 | CCC Panel -HC2 MISSING. | Low
2022-04-17 | TIR1639 |  | 613Low | 613 | oil level low and bogie 2 car B, oil color change | Low
2022-04-18 | TIR1643 |  | 622Low | 622 | Overfilled gearbox oil HC2 bogie 1 axle 2 | Low
2022-04-18 | TIR1647 |  | 601Low | 601 | Gearbox Oil leakage HC2 bogie 1 axle 2 | Low
2022-04-19 | TIR1651 |  | 424Low | 424 | Gangway panel was found missing. | Low
2022-04-19 | TIR1653 |  | 406Low | 406 | HC-02 BCU matrix - Exhaust filter screw missing | Low
2022-04-26 | TIR1680 |  | 604Low | 604 | HC2 gearbox door leakage | Low
2022-04-27 | TIR1684 |  | 621Low | 621 | HC1 AXLE2 RHS ECR cable is damaged-insulation damage at the end of the fixing | Low
2022-04-28 | TIR1689 |  | 603Low | 603 | EAD not working from Right side HC2 | Low
2022-05-15 | TIR1740 |  | 617Low | 617 | hvac water drainage distribution box hose damaged during PM simulation | Low
2022-05-16 | TIR1742 |  | 402Low | 402 | Torqueing to be checked after dismounting the motor for noise test | Low
2022-05-16 | TIR1743 |  | 402Low | 402 | Seals and motor covers damaged after noise test | Low
2022-05-17 | TIR1750 |  | 602Low | 602 | Something unknown is restricting the internal gangway panel movement. | Low
2022-05-17 | TIR1751 |  | 611Low | 611 | The left internal Gangway panel was found missing. | Low
2022-05-17 | TIR1754 |  | 604Low | 604 | The left internal Gangway panel was found missing. | Low
2022-05-18 | TIR1761 |  | 617Low | 617 | IOS267 : At least one software version discordancy fault | Low
2022-05-18 | TIR1762 |  | 617Low | 617 | IOS125 : At least one external smoke sensor is on failure | Low
2022-05-18 | TIR1768 |  | 612Low | 612 | car2 saloon light off near door2 | Low
2022-05-18 | TIR1769 |  | 405Low | 405 | car2 horn pushbutton not working | Low
2022-05-23 | TIR1778 |  | 611Low | 611 | battery warning signages are missing (safety labels) | Low
2022-05-23 | TIR1779 |  | 406Low | 406 | Safety missing in wheel flange lubricator in hc2 | Low
2022-05-25 | TIR1787 |  | 605Low | 605 | HC2 HVAC 1 very strange sound is coming from the hvac unit while start up. | Low
2022-05-25 | TIR1788 |  | 420Low | 420 | HC2 GCL Panel one holding clip missing. | Low
2022-05-25 | TIR1790 |  | 409Low | 409 | TS409 HC1 LV Earthing Cable is broken | Low
2022-06-02 | TIR1794 |  | 404Low | 404 | Traction box : Single pole connector (interfaced with a workshop POS stinger) is boken from train side | Low
2022-06-05 | TIR1796 |  | 611Low | 611 | HC2 HVAC NO2 FAILED IN EXHAUST AIR LOW AND HIGH, CONDENSER FAN lOW AND HIGH | Low
2022-06-05 | TIR1797 |  | 622Low | 622 | There is abnormal sound coming from HVAC in mC1 while train running through tunnel section. | Low
2022-06-06 | TIR1798 |  | 612Low | 612 | automatic coupler level, one bolt is not tighten and otrque marquing not visible (see attached picture) | Low
2022-06-06 | TIR1799 |  | 424Low | 424 | HC2-Left Derailment sensor- one screw Missing | Low
2022-06-09 | TIR1803 |  | 417Low | 417 | IOS1 : One compressor out of service indication | Low
2022-06-13 | TIR1809 |  | 401Low | 401 | Left panel safety rope damaged. Right panel safety rope damaged. Right panel damaged because of not closing. | Low
2022-06-13 | TIR1810 |  | 402Low | 402 | Right Panel safety rope damaged. | Low
2022-06-13 | TIR1811 |  | 403Low | 403 | Left Panel safety rope damaged. Right Panel safety rope damaged. | Low
2022-06-13 | TIR1812 |  | 404Low | 404 | Right Panel middle and bottom Square key locks damaged, cannot open the panel. | Low
2022-06-13 | TIR1813 |  | 405Low | 405 | Gangway left panel door is not available | Low
2022-06-13 | TIR1814 |  | 406Low | 406 | Left Panel safety rope damaged. Right Panel safety rope damaged. | Low
2022-06-13 | TIR1815 |  | 409Low | 409 | Left panel square key lock pattern differnt cannot openRight panel middle sqaure key lock cannot close | Low
2022-06-13 | TIR1816 |  | 410Low | 410 | Right panel middle and bottom Square key locks damaged. | Low
2022-06-13 | TIR1817 |  | 412Low | 412 | Left Panel safety rope damaged. Right Panel safety rope damaged. | Low
2022-06-13 | TIR1818 |  | 413Low | 413 | Left Panel middle square key cannot be locked. Right Panel top and bottom Square key locks damaged, cannot open the panel. | Low
2022-06-13 | TIR1819 |  | 417Low | 417 | on the left side panel -one of the inner black rope is broken on the left side panel -the central lock is unable to close | Low
2022-06-13 | TIR1820 |  | 420Low | 420 | Left panel lock broken and inside safety rope damage, Also gangway suspension spring out of the wheel | Low
2022-06-13 | TIR1821 |  | 423Low | 423 | In both sides - gangway inside safety rope broken. | Low
2022-06-13 | TIR1822 |  | 424Low | 424 | Gangway left panel door is not available Gangway left panel door is not availab | Low
2022-06-13 | TIR1823 |  | 601Low | 601 | On the left side the locking mechanism plate also missing on left side one of the rope is broken on right side the gangway side wall panel(hold in place with only locks ) is detached from its hinges-no hinges are available to hold the gangway panel on right side gangway -one of the rope is wrongly attached to a corner bolt | Low
2022-06-13 | TIR1824 |  | 602Low | 602 | Left Panel middle square key cannot be locked | Low
2022-06-13 | TIR1825 |  | 603Low | 603 | Left Panel middle square key cannot be locked. Left panel safety rope damaged. Right panel safety rope damaged. | Low
2022-06-13 | TIR1826 |  | 604Low | 604 | gangway left panel was found missing. | Low
2022-06-13 | TIR1827 |  | 605Low | 605 | Right Panel middle square key cannot be opened, cannot open the panel. | Low
2022-06-13 | TIR1828 |  | 611Low | 611 | Right panel safety rope is missing. Gangway left found missing | Low
2022-06-13 | TIR1829 |  | 615Low | 615 | Left Panel middle square key cannot be locked | Low
2022-06-13 | TIR1830 |  | 616Low | 616 | left side central lock is unable to close left side panel locks -lock indication is reverse position -it is showing open in horizonatl position and closed in vertical position | Low
2022-06-13 | TIR1831 |  | 617Low | 617 | Right Panel bottom square key lock damaged(rotating). | Low
2022-06-13 | TIR1832 |  | 618Low | 618 | Left panel one of the safety rope is broken In both the panels the central locks are not able to close -only the top and bottom locks are closed in these two panels | Low
2022-06-13 | TIR1833 |  | 619Low | 619 | Left panel middle square key cannot be locked Right panel middle squre key lock damaged | Low
2022-06-13 | TIR1834 |  | 622Low | 622 | Right side panel, lock broken. 2. Also safety rope damage | Low
2022-06-13 | TIR1835 |  | 623Low | 623 | Right side panel, out of 3 locks, 2 locks are not working properly. | Low
2022-06-13 | TIR1836 |  | 624Low | 624 | Right panel Red plastic handle missing. | Low
2022-06-13 | TIR1837 |  | 625Low | 625 | Left panel cannot open Right panel middle square key lock cannot close | Low
2022-06-13 | TIR1838 |  | 626Low | 626 | Right panel middle square key lock cannot close | Low
2022-06-15 | TIR1843 |  | 407Low | 407 | siganges of movements of torque marking of hc2 | Low
2022-06-15 | TIR1849 |  | 410Low | 410 | Many F_DRS_RelCBTrip_2 in the log 45 | Low
2022-06-26 | TIR1862 |  | 617High | 617 | CVS1 Major fault | High
2022-06-27 | TIR1863 |  | 617High | 617 | A-MATRIC 2 HC1 need to replace (swap with 617 and 625). Communication not established after the wakeup | High
2022-06-27 | TIR1864 |  | 617High | 617 | IES module to be replaced PCE_1. | High
2022-06-28 | TIR1868 |  | 604Low | 604 | The manual partition door locking mechanism is broken | Low
2022-07-06 | TIR1876 |  | 610Low | 610 | HVAC2 CAR2 Exhaust air fan low and high are failed. | Low
2022-07-19 | TIR1884 |  | 602Low | 602 | HC2: Bogie2-gearbox 4 has a oil leakage from door | Low
2022-07-20 | TIR1887 |  | 618Low | 618 | HC-1 ACE 1 Square key lock is missing | Low
2022-07-25 | TIR1891 |  | 611Low | 611 | HC2: gear box 4 oil is leakage from gearbox door | Low
2022-07-21 | TIR1893 |  | 405Low | 405 | Pei2/V2 -IP offlineIOS196,203 : Loss of at least 1 PEI in a class | Low
2022-07-31 | TIR1905 |  | 412Low | 412 | TS412 HC2 Bogie-02 Axle-03 (right), missing clamp. | Low
2022-07-31 | TIR1906 |  | 403Low | 403 | Light cover inside the train is damaged, second cover, right side HC2. | Low
2022-07-31 | TIR1908 |  | 413Low | 413 | Saloon light covers inside the train are wrongly positioned. | Low
2022-08-01 | TIR1921 |  | 617Low | 617 | HC1-LV box front cover removed to installed at HC1 T413, | Low
2022-07-31 | TIR1929 |  | 608Low | 608 | ACE Cover is with damaged electrical safety stickers | Low
2022-08-04 | TIR1930 |  | 611Low | 611 | HC2 LV Box Earthing cable found damaged | Low
2022-08-07 | TIR1933 |  | 623Low | 623 | Broken bolt found in TS623 HC2 Traction Box underframe cover. | Low
2022-08-08 | TIR1934 |  | 404Low | 404 | Broken bolt found in TS404 HC1 Traction Box Underframe cover. | Low
2022-08-09 | TIR1939 |  | 626Medium | 626 | TS626 HC2 Bogie-01 Current Colector Arm (right) is not properly align. Please see attached photo for your reference | Medium
2022-08-16 | TIR1952 |  | 625Low | 625 | Corrosion at lifting point on the bogie. Issue observed for all the fleet | Low
2022-08-18 | TIR1956 |  | 424Low | 424 | Need to wheel profil. Impact observed in some wheels | Low
2022-08-17 | TIR1959 |  | 610Low | 610 | HC-2 PCE underframe 1 bolt cannot be tightened because of thread not being ok | Low
2022-08-21 | TIR1961 |  | 423Low | 423 | HC2 - Seat damage. | Low
2022-08-22 | TIR1962 |  | 622Medium | 622 | IOS298:Derailment failure on multiple unit or single unit configuration | Medium
2022-08-22 | TIR1965 |  | 405Low | 405 | pei1 v2, led3 v1 not working | Low
2022-08-22 | TIR1966 |  | 403Low | 403 | Train association issues HVAC IOS39/40 | Low
2022-08-22 | TIR1967 |  | 625Low | 625 | IOS40 and IOS39 , normalized after train sleep-wake-up | Low
2022-08-22 | TIR1968 |  | 602Medium | 602 | IOS39 triggered at transfer track. Could not associate to TT, sent to 6A1. Then 4B1 and 4C1 P1 to associate | Medium
2022-08-23 | TIR1969 |  | 421Low | 421 | Damaged paint in roof covers HC1 | Low
2022-08-23 | TIR1970 |  | 601Low | 601 | HVAC 2 V1 communication failed | Low
2022-08-23 | TIR1971 |  | 615Low | 615 | VAC Auto test failed | Low
2022-08-24 | TIR1972 |  | 413Low | 413 | IP Offline : papis ctrl2 and pais pa2,UMC autotest failed and UMC2 SW version nok.;IOS251 : One MUC have a communication fault | Low
2022-08-23 | TIR1974 |  | 417Low | 417 | lcd2-v1 ip offline | Low
2022-08-23 | TIR1975 |  | 619Low | 619 | papis pa2 ip offline | Low
2022-08-25 | TIR1976 |  | 411Low | 411 | no CCTV display can seen for any camera | Low
2022-08-25 | TIR1977 |  | 619Low | 619 | no CCTV display can seen for any camera | Low
2022-08-25 | TIR1978 |  | 601Low | 601 | IOS250 : One HVAC communication fault. | Low
2022-08-25 | TIR1979 |  | 607Low | 607 | TS607 HC2 Odometer Cover bolt missing. See attached photo | Low
2022-08-25 | TIR1980 |  | 616Low | 616 | MC2 water gutter or duct missing. See picture sent in FAMP TSY RST groupe | Low
| RETR0002 | CMR0450 | 401Low | 401 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0451 | 402Low | 402 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0452 | 403Low | 403 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0453 | 404Low | 404 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0454 | 405Low | 405 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0455 | 406Low | 406 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0456 | 407Low | 407 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0457 | 408Low | 408 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0458 | 409Low | 409 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0459 | 410Low | 410 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0460 | 411Low | 411 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0461 | 412Low | 412 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0462 | 413Low | 413 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0463 | 414Low | 414 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0464 | 415Low | 415 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0465 | 416Low | 416 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0466 | 417Low | 417 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0467 | 418Low | 418 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0468 | 419Low | 419 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0469 | 420Low | 420 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0470 | 421Low | 421 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0471 | 422Low | 422 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0472 | 423Low | 423 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0473 | 424Low | 424 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0474 | 601Low | 601 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0475 | 602Low | 602 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0476 | 603Low | 603 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0477 | 604Low | 604 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0478 | 605Low | 605 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0479 | 606Low | 606 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0480 | 607Low | 607 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0481 | 608Low | 608 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0482 | 609Low | 609 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0483 | 610Low | 610 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0484 | 611Low | 611 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0485 | 612Low | 612 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0486 | 613Low | 613 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0487 | 614Low | 614 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0488 | 615Low | 615 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0489 | 616Low | 616 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0490 | 617Low | 617 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0491 | 618Low | 618 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0492 | 619Low | 619 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0493 | 620Low | 620 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0494 | 621Low | 621 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0495 | 622Low | 622 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0496 | 623Low | 623 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0497 | 624Low | 624 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0498 | 625Low | 625 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0499 | 626Low | 626 | CVS AGATE Retrofitted | Low
| RETR0003 | CMR0519 | 401Low | 401 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0520 | 402Low | 402 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0521 | 403Low | 403 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0522 | 404Low | 404 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0523 | 405Low | 405 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0524 | 406Low | 406 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0525 | 407Low | 407 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0526 | 408Low | 408 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0527 | 409Low | 409 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0528 | 410Low | 410 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0529 | 411Low | 411 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0530 | 412Low | 412 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0531 | 413Low | 413 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0532 | 414Low | 414 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0533 | 415Low | 415 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0534 | 416Low | 416 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0535 | 417Low | 417 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0536 | 418Low | 418 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0537 | 419Low | 419 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0538 | 420Low | 420 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0539 | 421Low | 421 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0540 | 422Low | 422 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0541 | 423Low | 423 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0542 | 424Low | 424 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0543 | 601Low | 601 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0544 | 602Low | 602 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0545 | 603Low | 603 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0546 | 604Low | 604 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0547 | 605Low | 605 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0548 | 606Low | 606 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0549 | 607Low | 607 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0550 | 608Low | 608 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0551 | 609Low | 609 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0552 | 610Low | 610 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0553 | 611Low | 611 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0554 | 612Low | 612 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0555 | 613Low | 613 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0556 | 614Low | 614 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0557 | 615Low | 615 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0558 | 616Low | 616 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0559 | 617Low | 617 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0560 | 618Low | 618 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0561 | 619Low | 619 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0562 | 620Low | 620 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0563 | 621Low | 621 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0564 | 622Low | 622 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0565 | 623Low | 623 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0566 | 624Low | 624 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0567 | 625Low | 625 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0568 | 626Low | 626 | PCE AGATE Retrofitted | Low
| RETR0007 | CMR0590 | 403Low | 403 | RESCUE COUPLING | Low
| RETR0007 | CMR0598 | 411Low | 411 | RESCUE COUPLING | Low
| RETR0011 | CMR0726 | 401Low | 401 | Battery tray connector | Low
| RETR0011 | CMR0727 | 402Low | 402 | Battery tray connector | Low
2022-02-07 | RETR0011 | CMR0728 | 403Low | 403 | Battery tray connector | Low
2022-02-01 | RETR0011 | CMR0729 | 404Low | 404 | Battery tray connector | Low
| RETR0011 | CMR0730 | 405Low | 405 | Battery tray connector | Low
| RETR0011 | CMR0732 | 407Low | 407 | Battery tray connector | Low
| RETR0011 | CMR0733 | 408Low | 408 | Battery tray connector | Low
2022-02-01 | RETR0011 | CMR0734 | 409Low | 409 | Battery tray connector | Low
| RETR0011 | CMR0735 | 410Low | 410 | Battery tray connector | Low
| RETR0011 | CMR0738 | 413Low | 413 | Battery tray connector | Low
| RETR0011 | CMR0739 | 414Low | 414 | Battery tray connector | Low
| RETR0011 | CMR0740 | 415Low | 415 | Battery tray connector | Low
| RETR0011 | CMR0741 | 416Low | 416 | Battery tray connector | Low
2022-02-07 | RETR0011 | CMR0742 | 417Low | 417 | Battery tray connector | Low
| RETR0011 | CMR0743 | 418Low | 418 | Battery tray connector | Low
| RETR0011 | CMR0744 | 419Low | 419 | Battery tray connector | Low
| RETR0011 | CMR0745 | 420Low | 420 | Battery tray connector | Low
| RETR0011 | CMR0746 | 421Low | 421 | Battery tray connector | Low
| RETR0011 | CMR0749 | 424Low | 424 | Battery tray connector | Low
2022-01-31 | RETR0011 | CMR0750 | 601Low | 601 | Battery tray connector | Low
2022-01-31 | RETR0011 | CMR0751 | 602Low | 602 | Battery tray connector | Low
| RETR0011 | CMR0752 | 603Low | 603 | Battery tray connector | Low
2022-01-05 | RETR0011 | CMR0756 | 607Low | 607 | Battery tray connector | Low
| RETR0011 | CMR0757 | 608Low | 608 | Battery tray connector | Low
| RETR0011 | CMR0760 | 611Low | 611 | Battery tray connector | Low
2022-01-09 | RETR0011 | CMR0762 | 613Low | 613 | Battery tray connector | Low
| RETR0011 | CMR0764 | 615Low | 615 | Battery tray connector | Low
| RETR0011 | CMR0765 | 616Low | 616 | Battery tray connector | Low
| RETR0011 | CMR0768 | 619Low | 619 | Battery tray connector | Low
| RETR0011 | CMR0770 | 621Low | 621 | Battery tray connector | Low
| RETR0011 | CMR0772 | 623Low | 623 | Battery tray connector | Low
| RETR0011 | CMR0773 | 624Low | 624 | Battery tray connector | Low
| RETR0011 | CMR0774 | 625Low | 625 | Battery tray connector | Low
| RETR0013 | CMR1002 | 401Low | 401 | HVAC roof plate exchange | Low
| RETR0013 | CMR1005 | 404Low | 404 | HVAC roof plate exchange | Low
| RETR0013 | CMR1010 | 409Low | 409 | HVAC roof plate exchange | Low
| RETR0013 | CMR1013 | 412Low | 412 | HVAC roof plate exchange | Low
| RETR0013 | CMR1019 | 418Low | 418 | HVAC roof plate exchange | Low
| RETR0013 | CMR1020 | 419Low | 419 | HVAC roof plate exchange | Low
| RETR0013 | CMR1021 | 420Low | 420 | HVAC roof plate exchange | Low
| RETR0013 | CMR1023 | 422Low | 422 | HVAC roof plate exchange | Low
| RETR0013 | CMR1024 | 423Low | 423 | HVAC roof plate exchange | Low
| RETR0013 | CMR1025 | 424Low | 424 | HVAC roof plate exchange | Low
| RETR0013 | CMR1029 | 604Low | 604 | HVAC roof plate exchange | Low
| RETR0013 | CMR1031 | 606Low | 606 | HVAC roof plate exchange | Low
| RETR0013 | CMR1033 | 608Low | 608 | HVAC roof plate exchange | Low
| RETR0013 | CMR1034 | 609Low | 609 | HVAC roof plate exchange | Low
| RETR0013 | CMR1037 | 612Low | 612 | HVAC roof plate exchange | Low
| RETR0013 | CMR1039 | 614Low | 614 | HVAC roof plate exchange | Low
| RETR0013 | CMR1040 | 615Low | 615 | HVAC roof plate exchange | Low
| RETR0013 | CMR1042 | 617Low | 617 | HVAC roof plate exchange | Low
| RETR0013 | CMR1044 | 619Low | 619 | HVAC roof plate exchange | Low
| RETR0013 | CMR1049 | 624Low | 624 | HVAC roof plate exchange | Low
| RETR0013 | CMR1051 | 626Low | 626 | HVAC roof plate exchange | Low
| RETR0020 | CMR1468 | 403Low | 403 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1472 | 407Low | 407 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1477 | 412Low | 412 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1479 | 414Low | 414 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1487 | 422Low | 422 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1488 | 423Low | 423 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1491 | 602Low | 602 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1492 | 603Low | 603 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1495 | 606Low | 606 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1498 | 609Low | 609 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1499 | 610Low | 610 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1500 | 611Low | 611 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1501 | 612Low | 612 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1506 | 617Low | 617 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1507 | 618Low | 618 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1508 | 619Low | 619 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1509 | 620Low | 620 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1513 | 624Low | 624 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1514 | 625Low | 625 | Jumper cable and piping at intermiddiate. | Low
| RETR0020 | CMR1515 | 626Low | 626 | Jumper cable and piping at intermiddiate. | Low
| RETR0021 | CMR1518 | 403Low | 403 | Internal HVAC plate | Low
| RETR0021 | CMR1538 | 423Low | 423 | Internal HVAC plate | Low
| RETR0021 | CMR1544 | 605Low | 605 | Internal HVAC plate | Low
| RETR0021 | CMR1545 | 606Low | 606 | Internal HVAC plate | Low
| RETR0021 | CMR1549 | 610Low | 610 | Internal HVAC plate | Low
| RETR0021 | CMR1550 | 611Low | 611 | Internal HVAC plate | Low
2022-05-22 | SU0017 | CMS1122 | 617Low | 617 | TCMS STR3.4.2 | Low
| SU0019 | CMS1210 | 605Low | 605 | Smoke detector Version : SRN1194B | Low
| SU0019 | CMS1222 | 617Low | 617 | Smoke detector Version : SRN1194B | Low
| SU0022 | CMS1372 | 617High | 617 | Riyadh Traction Software V1.1.6 | High
| SU0023 | CMS1422 | 617High | 617 | BRAKE SW V1.02 | High
| SU0024 | CMS1472 | 617High | 617 | SLV ATC Baseline BL 2.9.1.7 | High

## Sheet1
TRAIN | ACTIVITY TYPE | ACTIVITY REFERENCE | ACTIVITY DESCRIPTION | IMPACT | Status
606 | NCR | NCR0225 | Damaged train wipers | Low | Open
604 | NCR | NCR0226 | Damaged train wipers | Low | Open
416 | NCR | NCR0227 | Damaged train wipers | Low | Open
421 | NCR | NCR0341 | HVAC fault. | Low | Open
406 | NCR | NCR0342 | PEI lost communication | Medium | Open
512 | NCR | NCR0348 | HVAC compressor and ventilation fault | High | Open
418 | NCR | NCR0352 | Passenger door glass cracked | Low | Open
624 | NCR | NCR0353 | Scratches on T624 HC1 Door glass | Low | Open
411 | NCR | NCR0358 | Electrical coupler frame broken | Medium | Open
502 | NCR | NCR0360 | Sanding rubber hoses and clams missing | Low | Open
603 | NCR | NCR0361 | Beacon Antenna screws missing | Low | Open
603 | NCR | NCR0362 | Left side sanding hose not availabe | Low | Open
606 | NCR | NCR0372 | Gap filler between HVAC and Gangway missing | Low | Open
601 | NCR | NCR0375 | AGTU_Missing of Sand filter Assembly | Low | Open
601 | NCR | NCR0376 | leakage found from the spring brake part. | Low | Open
610 | NCR | NCR0377 | Head and Tail Light white LED not working | Low | Open
617 | NCR | NCR0378 | Head and Tail Light white LED not working | Low | Open
601 | NCR | NCR0381 | LCD & EDI error display | Low | Open
611 | NCR | NCR0382 | Axle Gearbox leakage | Low | Open
611 | NCR | NCR0383 | Head and Tail Light LED not working | Low | Open
417 | NCR | NCR0385 | Under seat fire extinguisher BOX and GCL fire Extinguisher bracket not available | Low | Open
626 | NCR | NCR0387 | LCD poor display issue | Low | Open
507 | NCR | NCR0389 | Under seat fire extinguisher BOX not available | Low | Open
404 | NCR | NCR0390 | fire extinguisher holding plate not available | Low | Open
404 | NCR | NCR0391 | Saloon light not working | Low | Open
612 | NCR | NCR0393 | LCD display issues | Low | Open
422 | NCR | NCR0394 | Door glass cracked | Low | Open
601 | NCR | NCR0395 | Saloon Light not working | Low | Open
623 | NCR | NCR0397 | Driver Cab Light not working | Low | Open
416 | NCR | NCR0401 | LCD display issues | Low | Open
603 | NCR | NCR0403 | Air leakage found from the spring brake part. | Low | Open
404 | NCR | NCR0405 | HV cable gland missing from the underframe Junction Box | Low | Open
623 | NCR | NCR0406 | stinger cap cover broken | Low | Open
606 | NCR | NCR0408 | Gangway Gap filler damaged | Low | Open
415 | NCR | NCR0414 | Earthing cable is not connected between permanent coupler | Low | Open
618 | NCR | NCR0417 | Earthing cable is not connected between permanent coupler | Low | Open
622 | NCR | NCR0418 | Earthing cable is not connected between permanent coupler | Low | Open
403 | NCR | NCR0420 | Axle Gearbox leakage | Low | Open
512 | NCR | NCR0422 | Head and Tail Light white LED not working | Low | Open
503 | NCR | NCR0425 | Gangway lights Dim,working inversely | Low | Open
413 | NCR | NCR0427 | Stick holding safety pin missing. | Low | Open
410 | NCR | NCR0428 | LCD dim display issue | Low | Open
503 | NCR | NCR0429 | Fuse box glass cracked. | Low | Open
501 | NCR | NCR0430 | DOOR indication light not working | Low | Open
515 | NCR | NCR0431 | Fuse box glass cracked. | Low | Open
508 | NCR | NCR0432 | STF-DL beacon Antenna : HC1 1 bolt ,HC2 2 bolt not available | Low | Open
515 | NCR | NCR0433 | Stick holding safety pin missing | Low | Open
513 | NCR | NCR0435 | Several devices communcation fail (TCN, CRS, TRS or Netbox and HVAC communication fault), | High | Open
507 | NCR | NCR0436 | HV cable support clamp missing | Low | Open
504 | NCR | NCR0437 | Gangway Panel has scractch &Lock missing | Low | Open
501 | NCR | NCR0438 | Derailment sensor cable clamp missing | Low | Open
410 | NCR | NCR0439 | ONE INTERNAL Gangway COVER MISSING | Low | Open
625 | NCR | NCR0440 | SWD3-V1 half display issue | Low | Open
601 | NCR | NCR0441 | Gangways panels are not able to be closed | Low | Open
502 | NCR | NCR0442 | Found minor leakage from the gearbox drain plug cause by O-ring defect. | Low | Open
407 | NCR | NCR0443 | Found minor leakage from the gearbox inspection cover | Low | Open
412 | NCR | NCR0444 | Gangways panels are missing | Low | Open
410 | NCR | NCR0445 | Gangways panel is missing | Low | Open
609 | NCR | NCR0446 | Gangway locks missing | Low | Open
511 | NCR | NCR0447 | Roof antenna damaged due to hit roller shutter at W5 while movement | Low | Open
607 | NCR | NCR0449 | Gearbox oil axle 3 is contaminated. | Low | Open
607 | NCR | NCR0450 | Gear box oil level is below minimum level | Low | Open
422 | NCR | NCR0452 | LEDI1-V2 offline and dark | Low | Open
611 | NCR | NCR0453 | Battery Door tubular seal some damaged | Low | Open
611 | NCR | NCR0454 | Battery Door External safety label damaged | Low | Open
409 | NCR | NCR1002 | IOS185 : 1 APC LV Status false, IOS179 : 1 APC MV Status false | High | Open
404 | NCR | NCR1056 | Gearbox 1&2 oil level below minimum but no leakage issue observed. | High | Open
401 | NCR | 192711 | I-NVR mask camera | LOW | Open
402 | NCR | 192711 | I-NVR mask camera | LOW | Open
403 | NCR | 192711 | I-NVR mask camera | LOW | Open
404 | NCR | 192711 | I-NVR mask camera | LOW | Open
405 | NCR | 192711 | I-NVR mask camera | LOW | Open
406 | NCR | 192711 | I-NVR mask camera | LOW | Open
407 | NCR | 192711 | I-NVR mask camera | LOW | Open
408 | NCR | 192711 | I-NVR mask camera | LOW | Open
409 | NCR | 192711 | I-NVR mask camera | LOW | Open
410 | NCR | 192711 | I-NVR mask camera | LOW | Open
411 | NCR | 192711 | I-NVR mask camera | LOW | Open
412 | NCR | 192711 | I-NVR mask camera | LOW | Open
413 | NCR | 192711 | I-NVR mask camera | LOW | Open
414 | NCR | 192711 | I-NVR mask camera | LOW | Open
415 | NCR | 192711 | I-NVR mask camera | LOW | Open
416 | NCR | 192711 | I-NVR mask camera | LOW | Open
417 | NCR | 192711 | I-NVR mask camera | LOW | Open
418 | NCR | 192711 | I-NVR mask camera | LOW | Open
419 | NCR | 192711 | I-NVR mask camera | LOW | Open
420 | NCR | 192711 | I-NVR mask camera | LOW | Open
421 | NCR | 192711 | I-NVR mask camera | LOW | Open
422 | NCR | 192711 | I-NVR mask camera | LOW | Open
423 | NCR | 192711 | I-NVR mask camera | LOW | Open
424 | NCR | 192711 | I-NVR mask camera | LOW | Open
501 | NCR | 192711 | I-NVR mask camera | LOW | Open
502 | NCR | 192711 | I-NVR mask camera | LOW | Open
503 | NCR | 192711 | I-NVR mask camera | LOW | Open
504 | NCR | 192711 | I-NVR mask camera | LOW | Open
505 | NCR | 192711 | I-NVR mask camera | LOW | Open
506 | NCR | 192711 | I-NVR mask camera | LOW | Open
507 | NCR | 192711 | I-NVR mask camera | LOW | Open
508 | NCR | 192711 | I-NVR mask camera | LOW | Open
509 | NCR | 192711 | I-NVR mask camera | LOW | Open
510 | NCR | 192711 | I-NVR mask camera | LOW | Open
511 | NCR | 192711 | I-NVR mask camera | LOW | Open
512 | NCR | 192711 | I-NVR mask camera | LOW | Open
513 | NCR | 192711 | I-NVR mask camera | LOW | Open
514 | NCR | 192711 | I-NVR mask camera | LOW | Open
515 | NCR | 192711 | I-NVR mask camera | LOW | Open
516 | NCR | 192711 | I-NVR mask camera | LOW | Open
517 | NCR | 192711 | I-NVR mask camera | LOW | Open
518 | NCR | 192711 | I-NVR mask camera | LOW | Open
519 | NCR | 192711 | I-NVR mask camera | LOW | Open
601 | NCR | 192711 | I-NVR mask camera | LOW | Open
602 | NCR | 192711 | I-NVR mask camera | LOW | Open
603 | NCR | 192711 | I-NVR mask camera | LOW | Open
604 | NCR | 192711 | I-NVR mask camera | LOW | Open
605 | NCR | 192711 | I-NVR mask camera | LOW | Open
606 | NCR | 192711 | I-NVR mask camera | LOW | Open
607 | NCR | 192711 | I-NVR mask camera | LOW | Open
608 | NCR | 192711 | I-NVR mask camera | LOW | Open
609 | NCR | 192711 | I-NVR mask camera | LOW | Open
610 | NCR | 192711 | I-NVR mask camera | LOW | Open
611 | NCR | 192711 | I-NVR mask camera | LOW | Open
612 | NCR | 192711 | I-NVR mask camera | LOW | Open
613 | NCR | 192711 | I-NVR mask camera | LOW | Open
614 | NCR | 192711 | I-NVR mask camera | LOW | Open
615 | NCR | 192711 | I-NVR mask camera | LOW | Open
616 | NCR | 192711 | I-NVR mask camera | LOW | Open
617 | NCR | 192711 | I-NVR mask camera | LOW | Open
618 | NCR | 192711 | I-NVR mask camera | LOW | Open
619 | NCR | 192711 | I-NVR mask camera | LOW | Open
620 | NCR | 192711 | I-NVR mask camera | LOW | Open
621 | NCR | 192711 | I-NVR mask camera | LOW | Open
622 | NCR | 192711 | I-NVR mask camera | LOW | Open
623 | NCR | 192711 | I-NVR mask camera | LOW | Open
624 | NCR | 192711 | I-NVR mask camera | LOW | Open
625 | NCR | 192711 | I-NVR mask camera | LOW | Open
626 | NCR | 192711 | I-NVR mask camera | LOW | Open
603 | NCR | 220211 | Air leakage is observed from the spring brake part. | LOW | Open
601 | NCR | 220211 | Air leakage is observed from the spring brake part. | LOW | Open

## INPUT
TRAIN | TYPE | IMPACT
401 | TIR | LOW
402 | NCR | HIGH
403 | RET | OPEN
404 | SU | MEDIUM | SU0004 | PAPIS
405 |  |  | SU0002 | brake
406 |  |  | SU0003 | HVAC
407 |  |  | SU0005 | TCMS
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626