## Train status
21/7/2022
Open Date | Doc Ref | CM Ref | TRAIN | Description | IMPACT | Progress
2021-09-21 | TIR0033 |  | 515 | HC2 Bogie2 Left Fuse box glass minor cracked | Low
2021-09-21 | TIR1014 |  | 506 | IP Offline - HC2 {Ledi1, Lcd3, Lcd4} Display Status - HC2 { (Ledi1-White)(Lcd3-Nok)(Lcd4-Dim) | Low
2021-09-26 | TIR1016 |  | 508 | IP Offline and Display also NOK { Ledi4-V1, Swd2-V1 } | Low
2021-09-26 | TIR1017 |  | 509 | Display Status { Ledi4-V2 - NOK } | Low
2021-09-26 | TIR1019 |  | 519 | HVAC2-V2 Low Pressure 1 NOK ( Compressor 1&2 ) | Medium
2021-12-06 | TIR0161 |  | 503 | HC1 Bogie2 Right- Fuse box glass minor cracked. | Low
2021-12-06 | TIR0164 |  | 502 | Sanding rubber hoses missing - 4 nos, clamp - 4pcs. (RIY 000000370) | Low
2021-12-08 | TIR0198 |  | 502 | HC2 Axle 4 found minor leakage from the gearbox. | Low
2021-12-08 | TIR0199 |  | 502 | Sand hose not available in both HC. | Low
2021-12-09 | TIR0207 |  | 512 | HC2- Head Light Nok(LHS 1 white LED not lit) | Low
2021-12-13 | TIR0229 |  | 515 | HC1-flange lubricator saftey pin missing | Low
2021-12-15 | TIR1034 |  | 519 | HC2-B2-Axle3 found minor leakage | Low
2021-12-26 | TIR1046 |  | 517 | HC2-B2 -Axle4 minor leakge from top door of gearbox.(GASKET )-s.no C484 | Low
2021-12-28 | TIR0325 |  | 504 | Gangway Panel has scractch &Lock missing | Low
2021-12-28 | TIR0326 |  | 507 | CCD to JB_ HV cable support clamp missing,HC1_bogie2 Left,HC2-Bogie1,2-Right | Low
2021-12-28 | TIR1051 |  | 505 | HC1-HVAC1_compressor2 Loud noise | Low
2021-12-28 | TIR1052 |  | 505 | HC1-swd.4-Half broken ,Ledi4-blank | Low
2021-12-29 | TIR0336 |  | 501 | HC2- Bogie1 left side derailment sensor cable clamp missing | Low
2021-12-30 | TIR1068 |  | 511 | Gangway 2 Lock Nok | Low
2022-01-02 | TIR1069 |  | 516 | Gangway Panel Lock 3 no.s Nok | Low
2022-01-03 | TIR1087 |  | 502 | Gangway 1 lock is broken | Low
2022-01-03 | TIR1088 |  | 512 | Gangway 1 lock is broken | Low
2022-01-05 | TIR1104 |  | 517 | HC1-B1 -Axle2 minor leakge from top door of gear box .(GASKET )-s.no C447 | Low
2022-01-06 | TIR1113 |  | 507 | HC1-HVAC1-compressor 1&3 making noise | Low
2022-01-09 | TIR1124 |  | 515 | HC1-becon Antenna Cable's clamp missing | Low
2022-01-10 | TIR1135 |  | 510 | Flange Lubricator saftey pin1 missing | Low
2022-01-10 | TIR1136 |  | 510 | Gangway lock has an issue | Low
2022-01-10 | TIR1137 |  | 505 | Hc1-becon Antenna Cable's clamp one screw is missing(refer picture in TIR report) | Low
2022-01-11 | TIR1141 |  | 502 | Gearbox oil leakage | Low
2022-01-16 | TIR1151 |  | 519 | HC2-Sand reserviour is empty | Low
2022-01-17 | TIR1155 |  | 501 | Primary suspension's bottom cover -8 nos.(Refer picture) | Low
2022-01-17 | TIR1157 |  | 506 | Primary suspension's bottom cover -8 nos.(Refer picture) | Low
2022-01-17 | TIR1158 |  | 506 | HC1-Flange Lubricator saftey pin missing | Low
2022-01-17 | TIR1159 |  | 511 | Primary suspension's bottom cover -8 nos.(Refer picture) | Low
2022-01-18 | TIR1176 |  | 514 | Hc2-Sand Level Low | Low
2022-01-19 | TIR1187 |  | 514 | when the train is correctly docked and PEED of the door towards the track is applied and the train driving mood is switched from ATPM to UTO the door towards the track opens (less than 2.5 cm) and closes immediately. o When the door opening alarm is triggered by ATC area securing zone is applied. o Issue is observed only on the mainline. | Low
2022-02-01 | TIR1208 |  | 516 | HC1-HVAC1-Compressor 3 Noise | Low
2022-02-01 | TIR1209 |  | 512 | Hc1-First class passenger saloon light in reverse brightness | Low
2022-02-01 | TIR1210 |  | 512 | Hc1-First class passenger saloon light in reverse brightness | Low
2022-02-06 | TIR1220 |  | 517 | HC1-Stinger 750vdc Power connector female broken(Refer Pic) | Low
2022-02-06 | TIR1221 |  | 517 | HC1-Bogie1 left side Fuse box -JB cable clamp missing(Refer Pic) | Low
2022-02-06 | TIR1222 |  | 518 | HC1- Becon Antenna cable stressed due to unfit bracket installed | Low
2022-02-06 | TIR1223 |  | 518 | HC1-HVAC1/LP2 Low level ;HC2-HVAC1/LP2 Low Level | Low
2022-02-08 | TIR1246 |  | 515 | Hc2- Both Derailment sensor and earth cable clamp missing | Low
2022-02-10 | TIR1264 |  | 505 | Gangway internal Panel has minor scratch | Low
2022-02-10 | TIR1265 |  | 510 | HC1-HVAC2 LP2 Gas level Low | Low
2022-02-11 | TIR1277 |  | 506 | Interglass door function - not open/close fully | Low
2022-02-14 | TIR1286 |  | 514 | HC1-lcd3 offline; HC1-Lcd.3 BLANK,HC2 Lcd3 Dim | Low
2022-02-14 | TIR1288 |  | 516 | HC2-SWD 3 offline;HC2 -SWD.3 Half blank,half error message | Low
2022-02-15 | TIR1293 |  | 502 | HC1-Ledi.6;HC2-Ledi3,Lcd3,Swd3 offline [HC1-Ledi.6-software not up-to-date ,HC2 -Ledi3 Error message] | Low
2022-02-15 | TIR1294 |  | 512 | HC1-Ledi.6;HC2-Ledi3,Lcd3,Swd3 offline [HC1-Ledi.6-software not up-to-date ,HC2 -Ledi3 Error message] | Low
2022-02-16 | TIR1304 |  | 503 | IP Offline: HC1- All Ledi-V1; HC2- All Ledi-V1, Lcd5-V2 PAPIS Display Visual Status: HC1 & HC2- All Ledi Error Message; HC2-Lcd 2 & 5 Blank IOS199 : Loss of all interior LCD compact displays in the same platform | Low
2022-02-16 | TIR1305 |  | 503 | Partition Door not closing fully | Low
2022-02-16 | TIR1306 |  | 503 | IP Offline: HC1- All Ledi-V1; HC2- All Ledi-V1, Lcd5-V2 PAPIS Display Visual Status: HC1:LCD2,LEDI3-Nok; SWD3 Half display with error message; SWD5 Half display HC2:LEDI2 Nok SW Not Up-To-Date- | Low
2022-02-17 | TIR1308 |  | 503 | Partition Door not closing fully | Low
2022-02-17 | TIR1316 |  | 517 | HVAC1-V1 gas level Low pressure 1 & 2 | Low
2022-02-17 | TIR1317 |  | 518 | IP Offline: Dcu2-v2 IOS262 : More than one DCU have a communication fault. | Medium
2022-02-17 | TIR1318 |  | 518 | HC1-HVAC1 Compressor1,2,3&4 are Noisy. | Low
2022-02-20 | TIR1321 |  | 503 | IOS199+ IOS196 | Low
2022-02-21 | TIR1328 |  | 504 | IP scanner : HC1: Lcd1, Swd4, Ledi 1,2,3,4&6; Hc2: Swd3, Ledi 1,2,3,4,5 & 6- Offline ; PAPIS Display Visual Status : HC1: Lcd1- SW not UP-TO-DATE ; Swd4- Nok Black; Ledi 1,2,3,4&6- Error message; Hc2: Swd3-Nok Black Ledi 1,2,3,4,5 & 6- Error Message; IOS199 : Loss of all interior LCD compact displays in the same platform | Low
2022-02-21 | TIR1330 |  | 507 | IP scanner : HC1-swd4; Hc2-Ledi3,Lcd3,Pei3,swd3- Offline; PAPIS Display Visual Status : SWD3-V1 half blank, SWD4-V1 black IOS196 : Loss of at least 1 PEI in a class | Low
2022-03-23 | TIR1475 |  | 509 | software version : UMC2 0.0.0;IOS251 : One MUC have a communication fault ; Display Status: HC1-SWD4 blank; HC2-SWD5-Half blank | Low
2022-03-24 | TIR1484 |  | 504 | IOS199 : Loss of all interior LCD compact displays in the same platform | Low
2022-03-25 | TIR1489 |  | 501 | IP offline-Papis Pa2,Hc1-SWD1 | Low
2022-03-25 | TIR1490 |  | 506 | HC2-HVAC1 All compressors Noise observed | Low
2022-03-30 | TIR1518 |  | 513 | IP offline-HC1-Ledi3,swd3, HC2 -Ledi2; Display status: HC1:LEDI3-Nok BLANK; SWD3 Half display with error message; SWD5 Half display,HC2:LEDI2 Nok SW Not Up-to date | Low
2022-03-30 | TIR1519 |  | 513 | GCL-saloon light off | Low
2022-04-13 | TIR1588 |  | 510 | low oil level gearbox C310 Hc2 | Low
2022-04-13 | TIR1589 |  | 505 | SWD5 has an unfunctional spot | Low
2022-04-13 | TIR1592 |  | 509 | Low oil level for gear box Hc2 Axle4 | Low
2022-04-14 | TIR1627 |  | 504 | Deep scratch HC1 door 1, side panel. | Low
2022-04-14 | TIR1634 |  | 517 | HC2-DCR_EB Push Button dosent hold when pressed | Low
2022-04-14 | TIR1635 |  | 518 | IP offline -(Papis Pa1,HC2-Pei3,Cami2};IOS192 : Loss of at least one camera;IOS196 : Loss of at least 1 PEI in a class | Low
2022-04-14 | TIR1636 |  | 518 | HC1-Door1,2 close immediately and intailly both DCU goes to offline after reset DCU then become online | Low
2022-04-20 | TIR1658 |  | 519 | HC1- Horn Volume Low | Low
2022-04-21 | TIR1665 |  | 519 | HC2- CVS bottom Filter cover alen screw Missing=1 no. | Low
2022-04-26 | TIR1682 |  | 502 | IP Offline- HC1-LCD5 ; Display Status - HC1-LCD5 Error message ;HC2 -LCD5 BLANK,SWD1 BLANK | Low
2022-05-08 | TIR1694 |  | 504 | IOS91 : ONE LMRG Bypass active on unit .Active in HC2 via PECD and found Bypass switch is Normal so Need to be further check. | Low
2022-05-09 | TIR1703 |  | 515 | HC1,HC2: Sand Level Low | Low
2022-05-09 | TIR1704 |  | 515 | Display status: HC 1-SWD1 half blank | Low
2022-05-09 | TIR1705 |  | 515 | HC2- Near to Door no.6 bottom cover found loose fitting | Low
2022-05-10 | TIR1713 |  | 505 | HC1-LCD.6 cover fitting found loose | Low
2022-05-12 | TIR1728 |  | 509 | cuple train (509&519) EB not relase during cuple with other train , I check modification wiring there is no issue. | Low
2022-05-15 | TIR10001 |  | 506 | IOS252 : One ATC have a communication fault | Medium
2022-05-15 | TIR10003 |  | 509 | HC2-HVAC1 All Compressors have Noise/vibration | Low
2022-05-15 | TIR10004 |  | 519 | HC2-HVAC2 compressor 3 &4 not started to run due to Gas level low LP2 | High
2022-05-17 | TIR10006 |  | 502 | HC2- Family class Fire extingusier holding belt Missing | Low
2022-05-17 | TIR10007 |  | 512 | HC2-Right side Flange Lubricator's saftey pin missing | Low
2022-05-22 | TIR10014 |  | 517 | HC2-Bogie2 Left side Collector shoe tilded- [Refer Picture] | Low
2022-05-22 | TIR10015 |  | 517 | HC2-Sand level is low | Low
2022-05-22 | TIR10016 |  | 518 | IP offline: HC1- HVAC2 IOS250 : One HVAC have a communication fault | Low
2022-05-22 | TIR10017 |  | 504 | HC2-Bogie1 Right 1 Collector shoe tilted (as Picture Shown) | Low
2022-05-24 | TIR10020 |  | 505 | HC1-LHS ESG Tail Light Red one LED not Lit | Low
2022-05-24 | TIR10021 |  | 509 | HC1-Bogie1 oil Leakage from Gasket S.No .392 | Low
2022-05-24 | TIR10022 |  | 519 | HC1-B2-(S.No. 472) found minor leakage from Gasket | Low
2022-05-24 | TIR10024 |  | 507 | SWD4-V1 & LEDI4-V1 Offline in IP scanner. | Low
2022-05-24 | TIR10025 |  | 508 | Ledi4-V1 & Swd2-V1 offline in IP scanner. | Low
2022-05-24 | TIR10027 |  | 501 | Following devices are offline ,Papis.pa2,Swd1-v1,Swd4-v1 | Low
2022-05-30 | TIR10032 |  | 514 | HC1( PECD Connected) - All Doors are getting closed immediately(with Alarm ) without delay timing. | Low
2022-05-31 | TIR10033 |  | 502 | There is No alarm/buzzer sound during door closing/opening from both HC | Low
2022-05-31 | TIR10034 |  | 512 | Display Status: HC2-Ledi6 Nok Blank | Low
2022-06-01 | TIR10036 |  | 513 | HC1-HVAC1 All compressor observed much noise | Low
2022-06-02 | TIR10039 |  | 517 | LCD3_V2 cover loosing | Low
2022-06-05 | TIR10040 |  | 507 | HC1- Ledi2,lcd2,swd2 IP offline | Low
2022-06-05 | TIR10041 |  | 507 | HC1-SWD5 Half green screen | Low
2022-06-06 | TIR10042 |  | 508 | HC1-Ledi2 IP offline | Low
2022-06-06 | TIR10044 |  | 504 | HC2- Bogie 1- Right side CC shoe Damaged and CC armed bended | Medium
2022-06-07 | TIR10045 |  | 505 | HC1- Hvac1 All compressor Noise(abnormal sound) | Low
2022-06-08 | TIR10046 |  | 514 | Reported by T&C: Closing Prewarning Delay (five seconds) not implemented for all doors | Low
2022-06-08 | TIR10047 |  | 515 | Reported by T&C:Closing Prewarning Delay (five seconds) not implemented for all doors | Low
2022-06-09 | TIR10050 |  | 504 | LCD1_V1 cover is loosing | Low
2022-06-13 | TIR10053 |  | 502 | HC1- Bogie 1- Left side CC shoe minor damaged and CC armed bended | Low
2022-06-13 | TIR10054 |  | 516 | HC2- Bogie 1- Right side CC shoe damaged and CC armed bended | Low
2022-06-13 | TIR10055 |  | 514 | HC1- Bogie 1- Left side CC shoe damaged | Low
2022-06-13 | TIR10056 |  | 514 | HC 1 - BCE 1 & BCE 2 - Cover missing; HC 2 - BCE 1 & BCE 2 - Cover missing | Low
2022-06-13 | TIR10057 |  | 516 | HC2- Bogie 2- Right side CC shoe damaged | Low
2022-06-13 | TIR10058 |  | 516 | HC2- BCE 2 - Cover missing | Low
2022-06-13 | TIR10060 |  | 516 | HC2-BOGIE1 AXLE1 Right Side corrossion | Low
2022-06-13 | TIR10061 |  | 502 | SWD2_V1 shown NOK | Low
2022-06-13 | TIR10063 |  | 504 | Gangway side panel cover - Side panel sheet rubber skirts damaged | Low
2022-06-13 | TIR10064 |  | 514 | HC1 & HC2 - Cabin seal between window & interior cover fragile | Low
2022-06-13 | TIR10065 |  | 514 | HC1 & HC2 - CCC Cover rubber seal peel off | Low
2022-06-13 | TIR10066 |  | 514 | HC2 - Internal door not smooth | Low
2022-06-14 | TIR10068 |  | 502 | HC2-Ledi1,Lcd1 IP offline | Low
2022-06-16 | TIR10070 |  | 513 | CRS issue [VS4/V2,BCE2,EVR,PEI.1,3,5/V2;LEDI6/V1;LEDI1/V2,LEDI3/V2,LEDI5/V2,LCD6/V1,LCD1/V2,LCD3/V2,LCD5/V2,SWD6/V1,SWD1,2,3,5/V2;CAMI2,3/V2]-IP offline.IOS196 : Loss of at least 1 PEI in a class | High
2022-06-16 | TIR10071 |  | 503 | HC1- Bogie 1- Left side CC shoe minor damaged | Low
2022-06-16 | TIR10072 |  | 503 | HC2- Bogie 2- Right side CC shoe minor damaged /chipped | Low
2022-06-16 | TIR10073 |  | 503 | HC1- Bogie 2- Left side CC shoe minor damaged /chipped | Low
2022-06-16 | TIR10074 |  | 503 | HC1- Bogie 2- Right side CC shoe damaged | Low
2022-06-16 | TIR10075 |  | 503 | HC2- Bogie 1- Right side CC shoe minor damaged | Low
2022-06-16 | TIR10076 |  | 517 | HC2- Bogie 2- Right side CC shoe gap | Low
2022-06-16 | TIR10077 |  | 517 | HC2- Bogie 1- Right side CC shoe minor damaged | Low
2022-06-16 | TIR10078 |  | 517 | HC1- Bogie 2- Right side CC shoe damaged | Low
2022-06-19 | TIR10079 |  | 504 | HC2-PEI.5-IP offline.IOS196 : Loss of at least 1 PEI in a class | Low
2022-06-19 | TIR10080 |  | 507 | HC2-Ledi6,Lcd6,swd6 -IP offline | Low
2022-06-19 | TIR10081 |  | 508 | HC1- Bogie 1- Left side CC shoe damaged | Low
2022-06-19 | TIR10082 |  | 513 | HC1- Bogie 2- Right side CC shoe damaged | Low
2022-06-21 | TIR10084 |  | 501 | NVR 4 screws are missing | Low
2022-06-22 | TIR10085 |  | 505 | HC1-HVAC1 LP1&2 Gas - Low Level | Low
2022-06-26 | TIR10087 |  | 505 | HC2- Bogie 1- Right side CC shoe damaged | Low
2022-06-26 | TIR10088 |  | 506 | HC1- Bogie 2- Left side CC shoe minor damaged | Low
2022-06-26 | TIR10089 |  | 506 | HC2- Bogie 1- Right side CC shoe minor damaged | Low
2022-06-26 | TIR10090 |  | 510 | HC2- Bogie 1- Right side CC shoe minor damaged | Low
2022-06-26 | TIR10091 |  | 519 | HC2- Bogie 1- Right side CC shoe damaged | Low
2022-06-26 | TIR10092 |  | 515 | HC2- Bogie 1- Right side CC shoe damaged | Low
2022-06-26 | TIR10093 |  | 515 | HC1_Bogie 1_Right Side_Service brake extra 1 breather (SN : M15 6003) | Low
2022-06-26 | TIR10094 |  | 515 | HC1_Bogie 1_Right Side_Parking brake missing 1 breather (SN : M15 6004) | Low
2022-06-26 | TIR10095 |  | 515 | HC1_Bogie 1_Left Side_Service brake extra 1 breather (SN : M15 6004) | Low
2022-06-26 | TIR10096 |  | 515 | HC1_Bogie 1_Left Side_Parking brake missing 1 breather (SN : M15 6003) | Low
2022-06-27 | TIR10097 |  | 514 | IOS247 : One ACE have a communication fault-ACE2 0.0.0; ACE2/V2- IP offline | Medium
2022-06-29 | TIR10099 |  | 502 | HC2-swd1 offline | Low
2022-06-29 | TIR10100 |  | 502 | HC1 &HC2-Gangway Light and Cabin Light brightness not change | Low
2022-06-29 | TIR10101 |  | 518 | Palm tree black cover 1&2 of HC2 loose partially | Low
2022-07-04 | TIR10106 |  | 513 | Palm tree black cover 1 of HC2 loose partially | Low
2022-07-06 | TIR10107 |  | 505 | HC2- EB Malfunction( When EB applied HSCB opened but CVS working remaining )abnormal | Low
2022-07-06 | TIR10108 |  | 505 | HC1- Palm1 Light brightness Dim/flicker | Low
2022-07-07 | TIR10109 |  | 511 | HC2 Under seat Light Not working in single class | Low
2022-07-07 | TIR10110 |  | 511 | HC2-LCD2 Blank | Low
2022-07-17 | TIR10111 |  | 506 | HC1-Right side derailment sensor's ground cable is cutted | Low
2022-07-17 | TIR10112 |  | 514 | HC2-LEDI3 Blurring data | Low
2022-07-17 | TIR10113 |  | 514 | IOS 274 : Communication Loss of CRS 2/V1 Not getting Power ON after wakeup the train then become ON{ Malfunction } | Low
2022-07-17 | TIR10114 |  | 516 | Auto Test fail-VAC RED;HC2/HVAC1 Controller Nok _Not Running ; All Hvac has Venting error Supply fan 1,2 with Low and high | Low
2022-07-17 | TIR10115 |  | 516 | HC1-Ledi3 Blurring data | Low
2022-07-20 | TIR10116 |  | 501 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10117 |  | 502 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10118 |  | 502 | HC2_Gear box 4 oil leakage from the drainage plug | Low
2022-07-20 | TIR10119 |  | 503 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10120 |  | 511 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10121 |  | 512 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10122 |  | 514 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10123 |  | 516 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10124 |  | 512 | Both HC1 and HC2 cab interior saloon light brightness not change to DIM(using PECD complementry light activate/deactivate) | Low
| RETR0002 | CMR0500 | 501 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0501 | 502 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0502 | 503 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0503 | 504 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0504 | 505 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0505 | 506 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0506 | 507 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0507 | 508 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0508 | 509 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0509 | 510 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0510 | 511 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0511 | 512 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0512 | 513 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0513 | 514 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0514 | 515 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0515 | 516 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0516 | 517 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0517 | 518 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0518 | 519 | CVS AGATE Retrofitted | Low
| RETR0003 | CMR0569 | 501 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0570 | 502 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0571 | 503 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0572 | 504 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0573 | 505 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0574 | 506 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0575 | 507 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0576 | 508 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0577 | 509 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0578 | 510 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0579 | 511 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0580 | 512 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0581 | 513 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0582 | 514 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0583 | 515 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0584 | 516 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0585 | 517 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0586 | 518 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0587 | 519 | PCE AGATE Retrofitted | Low
| RETR0011 | CMR0776 | 501 | Battery tray connector | Low
| RETR0011 | CMR0777 | 502 | Battery tray connector | Low
| RETR0011 | CMR0778 | 503 | Battery tray connector | Low
| RETR0011 | CMR0779 | 504 | Battery tray connector | Low
| RETR0011 | CMR0780 | 505 | Battery tray connector | Low
| RETR0011 | CMR0781 | 506 | Battery tray connector | Low
| RETR0011 | CMR0782 | 507 | Battery tray connector | Low
| RETR0011 | CMR0783 | 508 | Battery tray connector | Low
| RETR0011 | CMR0784 | 509 | Battery tray connector | Low
| RETR0011 | CMR0785 | 510 | Battery tray connector | Low
| RETR0011 | CMR0786 | 511 | Battery tray connector | Low
| RETR0011 | CMR0787 | 512 | Battery tray connector | Low
| RETR0011 | CMR0788 | 513 | Battery tray connector | Low
| RETR0011 | CMR0789 | 514 | Battery tray connector | Low
| RETR0011 | CMR0790 | 515 | Battery tray connector | Low
| RETR0011 | CMR0791 | 516 | Battery tray connector | Low
| RETR0011 | CMR0792 | 517 | Battery tray connector | Low
| RETR0011 | CMR0793 | 518 | Battery tray connector | Low
| RETR0011 | CMR0794 | 519 | Battery tray connector | Low
2022-06-19 | SU0019 | CMS10019 | 501 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10020 | 502 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10021 | 503 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10022 | 504 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10023 | 505 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10024 | 506 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10025 | 507 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10026 | 508 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10027 | 509 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10028 | 510 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10029 | 511 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10030 | 512 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10031 | 513 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10032 | 514 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10033 | 515 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10034 | 516 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10035 | 517 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10036 | 518 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10037 | 519 | Smoke detector SRN1194B | Low
2022-07-06 | SU0022 | CMS10038 | 501 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10042 | 505 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10043 | 506 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10045 | 508 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10047 | 510 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10048 | 511 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10052 | 515 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0023 | CMS10057 | 501 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10061 | 505 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10062 | 506 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10064 | 508 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10066 | 510 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10067 | 511 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10071 | 515 | BRAKE SW V1.02 | High

## availabilityCHK
21/7/2022
Open Date | Doc Ref | CM Ref |  | TRAIN | Description | IMPACT | Progress
2021-09-21 | TIR0033 |  | 515Low | 515 | HC2 Bogie2 Left Fuse box glass minor cracked | Low
2021-09-21 | TIR1014 |  | 506Low | 506 | IP Offline - HC2 {Ledi1, Lcd3, Lcd4} Display Status - HC2 { (Ledi1-White)(Lcd3-Nok)(Lcd4-Dim) | Low
2021-09-26 | TIR1016 |  | 508Low | 508 | IP Offline and Display also NOK { Ledi4-V1, Swd2-V1 } | Low
2021-09-26 | TIR1017 |  | 509Low | 509 | Display Status { Ledi4-V2 - NOK } | Low
2021-09-26 | TIR1019 |  | 519Medium | 519 | HVAC2-V2 Low Pressure 1 NOK ( Compressor 1&2 ) | Medium
2021-12-06 | TIR0161 |  | 503Low | 503 | HC1 Bogie2 Right- Fuse box glass minor cracked. | Low
2021-12-06 | TIR0164 |  | 502Low | 502 | Sanding rubber hoses missing - 4 nos, clamp - 4pcs. (RIY 000000370) | Low
2021-12-08 | TIR0198 |  | 502Low | 502 | HC2 Axle 4 found minor leakage from the gearbox. | Low
2021-12-08 | TIR0199 |  | 502Low | 502 | Sand hose not available in both HC. | Low
2021-12-09 | TIR0207 |  | 512Low | 512 | HC2- Head Light Nok(LHS 1 white LED not lit) | Low
2021-12-13 | TIR0229 |  | 515Low | 515 | HC1-flange lubricator saftey pin missing | Low
2021-12-15 | TIR1034 |  | 519Low | 519 | HC2-B2-Axle3 found minor leakage | Low
2021-12-26 | TIR1046 |  | 517Low | 517 | HC2-B2 -Axle4 minor leakge from top door of gearbox.(GASKET )-s.no C484 | Low
2021-12-28 | TIR0325 |  | 504Low | 504 | Gangway Panel has scractch &Lock missing | Low
2021-12-28 | TIR0326 |  | 507Low | 507 | CCD to JB_ HV cable support clamp missing,HC1_bogie2 Left,HC2-Bogie1,2-Right | Low
2021-12-28 | TIR1051 |  | 505Low | 505 | HC1-HVAC1_compressor2 Loud noise | Low
2021-12-28 | TIR1052 |  | 505Low | 505 | HC1-swd.4-Half broken ,Ledi4-blank | Low
2021-12-29 | TIR0336 |  | 501Low | 501 | HC2- Bogie1 left side derailment sensor cable clamp missing | Low
2021-12-30 | TIR1068 |  | 511Low | 511 | Gangway 2 Lock Nok | Low
2022-01-02 | TIR1069 |  | 516Low | 516 | Gangway Panel Lock 3 no.s Nok | Low
2022-01-03 | TIR1087 |  | 502Low | 502 | Gangway 1 lock is broken | Low
2022-01-03 | TIR1088 |  | 512Low | 512 | Gangway 1 lock is broken | Low
2022-01-05 | TIR1104 |  | 517Low | 517 | HC1-B1 -Axle2 minor leakge from top door of gear box .(GASKET )-s.no C447 | Low
2022-01-06 | TIR1113 |  | 507Low | 507 | HC1-HVAC1-compressor 1&3 making noise | Low
2022-01-09 | TIR1124 |  | 515Low | 515 | HC1-becon Antenna Cable's clamp missing | Low
2022-01-10 | TIR1135 |  | 510Low | 510 | Flange Lubricator saftey pin1 missing | Low
2022-01-10 | TIR1136 |  | 510Low | 510 | Gangway lock has an issue | Low
2022-01-10 | TIR1137 |  | 505Low | 505 | Hc1-becon Antenna Cable's clamp one screw is missing(refer picture in TIR report) | Low
2022-01-11 | TIR1141 |  | 502Low | 502 | Gearbox oil leakage | Low
2022-01-16 | TIR1151 |  | 519Low | 519 | HC2-Sand reserviour is empty | Low
2022-01-17 | TIR1155 |  | 501Low | 501 | Primary suspension's bottom cover -8 nos.(Refer picture) | Low
2022-01-17 | TIR1157 |  | 506Low | 506 | Primary suspension's bottom cover -8 nos.(Refer picture) | Low
2022-01-17 | TIR1158 |  | 506Low | 506 | HC1-Flange Lubricator saftey pin missing | Low
2022-01-17 | TIR1159 |  | 511Low | 511 | Primary suspension's bottom cover -8 nos.(Refer picture) | Low
2022-01-18 | TIR1176 |  | 514Low | 514 | Hc2-Sand Level Low | Low
2022-01-19 | TIR1187 |  | 514Low | 514 | when the train is correctly docked and PEED of the door towards the track is applied and the train driving mood is switched from ATPM to UTO the door towards the track opens (less than 2.5 cm) and closes immediately. o When the door opening alarm is triggered by ATC area securing zone is applied. o Issue is observed only on the mainline. | Low
2022-02-01 | TIR1208 |  | 516Low | 516 | HC1-HVAC1-Compressor 3 Noise | Low
2022-02-01 | TIR1209 |  | 512Low | 512 | Hc1-First class passenger saloon light in reverse brightness | Low
2022-02-01 | TIR1210 |  | 512Low | 512 | Hc1-First class passenger saloon light in reverse brightness | Low
2022-02-06 | TIR1220 |  | 517Low | 517 | HC1-Stinger 750vdc Power connector female broken(Refer Pic) | Low
2022-02-06 | TIR1221 |  | 517Low | 517 | HC1-Bogie1 left side Fuse box -JB cable clamp missing(Refer Pic) | Low
2022-02-06 | TIR1222 |  | 518Low | 518 | HC1- Becon Antenna cable stressed due to unfit bracket installed | Low
2022-02-06 | TIR1223 |  | 518Low | 518 | HC1-HVAC1/LP2 Low level ;HC2-HVAC1/LP2 Low Level | Low
2022-02-08 | TIR1246 |  | 515Low | 515 | Hc2- Both Derailment sensor and earth cable clamp missing | Low
2022-02-10 | TIR1264 |  | 505Low | 505 | Gangway internal Panel has minor scratch | Low
2022-02-10 | TIR1265 |  | 510Low | 510 | HC1-HVAC2 LP2 Gas level Low | Low
2022-02-11 | TIR1277 |  | 506Low | 506 | Interglass door function - not open/close fully | Low
2022-02-14 | TIR1286 |  | 514Low | 514 | HC1-lcd3 offline; HC1-Lcd.3 BLANK,HC2 Lcd3 Dim | Low
2022-02-14 | TIR1288 |  | 516Low | 516 | HC2-SWD 3 offline;HC2 -SWD.3 Half blank,half error message | Low
2022-02-15 | TIR1293 |  | 502Low | 502 | HC1-Ledi.6;HC2-Ledi3,Lcd3,Swd3 offline [HC1-Ledi.6-software not up-to-date ,HC2 -Ledi3 Error message] | Low
2022-02-15 | TIR1294 |  | 512Low | 512 | HC1-Ledi.6;HC2-Ledi3,Lcd3,Swd3 offline [HC1-Ledi.6-software not up-to-date ,HC2 -Ledi3 Error message] | Low
2022-02-16 | TIR1304 |  | 503Low | 503 | IP Offline: HC1- All Ledi-V1; HC2- All Ledi-V1, Lcd5-V2 PAPIS Display Visual Status: HC1 & HC2- All Ledi Error Message; HC2-Lcd 2 & 5 Blank IOS199 : Loss of all interior LCD compact displays in the same platform | Low
2022-02-16 | TIR1305 |  | 503Low | 503 | Partition Door not closing fully | Low
2022-02-16 | TIR1306 |  | 503Low | 503 | IP Offline: HC1- All Ledi-V1; HC2- All Ledi-V1, Lcd5-V2 PAPIS Display Visual Status: HC1:LCD2,LEDI3-Nok; SWD3 Half display with error message; SWD5 Half display HC2:LEDI2 Nok SW Not Up-To-Date- | Low
2022-02-17 | TIR1308 |  | 503Low | 503 | Partition Door not closing fully | Low
2022-02-17 | TIR1316 |  | 517Low | 517 | HVAC1-V1 gas level Low pressure 1 & 2 | Low
2022-02-17 | TIR1317 |  | 518Medium | 518 | IP Offline: Dcu2-v2 IOS262 : More than one DCU have a communication fault. | Medium
2022-02-17 | TIR1318 |  | 518Low | 518 | HC1-HVAC1 Compressor1,2,3&4 are Noisy. | Low
2022-02-20 | TIR1321 |  | 503Low | 503 | IOS199+ IOS196 | Low
2022-02-21 | TIR1328 |  | 504Low | 504 | IP scanner : HC1: Lcd1, Swd4, Ledi 1,2,3,4&6; Hc2: Swd3, Ledi 1,2,3,4,5 & 6- Offline ; PAPIS Display Visual Status : HC1: Lcd1- SW not UP-TO-DATE ; Swd4- Nok Black; Ledi 1,2,3,4&6- Error message; Hc2: Swd3-Nok Black Ledi 1,2,3,4,5 & 6- Error Message; IOS199 : Loss of all interior LCD compact displays in the same platform | Low
2022-02-21 | TIR1330 |  | 507Low | 507 | IP scanner : HC1-swd4; Hc2-Ledi3,Lcd3,Pei3,swd3- Offline; PAPIS Display Visual Status : SWD3-V1 half blank, SWD4-V1 black IOS196 : Loss of at least 1 PEI in a class | Low
2022-03-23 | TIR1475 |  | 509Low | 509 | software version : UMC2 0.0.0;IOS251 : One MUC have a communication fault ; Display Status: HC1-SWD4 blank; HC2-SWD5-Half blank | Low
2022-03-24 | TIR1484 |  | 504Low | 504 | IOS199 : Loss of all interior LCD compact displays in the same platform | Low
2022-03-25 | TIR1489 |  | 501Low | 501 | IP offline-Papis Pa2,Hc1-SWD1 | Low
2022-03-25 | TIR1490 |  | 506Low | 506 | HC2-HVAC1 All compressors Noise observed | Low
2022-03-30 | TIR1518 |  | 513Low | 513 | IP offline-HC1-Ledi3,swd3, HC2 -Ledi2; Display status: HC1:LEDI3-Nok BLANK; SWD3 Half display with error message; SWD5 Half display,HC2:LEDI2 Nok SW Not Up-to date | Low
2022-03-30 | TIR1519 |  | 513Low | 513 | GCL-saloon light off | Low
2022-04-13 | TIR1588 |  | 510Low | 510 | low oil level gearbox C310 Hc2 | Low
2022-04-13 | TIR1589 |  | 505Low | 505 | SWD5 has an unfunctional spot | Low
2022-04-13 | TIR1592 |  | 509Low | 509 | Low oil level for gear box Hc2 Axle4 | Low
2022-04-14 | TIR1627 |  | 504Low | 504 | Deep scratch HC1 door 1, side panel. | Low
2022-04-14 | TIR1634 |  | 517Low | 517 | HC2-DCR_EB Push Button dosent hold when pressed | Low
2022-04-14 | TIR1635 |  | 518Low | 518 | IP offline -(Papis Pa1,HC2-Pei3,Cami2};IOS192 : Loss of at least one camera;IOS196 : Loss of at least 1 PEI in a class | Low
2022-04-14 | TIR1636 |  | 518Low | 518 | HC1-Door1,2 close immediately and intailly both DCU goes to offline after reset DCU then become online | Low
2022-04-20 | TIR1658 |  | 519Low | 519 | HC1- Horn Volume Low | Low
2022-04-21 | TIR1665 |  | 519Low | 519 | HC2- CVS bottom Filter cover alen screw Missing=1 no. | Low
2022-04-26 | TIR1682 |  | 502Low | 502 | IP Offline- HC1-LCD5 ; Display Status - HC1-LCD5 Error message ;HC2 -LCD5 BLANK,SWD1 BLANK | Low
2022-05-08 | TIR1694 |  | 504Low | 504 | IOS91 : ONE LMRG Bypass active on unit .Active in HC2 via PECD and found Bypass switch is Normal so Need to be further check. | Low
2022-05-09 | TIR1703 |  | 515Low | 515 | HC1,HC2: Sand Level Low | Low
2022-05-09 | TIR1704 |  | 515Low | 515 | Display status: HC 1-SWD1 half blank | Low
2022-05-09 | TIR1705 |  | 515Low | 515 | HC2- Near to Door no.6 bottom cover found loose fitting | Low
2022-05-10 | TIR1713 |  | 505Low | 505 | HC1-LCD.6 cover fitting found loose | Low
2022-05-12 | TIR1728 |  | 509Low | 509 | cuple train (509&519) EB not relase during cuple with other train , I check modification wiring there is no issue. | Low
2022-05-15 | TIR10001 |  | 506Medium | 506 | IOS252 : One ATC have a communication fault | Medium
2022-05-15 | TIR10003 |  | 509Low | 509 | HC2-HVAC1 All Compressors have Noise/vibration | Low
2022-05-15 | TIR10004 |  | 519High | 519 | HC2-HVAC2 compressor 3 &4 not started to run due to Gas level low LP2 | High
2022-05-17 | TIR10006 |  | 502Low | 502 | HC2- Family class Fire extingusier holding belt Missing | Low
2022-05-17 | TIR10007 |  | 512Low | 512 | HC2-Right side Flange Lubricator's saftey pin missing | Low
2022-05-22 | TIR10014 |  | 517Low | 517 | HC2-Bogie2 Left side Collector shoe tilded- [Refer Picture] | Low
2022-05-22 | TIR10015 |  | 517Low | 517 | HC2-Sand level is low | Low
2022-05-22 | TIR10016 |  | 518Low | 518 | IP offline: HC1- HVAC2 IOS250 : One HVAC have a communication fault | Low
2022-05-22 | TIR10017 |  | 504Low | 504 | HC2-Bogie1 Right 1 Collector shoe tilted (as Picture Shown) | Low
2022-05-24 | TIR10020 |  | 505Low | 505 | HC1-LHS ESG Tail Light Red one LED not Lit | Low
2022-05-24 | TIR10021 |  | 509Low | 509 | HC1-Bogie1 oil Leakage from Gasket S.No .392 | Low
2022-05-24 | TIR10022 |  | 519Low | 519 | HC1-B2-(S.No. 472) found minor leakage from Gasket | Low
2022-05-24 | TIR10024 |  | 507Low | 507 | SWD4-V1 & LEDI4-V1 Offline in IP scanner. | Low
2022-05-24 | TIR10025 |  | 508Low | 508 | Ledi4-V1 & Swd2-V1 offline in IP scanner. | Low
2022-05-24 | TIR10027 |  | 501Low | 501 | Following devices are offline ,Papis.pa2,Swd1-v1,Swd4-v1 | Low
2022-05-30 | TIR10032 |  | 514Low | 514 | HC1( PECD Connected) - All Doors are getting closed immediately(with Alarm ) without delay timing. | Low
2022-05-31 | TIR10033 |  | 502Low | 502 | There is No alarm/buzzer sound during door closing/opening from both HC | Low
2022-05-31 | TIR10034 |  | 512Low | 512 | Display Status: HC2-Ledi6 Nok Blank | Low
2022-06-01 | TIR10036 |  | 513Low | 513 | HC1-HVAC1 All compressor observed much noise | Low
2022-06-02 | TIR10039 |  | 517Low | 517 | LCD3_V2 cover loosing | Low
2022-06-05 | TIR10040 |  | 507Low | 507 | HC1- Ledi2,lcd2,swd2 IP offline | Low
2022-06-05 | TIR10041 |  | 507Low | 507 | HC1-SWD5 Half green screen | Low
2022-06-06 | TIR10042 |  | 508Low | 508 | HC1-Ledi2 IP offline | Low
2022-06-06 | TIR10044 |  | 504Medium | 504 | HC2- Bogie 1- Right side CC shoe Damaged and CC armed bended | Medium
2022-06-07 | TIR10045 |  | 505Low | 505 | HC1- Hvac1 All compressor Noise(abnormal sound) | Low
2022-06-08 | TIR10046 |  | 514Low | 514 | Reported by T&C: Closing Prewarning Delay (five seconds) not implemented for all doors | Low
2022-06-08 | TIR10047 |  | 515Low | 515 | Reported by T&C:Closing Prewarning Delay (five seconds) not implemented for all doors | Low
2022-06-09 | TIR10050 |  | 504Low | 504 | LCD1_V1 cover is loosing | Low
2022-06-13 | TIR10053 |  | 502Low | 502 | HC1- Bogie 1- Left side CC shoe minor damaged and CC armed bended | Low
2022-06-13 | TIR10054 |  | 516Low | 516 | HC2- Bogie 1- Right side CC shoe damaged and CC armed bended | Low
2022-06-13 | TIR10055 |  | 514Low | 514 | HC1- Bogie 1- Left side CC shoe damaged | Low
2022-06-13 | TIR10056 |  | 514Low | 514 | HC 1 - BCE 1 & BCE 2 - Cover missing; HC 2 - BCE 1 & BCE 2 - Cover missing | Low
2022-06-13 | TIR10057 |  | 516Low | 516 | HC2- Bogie 2- Right side CC shoe damaged | Low
2022-06-13 | TIR10058 |  | 516Low | 516 | HC2- BCE 2 - Cover missing | Low
2022-06-13 | TIR10060 |  | 516Low | 516 | HC2-BOGIE1 AXLE1 Right Side corrossion | Low
2022-06-13 | TIR10061 |  | 502Low | 502 | SWD2_V1 shown NOK | Low
2022-06-13 | TIR10063 |  | 504Low | 504 | Gangway side panel cover - Side panel sheet rubber skirts damaged | Low
2022-06-13 | TIR10064 |  | 514Low | 514 | HC1 & HC2 - Cabin seal between window & interior cover fragile | Low
2022-06-13 | TIR10065 |  | 514Low | 514 | HC1 & HC2 - CCC Cover rubber seal peel off | Low
2022-06-13 | TIR10066 |  | 514Low | 514 | HC2 - Internal door not smooth | Low
2022-06-14 | TIR10068 |  | 502Low | 502 | HC2-Ledi1,Lcd1 IP offline | Low
2022-06-16 | TIR10070 |  | 513High | 513 | CRS issue [VS4/V2,BCE2,EVR,PEI.1,3,5/V2;LEDI6/V1;LEDI1/V2,LEDI3/V2,LEDI5/V2,LCD6/V1,LCD1/V2,LCD3/V2,LCD5/V2,SWD6/V1,SWD1,2,3,5/V2;CAMI2,3/V2]-IP offline.IOS196 : Loss of at least 1 PEI in a class | High
2022-06-16 | TIR10071 |  | 503Low | 503 | HC1- Bogie 1- Left side CC shoe minor damaged | Low
2022-06-16 | TIR10072 |  | 503Low | 503 | HC2- Bogie 2- Right side CC shoe minor damaged /chipped | Low
2022-06-16 | TIR10073 |  | 503Low | 503 | HC1- Bogie 2- Left side CC shoe minor damaged /chipped | Low
2022-06-16 | TIR10074 |  | 503Low | 503 | HC1- Bogie 2- Right side CC shoe damaged | Low
2022-06-16 | TIR10075 |  | 503Low | 503 | HC2- Bogie 1- Right side CC shoe minor damaged | Low
2022-06-16 | TIR10076 |  | 517Low | 517 | HC2- Bogie 2- Right side CC shoe gap | Low
2022-06-16 | TIR10077 |  | 517Low | 517 | HC2- Bogie 1- Right side CC shoe minor damaged | Low
2022-06-16 | TIR10078 |  | 517Low | 517 | HC1- Bogie 2- Right side CC shoe damaged | Low
2022-06-19 | TIR10079 |  | 504Low | 504 | HC2-PEI.5-IP offline.IOS196 : Loss of at least 1 PEI in a class | Low
2022-06-19 | TIR10080 |  | 507Low | 507 | HC2-Ledi6,Lcd6,swd6 -IP offline | Low
2022-06-19 | TIR10081 |  | 508Low | 508 | HC1- Bogie 1- Left side CC shoe damaged | Low
2022-06-19 | TIR10082 |  | 513Low | 513 | HC1- Bogie 2- Right side CC shoe damaged | Low
2022-06-21 | TIR10084 |  | 501Low | 501 | NVR 4 screws are missing | Low
2022-06-22 | TIR10085 |  | 505Low | 505 | HC1-HVAC1 LP1&2 Gas - Low Level | Low
2022-06-26 | TIR10087 |  | 505Low | 505 | HC2- Bogie 1- Right side CC shoe damaged | Low
2022-06-26 | TIR10088 |  | 506Low | 506 | HC1- Bogie 2- Left side CC shoe minor damaged | Low
2022-06-26 | TIR10089 |  | 506Low | 506 | HC2- Bogie 1- Right side CC shoe minor damaged | Low
2022-06-26 | TIR10090 |  | 510Low | 510 | HC2- Bogie 1- Right side CC shoe minor damaged | Low
2022-06-26 | TIR10091 |  | 519Low | 519 | HC2- Bogie 1- Right side CC shoe damaged | Low
2022-06-26 | TIR10092 |  | 515Low | 515 | HC2- Bogie 1- Right side CC shoe damaged | Low
2022-06-26 | TIR10093 |  | 515Low | 515 | HC1_Bogie 1_Right Side_Service brake extra 1 breather (SN : M15 6003) | Low
2022-06-26 | TIR10094 |  | 515Low | 515 | HC1_Bogie 1_Right Side_Parking brake missing 1 breather (SN : M15 6004) | Low
2022-06-26 | TIR10095 |  | 515Low | 515 | HC1_Bogie 1_Left Side_Service brake extra 1 breather (SN : M15 6004) | Low
2022-06-26 | TIR10096 |  | 515Low | 515 | HC1_Bogie 1_Left Side_Parking brake missing 1 breather (SN : M15 6003) | Low
2022-06-27 | TIR10097 |  | 514Medium | 514 | IOS247 : One ACE have a communication fault-ACE2 0.0.0; ACE2/V2- IP offline | Medium
2022-06-29 | TIR10099 |  | 502Low | 502 | HC2-swd1 offline | Low
2022-06-29 | TIR10100 |  | 502Low | 502 | HC1 &HC2-Gangway Light and Cabin Light brightness not change | Low
2022-06-29 | TIR10101 |  | 518Low | 518 | Palm tree black cover 1&2 of HC2 loose partially | Low
2022-07-04 | TIR10106 |  | 513Low | 513 | Palm tree black cover 1 of HC2 loose partially | Low
2022-07-06 | TIR10107 |  | 505Low | 505 | HC2- EB Malfunction( When EB applied HSCB opened but CVS working remaining )abnormal | Low
2022-07-06 | TIR10108 |  | 505Low | 505 | HC1- Palm1 Light brightness Dim/flicker | Low
2022-07-07 | TIR10109 |  | 511Low | 511 | HC2 Under seat Light Not working in single class | Low
2022-07-07 | TIR10110 |  | 511Low | 511 | HC2-LCD2 Blank | Low
2022-07-17 | TIR10111 |  | 506Low | 506 | HC1-Right side derailment sensor's ground cable is cutted | Low
2022-07-17 | TIR10112 |  | 514Low | 514 | HC2-LEDI3 Blurring data | Low
2022-07-17 | TIR10113 |  | 514Low | 514 | IOS 274 : Communication Loss of CRS 2/V1 Not getting Power ON after wakeup the train then become ON{ Malfunction } | Low
2022-07-17 | TIR10114 |  | 516Low | 516 | Auto Test fail-VAC RED;HC2/HVAC1 Controller Nok _Not Running ; All Hvac has Venting error Supply fan 1,2 with Low and high | Low
2022-07-17 | TIR10115 |  | 516Low | 516 | HC1-Ledi3 Blurring data | Low
2022-07-20 | TIR10116 |  | 501Low | 501 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10117 |  | 502Low | 502 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10118 |  | 502Low | 502 | HC2_Gear box 4 oil leakage from the drainage plug | Low
2022-07-20 | TIR10119 |  | 503Low | 503 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10120 |  | 511Low | 511 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10121 |  | 512Low | 512 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10122 |  | 514Low | 514 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10123 |  | 516Low | 516 | Frontal HC1&HC2 Exterior body need polish | Low
2022-07-20 | TIR10124 |  | 512Low | 512 | Both HC1 and HC2 cab interior saloon light brightness not change to DIM(using PECD complementry light activate/deactivate) | Low
| RETR0002 | CMR0500 | 501Low | 501 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0501 | 502Low | 502 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0502 | 503Low | 503 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0503 | 504Low | 504 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0504 | 505Low | 505 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0505 | 506Low | 506 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0506 | 507Low | 507 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0507 | 508Low | 508 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0508 | 509Low | 509 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0509 | 510Low | 510 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0510 | 511Low | 511 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0511 | 512Low | 512 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0512 | 513Low | 513 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0513 | 514Low | 514 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0514 | 515Low | 515 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0515 | 516Low | 516 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0516 | 517Low | 517 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0517 | 518Low | 518 | CVS AGATE Retrofitted | Low
| RETR0002 | CMR0518 | 519Low | 519 | CVS AGATE Retrofitted | Low
| RETR0003 | CMR0569 | 501Low | 501 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0570 | 502Low | 502 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0571 | 503Low | 503 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0572 | 504Low | 504 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0573 | 505Low | 505 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0574 | 506Low | 506 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0575 | 507Low | 507 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0576 | 508Low | 508 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0577 | 509Low | 509 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0578 | 510Low | 510 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0579 | 511Low | 511 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0580 | 512Low | 512 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0581 | 513Low | 513 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0582 | 514Low | 514 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0583 | 515Low | 515 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0584 | 516Low | 516 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0585 | 517Low | 517 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0586 | 518Low | 518 | PCE AGATE Retrofitted | Low
| RETR0003 | CMR0587 | 519Low | 519 | PCE AGATE Retrofitted | Low
| RETR0011 | CMR0776 | 501Low | 501 | Battery tray connector | Low
| RETR0011 | CMR0777 | 502Low | 502 | Battery tray connector | Low
| RETR0011 | CMR0778 | 503Low | 503 | Battery tray connector | Low
| RETR0011 | CMR0779 | 504Low | 504 | Battery tray connector | Low
| RETR0011 | CMR0780 | 505Low | 505 | Battery tray connector | Low
| RETR0011 | CMR0781 | 506Low | 506 | Battery tray connector | Low
| RETR0011 | CMR0782 | 507Low | 507 | Battery tray connector | Low
| RETR0011 | CMR0783 | 508Low | 508 | Battery tray connector | Low
| RETR0011 | CMR0784 | 509Low | 509 | Battery tray connector | Low
| RETR0011 | CMR0785 | 510Low | 510 | Battery tray connector | Low
| RETR0011 | CMR0786 | 511Low | 511 | Battery tray connector | Low
| RETR0011 | CMR0787 | 512Low | 512 | Battery tray connector | Low
| RETR0011 | CMR0788 | 513Low | 513 | Battery tray connector | Low
| RETR0011 | CMR0789 | 514Low | 514 | Battery tray connector | Low
| RETR0011 | CMR0790 | 515Low | 515 | Battery tray connector | Low
| RETR0011 | CMR0791 | 516Low | 516 | Battery tray connector | Low
| RETR0011 | CMR0792 | 517Low | 517 | Battery tray connector | Low
| RETR0011 | CMR0793 | 518Low | 518 | Battery tray connector | Low
| RETR0011 | CMR0794 | 519Low | 519 | Battery tray connector | Low
2022-06-19 | SU0019 | CMS10019 | 501Low | 501 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10020 | 502Low | 502 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10021 | 503Low | 503 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10022 | 504Low | 504 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10023 | 505Low | 505 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10024 | 506Low | 506 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10025 | 507Low | 507 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10026 | 508Low | 508 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10027 | 509Low | 509 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10028 | 510Low | 510 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10029 | 511Low | 511 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10030 | 512Low | 512 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10031 | 513Low | 513 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10032 | 514Low | 514 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10033 | 515Low | 515 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10034 | 516Low | 516 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10035 | 517Low | 517 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10036 | 518Low | 518 | Smoke detector SRN1194B | Low
2022-06-19 | SU0019 | CMS10037 | 519Low | 519 | Smoke detector SRN1194B | Low
2022-07-06 | SU0022 | CMS10038 | 501High | 501 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10042 | 505High | 505 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10043 | 506High | 506 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10045 | 508High | 508 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10047 | 510High | 510 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10048 | 511High | 511 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0022 | CMS10052 | 515High | 515 | Riyadh Traction software V1.1.6 | High
2022-07-06 | SU0023 | CMS10057 | 501High | 501 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10061 | 505High | 505 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10062 | 506High | 506 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10064 | 508High | 508 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10066 | 510High | 510 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10067 | 511High | 511 | BRAKE SW V1.02 | High
2022-07-06 | SU0023 | CMS10071 | 515High | 515 | BRAKE SW V1.02 | High

## Sheet1
TRAIN | ACTIVITY TYPE | ACTIVITY REFERENCE | ACTIVITY DESCRIPTION | IMPACT | Status
606 | NCR | NCR0225 | Damaged train wipers | Low | Open
604 | NCR | NCR0226 | Damaged train wipers | Low | Open
416 | NCR | NCR0227 | Damaged train wipers | Low | Open
421 | NCR | NCR0341 | HVAC fault. | Low | Open
406 | NCR | NCR0342 | PEI lost communication | Medium | Open
512 | NCR | NCR0348 | HVAC compressor and ventilation fault | High | Open
418 | NCR | NCR0352 | Passenger door glass cracked | Low | Open
624 | NCR | NCR0353 | Scratches on T624 HC1 Door glass | Low | Open
411 | NCR | NCR0358 | Electrical coupler frame broken | Medium | Open
502 | NCR | NCR0360 | Sanding rubber hoses and clams missing | Low | Open
603 | NCR | NCR0361 | Beacon Antenna screws missing | Low | Open
603 | NCR | NCR0362 | Left side sanding hose not availabe | Low | Open
606 | NCR | NCR0372 | Gap filler between HVAC and Gangway missing | Low | Open
601 | NCR | NCR0375 | AGTU_Missing of Sand filter Assembly | Low | Open
601 | NCR | NCR0376 | leakage found from the spring brake part. | Low | Open
610 | NCR | NCR0377 | Head and Tail Light white LED not working | Low | Open
617 | NCR | NCR0378 | Head and Tail Light white LED not working | Low | Open
601 | NCR | NCR0381 | LCD & EDI error display | Low | Open
611 | NCR | NCR0382 | Axle Gearbox leakage | Low | Open
611 | NCR | NCR0383 | Head and Tail Light LED not working | Low | Open
417 | NCR | NCR0385 | Under seat fire extinguisher BOX and GCL fire Extinguisher bracket not available | Low | Open
626 | NCR | NCR0387 | LCD poor display issue | Low | Open
507 | NCR | NCR0389 | Under seat fire extinguisher BOX not available | Low | Open
404 | NCR | NCR0390 | fire extinguisher holding plate not available | Low | Open
404 | NCR | NCR0391 | Saloon light not working | Low | Open
612 | NCR | NCR0393 | LCD display issues | Low | Open
422 | NCR | NCR0394 | Door glass cracked | Low | Open
601 | NCR | NCR0395 | Saloon Light not working | Low | Open
623 | NCR | NCR0397 | Driver Cab Light not working | Low | Open
416 | NCR | NCR0401 | LCD display issues | Low | Open
603 | NCR | NCR0403 | Air leakage found from the spring brake part. | Low | Open
404 | NCR | NCR0405 | HV cable gland missing from the underframe Junction Box | Low | Open
623 | NCR | NCR0406 | stinger cap cover broken | Low | Open
606 | NCR | NCR0408 | Gangway Gap filler damaged | Low | Open
415 | NCR | NCR0414 | Earthing cable is not connected between permanent coupler | Low | Open
618 | NCR | NCR0417 | Earthing cable is not connected between permanent coupler | Low | Open
622 | NCR | NCR0418 | Earthing cable is not connected between permanent coupler | Low | Open
403 | NCR | NCR0420 | Axle Gearbox leakage | Low | Open
512 | NCR | NCR0422 | Head and Tail Light white LED not working | Low | Open
503 | NCR | NCR0425 | Gangway lights Dim,working inversely | Low | Open
413 | NCR | NCR0427 | Stick holding safety pin missing. | Low | Open
410 | NCR | NCR0428 | LCD dim display issue | Low | Open
503 | NCR | NCR0429 | Fuse box glass cracked. | Low | Open
501 | NCR | NCR0430 | DOOR indication light not working | Low | Open
515 | NCR | NCR0431 | Fuse box glass cracked. | Low | Open
508 | NCR | NCR0432 | STF-DL beacon Antenna : HC1 1 bolt ,HC2 2 bolt not available | Low | Open
515 | NCR | NCR0433 | Stick holding safety pin missing | Low | Open
513 | NCR | NCR0435 | Several devices communcation fail (TCN, CRS, TRS or Netbox and HVAC communication fault), | High | Open
507 | NCR | NCR0436 | HV cable support clamp missing | Low | Open
504 | NCR | NCR0437 | Gangway Panel has scractch &Lock missing | Low | Open
501 | NCR | NCR0438 | Derailment sensor cable clamp missing | Low | Open
410 | NCR | NCR0439 | ONE INTERNAL Gangway COVER MISSING | Low | Open
625 | NCR | NCR0440 | SWD3-V1 half display issue | Low | Open
601 | NCR | NCR0441 | Gangways panels are not able to be closed | Low | Open
502 | NCR | NCR0442 | Found minor leakage from the gearbox drain plug cause by O-ring defect. | Low | Open
407 | NCR | NCR0443 | Found minor leakage from the gearbox inspection cover | Low | Open
412 | NCR | NCR0444 | Gangways panels are missing | Low | Open
410 | NCR | NCR0445 | Gangways panel is missing | Low | Open
609 | NCR | NCR0446 | Gangway locks missing | Low | Open
511 | NCR | NCR0447 | Roof antenna damaged due to hit roller shutter at W5 while movement | Low | Open
607 | NCR | NCR0449 | Gearbox oil axle 3 is contaminated. | Low | Open
607 | NCR | NCR0450 | Gear box oil level is below minimum level | Low | Open
422 | NCR | NCR0452 | LEDI1-V2 offline and dark | Low | Open
611 | NCR | NCR0453 | Battery Door tubular seal some damaged | Low | Open
611 | NCR | NCR0454 | Battery Door External safety label damaged | Low | Open
409 | NCR | NCR1002 | IOS185 : 1 APC LV Status false, IOS179 : 1 APC MV Status false | High | Open
404 | NCR | NCR1056 | Gearbox 1&2 oil level below minimum but no leakage issue observed. | High | Open
401 | NCR | 192711 | I-NVR mask camera | LOW | Open
402 | NCR | 192711 | I-NVR mask camera | LOW | Open
403 | NCR | 192711 | I-NVR mask camera | LOW | Open
404 | NCR | 192711 | I-NVR mask camera | LOW | Open
405 | NCR | 192711 | I-NVR mask camera | LOW | Open
406 | NCR | 192711 | I-NVR mask camera | LOW | Open
407 | NCR | 192711 | I-NVR mask camera | LOW | Open
408 | NCR | 192711 | I-NVR mask camera | LOW | Open
409 | NCR | 192711 | I-NVR mask camera | LOW | Open
410 | NCR | 192711 | I-NVR mask camera | LOW | Open
411 | NCR | 192711 | I-NVR mask camera | LOW | Open
412 | NCR | 192711 | I-NVR mask camera | LOW | Open
413 | NCR | 192711 | I-NVR mask camera | LOW | Open
414 | NCR | 192711 | I-NVR mask camera | LOW | Open
415 | NCR | 192711 | I-NVR mask camera | LOW | Open
416 | NCR | 192711 | I-NVR mask camera | LOW | Open
417 | NCR | 192711 | I-NVR mask camera | LOW | Open
418 | NCR | 192711 | I-NVR mask camera | LOW | Open
419 | NCR | 192711 | I-NVR mask camera | LOW | Open
420 | NCR | 192711 | I-NVR mask camera | LOW | Open
421 | NCR | 192711 | I-NVR mask camera | LOW | Open
422 | NCR | 192711 | I-NVR mask camera | LOW | Open
423 | NCR | 192711 | I-NVR mask camera | LOW | Open
424 | NCR | 192711 | I-NVR mask camera | LOW | Open
501 | NCR | 192711 | I-NVR mask camera | LOW | Open
502 | NCR | 192711 | I-NVR mask camera | LOW | Open
503 | NCR | 192711 | I-NVR mask camera | LOW | Open
504 | NCR | 192711 | I-NVR mask camera | LOW | Open
505 | NCR | 192711 | I-NVR mask camera | LOW | Open
506 | NCR | 192711 | I-NVR mask camera | LOW | Open
507 | NCR | 192711 | I-NVR mask camera | LOW | Open
508 | NCR | 192711 | I-NVR mask camera | LOW | Open
509 | NCR | 192711 | I-NVR mask camera | LOW | Open
510 | NCR | 192711 | I-NVR mask camera | LOW | Open
511 | NCR | 192711 | I-NVR mask camera | LOW | Open
512 | NCR | 192711 | I-NVR mask camera | LOW | Open
513 | NCR | 192711 | I-NVR mask camera | LOW | Open
514 | NCR | 192711 | I-NVR mask camera | LOW | Open
515 | NCR | 192711 | I-NVR mask camera | LOW | Open
516 | NCR | 192711 | I-NVR mask camera | LOW | Open
517 | NCR | 192711 | I-NVR mask camera | LOW | Open
518 | NCR | 192711 | I-NVR mask camera | LOW | Open
519 | NCR | 192711 | I-NVR mask camera | LOW | Open
601 | NCR | 192711 | I-NVR mask camera | LOW | Open
602 | NCR | 192711 | I-NVR mask camera | LOW | Open
603 | NCR | 192711 | I-NVR mask camera | LOW | Open
604 | NCR | 192711 | I-NVR mask camera | LOW | Open
605 | NCR | 192711 | I-NVR mask camera | LOW | Open
606 | NCR | 192711 | I-NVR mask camera | LOW | Open
607 | NCR | 192711 | I-NVR mask camera | LOW | Open
608 | NCR | 192711 | I-NVR mask camera | LOW | Open
609 | NCR | 192711 | I-NVR mask camera | LOW | Open
610 | NCR | 192711 | I-NVR mask camera | LOW | Open
611 | NCR | 192711 | I-NVR mask camera | LOW | Open
612 | NCR | 192711 | I-NVR mask camera | LOW | Open
613 | NCR | 192711 | I-NVR mask camera | LOW | Open
614 | NCR | 192711 | I-NVR mask camera | LOW | Open
615 | NCR | 192711 | I-NVR mask camera | LOW | Open
616 | NCR | 192711 | I-NVR mask camera | LOW | Open
617 | NCR | 192711 | I-NVR mask camera | LOW | Open
618 | NCR | 192711 | I-NVR mask camera | LOW | Open
619 | NCR | 192711 | I-NVR mask camera | LOW | Open
620 | NCR | 192711 | I-NVR mask camera | LOW | Open
621 | NCR | 192711 | I-NVR mask camera | LOW | Open
622 | NCR | 192711 | I-NVR mask camera | LOW | Open
623 | NCR | 192711 | I-NVR mask camera | LOW | Open
624 | NCR | 192711 | I-NVR mask camera | LOW | Open
625 | NCR | 192711 | I-NVR mask camera | LOW | Open
626 | NCR | 192711 | I-NVR mask camera | LOW | Open
603 | NCR | 220211 | Air leakage is observed from the spring brake part. | LOW | Open
601 | NCR | 220211 | Air leakage is observed from the spring brake part. | LOW | Open

## INPUT
TRAIN | TYPE | IMPACT
401 | TIR | LOW
402 | NCR | HIGH
403 | RET | OPEN
404 | SU | MEDIUM | SU0004 | PAPIS
405 |  |  | SU0002 | brake
406 |  |  | SU0003 | HVAC
407 |  |  | SU0005 | TCMS
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626